## Period 1
Period 2 |  | Analysis Date at 17:00
2021-05-05
Task | Real Start Date | Real Duration | Real End Date | Network Days to Analysis Date | Complete/Busy | Full Budget | Planned Value | %Sched Completion | %Actual Completion | Earned Value | Actual Cost | Actual Cost at Analysis Date | Planned Start Date | Network Days to Analysis Date | Planned Duration
Evaluate Market | 2021-03-31 09:00 | 6.69 | 2021-04-08 15:31 | 26 | Complete | 7728 | 7728 | 1 | 1 | 7728 | 8563.2 | 8563.2
Develop Business Opportunity | 2021-04-08 15:31 | 8.06 | 2021-04-20 16:00 | 20 | Complete | 9016 | 9016 | 1 | 1 | 9016 | 10316.8 | 10316.8
Customer Preference Study | 2021-04-20 16:00 | 12.13 | 2021-05-07 08:02 | 12 | Busy | 13524 | 13524 | 1 | 1 | 13524 | 14240 | 14240
Business Evaluation (NPV, etc.) | 2021-05-07 08:02 | 2.38 | 2021-05-11 11:05 | -3 | Busy | 2576 | 2576 | 1 | 1 | 2576 | 4973 | 4973
PM Period 1 | 2021-03-31 09:00 | 18.06 | 2021-04-26 09:29 | 26 | Complete | 12300 | 12300 | 1 | 1 | 12300 | 17734.92 | 17734.92
Milestone 1 | 2021-05-11 11:05 | 0 | 2021-05-11 11:05 | -5 | Busy | 0 | 0 | 1 | 0 | 0 | 0 | 0
Design and Development Plan | 2021-05-11 11:05 | 3.88 | 2021-05-17 10:07 | -5 | Busy | 2352 | 783.9216 | 0.3333 | 0 | 0 | 3585.12 | 0 | 2021-05-05 | 1 | 3
Design Specs | 2021-05-17 10:07 | 13.75 | 2021-06-04 08:07 | -9 | Busy | 8624 | 0 | 0 | 0 | 0 | 12705 | 0
Develop Prelim Marketing Plan | 2021-05-11 11:05 | 2.81 | 2021-05-14 09:34 | -5 | Busy | 3220 | 1288 | 0.4 | 0 | 0 | 3596.8 | 0 | 2021-05-05 | 1 | 2.5
Develop Marketing Program | 2021-05-14 09:34 | 8.44 | 2021-05-26 14:05 | -8 | Busy | 9660 | 0 | 0 | 0 | 0 | 10803.2 | 0
PM Period 2 | 2021-05-11 11:05 | 10.06 | 2021-05-25 11:34 | -5 | Busy | 6888 | 984.2952 | 0.1429 | 0 | 0 | 9878.92 | 0 | 2021-05-05 | 1 | 7
Milestone 2 | 2021-06-04 08:07 | 0 | 2021-06-04 08:07 | -23 | Busy | 0 | 0 | 0 | 0 | 0 | 0 | 0
Totals | [6 empty] | 48200.2168 |  |  | 45144 |  | 55827.92
CPI | 0.8086
SPI | 0.9366
ETC | 3779.6399
EAC | 59607.5599
Formulas:
Network Days to Analysis Date = NETWORKDAYS([Real Start Date],D3)
Network Days to Analysis Date = NETWORKDAYS([Planned Start Date],D3)

## Period 2
Period 2 |  | Analysis Date at 17:00
2021-05-31
Task | Real Start Date | Real Duration | Real End Date | Network Days to Analysis Date | Complete/Busy | Full Budget | Planned Value | %Sched Completion | %Actual Completion | Earned Value | Actual Cost | Actual Cost at Analysis Date | Planned Start Date | Network Days to Analysis Date | Planned Duration
Evaluate Market | 2021-03-31 09:00 | 6.69 | 2021-04-08 15:31 | 44 | Complete | 7728 | 7728 | 1 | 1 | 7728 | 8563.2 | 8563.2
Develop Business Opportunity | 2021-04-08 15:31 | 8.06 | 2021-04-20 16:00 | 38 | Complete | 9016 | 9016 | 1 | 1 | 9016 | 10316.8 | 10316.8
Customer Preference Study | 2021-04-20 16:00 | 12.13 | 2021-05-07 08:02 | 30 | Complete | 13524 | 13524 | 1 | 1 | 13524 | 14240 | 14240
Business Evaluation (NPV, etc.) | 2021-05-07 08:02 | 2.38 | 2021-05-11 11:05 | 17 | Complete | 2576 | 2576 | 1 | 1 | 2576 | 4973 | 4973
PM Period 1 | 2021-03-31 09:00 | 18.06 | 2021-04-26 09:29 | 44 | Complete | 12300 | 12300 | 1 | 1 | 12300 | 17734.92 | 17734.92
Milestone 1 | 2021-05-11 11:05 | 0 | 2021-05-11 11:05 | 15 | Complete | 0 | 0 | 1 | 1 | 0 | 0 | 0
Design and Development Plan | 2021-05-11 11:05 | 3.88 | 2021-05-17 10:07 | 15 | Complete | 2352 | 2352 | 1 | 1 | 2352 | 3585.12 | 3585.12
Design Specs | 2021-05-17 10:07 | 13.75 | 2021-06-04 08:07 | 11 | Busy | 8624 | 8624 | 1 | 0.71 | 6123.04 | 12705 | 9020.55
Develop Prelim Marketing Plan | 2021-05-11 11:05 | 2.81 | 2021-05-14 09:34 | 15 | Complete | 3220 | 3220 | 1 | 1 | 3220 | 3596.8 | 3596.8
Develop Marketing Program | 2021-05-14 09:34 | 8.44 | 2021-05-26 14:05 | 12 | Complete | 9660 | 9660 | 1 | 1 | 9660 | 10803.2 | 10803.2
PM Period 2 | 2021-05-11 11:05 | 10.06 | 2021-05-25 11:34 | 15 | Complete | 6888 | 6888 | 1 | 1 | 6888 | 9878.92 | 9878.92
Milestone 2 | 2021-06-04 08:07 | 0 | 2021-06-04 08:07 | -5 | Busy | 0 | 0 | 1 | 0 | 0 | 5000 | 0
Identify Testing Requirements | 2021-06-04 08:07 | 6.25 | 2021-06-14 10:07 | -5 | Busy | 3920 | 3920 | 1 | 0 | 0 | 5775 | 0 | 2021-05-25 | 5 | 5
Risk Analysis | 2021-06-14 10:07 | 7.06 | 2021-06-23 10:36 | -11 | Busy | 3920 | 0 | 0 | 0 | 0 | 6523.44 | 0
Train Sales Team | 2021-06-04 08:07 | 24.88 | 2021-07-08 16:10 | -5 | Busy | 11088 | 2520.3024 | 0.2273 | 0 | 0 | 12440 | 0 | 2021-05-25 | 5 | 22
Advertising Campaign | 2021-06-04 08:07 | 31.38 | 2021-07-19 11:10 | -5 | Busy | 21952 | 3920.6272 | 0.1786 | 0 | 0 | 24476.4 | 0 | 2021-05-25 | 5 | 28
PM Period 3 | 2021-06-04 08:07 | 10.13 | 2021-06-18 09:10 | -5 | Busy | 6888 | 4920.0984 | 0.7143 | 0 | 0 | 9947.66 | 0 | 2021-05-25 | 5 | 7
Milestone 3 | 2021-07-19 11:10 | 0 | 2021-07-19 11:10 | -36 | Busy | 0 | 0 | 1 | 1 | 0 | 0 | 0
Totals | [6 empty] | 91169.028 |  |  | 73387.04 |  | 92712.51
CPI | 0.7916
SPI | 0.805
ETC | 22463.3502
EAC | 115175.8602
Formulas:
Network Days to Analysis Date = NETWORKDAYS([Real Start Date],D3)
Network Days to Analysis Date = NETWORKDAYS([Planned Start Date],D3)

## Period 3
Period 3 |  | Analysis Date at 17:00
2021-07-13
Task | Real Start Date | Real Duration | Real End Date | Network Days to Analysis Date | Complete/Busy | Full Budget | Planned Value | %Sched Completion | %Actual Completion | Earned Value | Actual Cost | Actual Cost at Analysis Date | Planned Start Date | Network Days to Analysis Date | Planned Duration
Evaluate Market | 2021-03-31 09:00 | 6.69 | 2021-04-08 15:31 | 75 | Complete | 7728 | 7728 | 1 | 1 | 7728 | 8563.2 | 8563.2
Develop Business Opportunity | 2021-04-08 15:31 | 8.06 | 2021-04-20 16:00 | 69 | Complete | 9016 | 9016 | 1 | 1 | 9016 | 10316.8 | 10316.8
Customer Preference Study | 2021-04-20 16:00 | 12.13 | 2021-05-07 08:02 | 61 | Complete | 13524 | 13524 | 1 | 1 | 13524 | 14240 | 14240
Business Evaluation (NPV, etc.) | 2021-05-07 08:02 | 2.38 | 2021-05-11 11:05 | 48 | Complete | 2576 | 2576 | 1 | 1 | 2576 | 4973 | 4973
PM Period 1 | 2021-03-31 09:00 | 18.06 | 2021-04-26 09:29 | 75 | Complete | 12300 | 12300 | 1 | 1 | 12300 | 17734.92 | 17734.92
Milestone 1 | 2021-05-11 11:05 | 0 | 2021-05-11 11:05 | 46 | Complete | 0 | 0 | 1 | 1 | 0 | 0 | 0
Design and Development Plan | 2021-05-11 11:05 | 3.88 | 2021-05-17 10:07 | 46 | Complete | 2352 | 2352 | 1 | 1 | 2352 | 3585.12 | 3585.12
Design Specs | 2021-05-17 10:07 | 13.75 | 2021-06-04 08:07 | 42 | Complete | 8624 | 8624 | 1 | 1 | 8624 | 12705 | 12705
Develop Prelim Marketing Plan | 2021-05-11 11:05 | 2.81 | 2021-05-14 09:34 | 46 | Complete | 3220 | 3220 | 1 | 1 | 3220 | 3596.8 | 3596.8
Develop Marketing Program | 2021-05-14 09:34 | 8.44 | 2021-05-26 14:05 | 43 | Complete | 9660 | 9660 | 1 | 1 | 9660 | 10803.2 | 10803.2
PM Period 2 | 2021-05-11 11:05 | 10.06 | 2021-05-25 11:34 | 46 | Complete | 6888 | 6888 | 1 | 1 | 6888 | 9878.92 | 9878.92
Milestone 2 | 2021-06-04 08:07 | 0 | 2021-06-04 08:07 | 28 | Complete | 0 | 0 | 1 | 1 | 0 | 5000 | 5000
Identify Testing Requirements | 2021-06-04 08:07 | 6.25 | 2021-06-14 10:07 | 28 | Complete | 3920 | 3920 | 1 | 1 | 3920 | 5775 | 5775
Risk Analysis | 2021-06-14 10:07 | 7.06 | 2021-06-23 10:36 | 22 | Complete | 3920 | 3920 | 1 | 1 | 3920 | 6523.44 | 6523.44
Train Sales Team | 2021-06-04 08:07 | 24.88 | 2021-07-08 16:10 | 28 | Complete | 11088 | 11088 | 1 | 1 | 11088 | 12440 | 12440
Advertising Campaign | 2021-06-04 08:07 | 31.38 | 2021-07-19 11:10 | 28 | Busy | 21952 | 21952 | 1 | 0.89 | 19537.28 | 24476.4 | 21783.996
PM Period 3 | 2021-06-04 08:07 | 10.13 | 2021-06-18 09:10 | 28 | Complete | 6888 | 6888 | 1 | 1 | 6888 | 9947.66 | 9947.66
Milestone 3 | 2021-07-19 11:10 | 0 | 2021-07-19 11:10 | -5 | Busy | 0 | 0 | 1 | 0 | 0 | 0 | 0
Design Labelling | 2021-07-14 08:07 | 3.25 | 2021-07-19 10:07 | -2 | Busy | 1960 | 1960 | 1 | 0 | 0 | 3003 | 0
Approve Design | 2021-07-19 10:07 | 2.63 | 2021-07-21 16:10 | -5 | Busy | 1568 | 1568 | 1 | 0 | 0 | 2430.12 | 0
Initial Engineering Specs | 2021-07-21 16:10 | 2.88 | 2021-07-26 15:12 | -7 | Busy | 2460 | 2460 | 1 | 0 | 0 | 2828.16 | 0
PM Period 4 | 2021-07-19 11:10 | 14.63 | 2021-08-09 08:12 | -5 | Busy | 10192 | 6272.1568 | 0.6154 | 0 | 0 | 11411.4 | 0 | 2021-07-02 | 8 | 13
Milestone 4 | 2021-08-09 08:12 | 0 | 2021-08-09 08:12 | -20 | Busy | 0 | 0 | 1 | 0 | 0 | -50000 | 0
Totals | [6 empty] | 135916.1568 |  |  | 121241.28 |  | 157867.056
CPI | 0.768
SPI | 0.892
ETC | 19107.9125
EAC | 176974.9685
Formulas:
Network Days to Analysis Date = NETWORKDAYS([Real Start Date],D3)
Network Days to Analysis Date = NETWORKDAYS([Planned Start Date],D3)

## Period 4
Period 4 |  | Analysis Date at 17:00
2021-08-03
Task | Real Start Date | Real Duration | Real End Date | Network Days to Analysis Date | Complete/Busy | Full Budget | Planned Value | %Sched Completion | %Actual Completion | Earned Value | Actual Cost | Actual Cost at Analysis Date | Planned Start Date | Network Days to Analysis Date | Planned Duration
Evaluate Market | 2021-03-31 09:00 | 6.69 | 2021-04-08 15:31 | 90 | Complete | 7728 | 7728 | 1 | 1 | 7728 | 8563.2 | 8563.2
Develop Business Opportunity | 2021-04-08 15:31 | 8.06 | 2021-04-20 16:00 | 84 | Complete | 9016 | 9016 | 1 | 1 | 9016 | 10316.8 | 10316.8
Customer Preference Study | 2021-04-20 16:00 | 12.13 | 2021-05-07 08:02 | 76 | Complete | 13524 | 13524 | 1 | 1 | 13524 | 14240 | 14240
Business Evaluation (NPV, etc.) | 2021-05-07 08:02 | 2.38 | 2021-05-11 11:05 | 63 | Complete | 2576 | 2576 | 1 | 1 | 2576 | 4973 | 4973
PM Period 1 | 2021-03-31 09:00 | 18.06 | 2021-04-26 09:29 | 90 | Complete | 12300 | 12300 | 1 | 1 | 12300 | 17734.92 | 17734.92
Milestone 1 | 2021-05-11 11:05 | 0 | 2021-05-11 11:05 | 61 | Complete | 0 | 0 | 1 | 1 | 0 | 0 | 0
Design and Development Plan | 2021-05-11 11:05 | 3.88 | 2021-05-17 10:07 | 61 | Complete | 2352 | 2352 | 1 | 1 | 2352 | 3585.12 | 3585.12
Design Specs | 2021-05-17 10:07 | 13.75 | 2021-06-04 08:07 | 57 | Complete | 8624 | 8624 | 1 | 1 | 8624 | 12705 | 12705
Develop Prelim Marketing Plan | 2021-05-11 11:05 | 2.81 | 2021-05-14 09:34 | 61 | Complete | 3220 | 3220 | 1 | 1 | 3220 | 3596.8 | 3596.8
Develop Marketing Program | 2021-05-14 09:34 | 8.44 | 2021-05-26 14:05 | 58 | Complete | 9660 | 9660 | 1 | 1 | 9660 | 10803.2 | 10803.2
PM Period 2 | 2021-05-11 11:05 | 10.06 | 2021-05-25 11:34 | 61 | Complete | 6888 | 6888 | 1 | 1 | 6888 | 9878.92 | 9878.92
Milestone 2 | 2021-06-04 08:07 | 0 | 2021-06-04 08:07 | 43 | Complete | 0 | 0 | 1 | 1 | 0 | 5000 | 5000
Identify Testing Requirements | 2021-06-04 08:07 | 6.25 | 2021-06-14 10:07 | 43 | Complete | 3920 | 3920 | 1 | 1 | 3920 | 5775 | 5775
Risk Analysis | 2021-06-14 10:07 | 7.06 | 2021-06-23 10:36 | 37 | Complete | 3920 | 3920 | 1 | 1 | 3920 | 6523.44 | 6523.44
Train Sales Team | 2021-06-04 08:07 | 24.88 | 2021-07-08 16:10 | 43 | Complete | 11088 | 11088 | 1 | 1 | 11088 | 12440 | 12440
Advertising Campaign | 2021-06-04 08:07 | 31.38 | 2021-07-19 11:10 | 43 | Complete | 21952 | 21952 | 1 | 1 | 21952 | 24476.4 | 24476.4
PM Period 3 | 2021-06-04 08:07 | 10.13 | 2021-06-18 09:10 | 43 | Complete | 6888 | 6888 | 1 | 1 | 6888 | 9947.66 | 9947.66
Milestone 3 | 2021-07-19 11:10 | 0 | 2021-07-19 11:10 | 12 | Complete | 0 | 0 | 1 | 1 | 0 | 0 | 0
Design Labelling | 2021-07-14 08:07 | 3.25 | 2021-07-19 10:07 | 15 | Complete | 1960 | 1960 | 1 | 1 | 1960 | 3003 | 3003
Approve Design | 2021-07-19 10:07 | 2.63 | 2021-07-21 16:10 | 12 | Complete | 1568 | 1568 | 1 | 1 | 1568 | 2430.12 | 2430.12
Initial Engineering Specs | 2021-07-21 16:10 | 2.88 | 2021-07-26 15:12 | 10 | Complete | 2460 | 2460 | 1 | 1 | 2460 | 2828.16 | 2828.16
PM Period 4 | 2021-07-19 11:10 | 14.63 | 2021-08-09 08:12 | 12 | Busy | 10192 | 10192 | 1 | 0.79 | 8051.68 | 11411.4 | 9015.006
Milestone 4 | 2021-08-09 08:12 | 0 | 2021-08-09 08:12 | -5 | Busy | 0 | 0 | 1 | 0 | 0 | -50000 | 0
Design Verification Activities | 2021-08-09 08:12 | 4.19 | 2021-08-13 09:43 | -5 | Busy | 3444 | 3444 | 1 | 0 | 0 | 4114.58 | 0
Verification Design Review | 2021-08-13 09:43 | 2.31 | 2021-08-17 13:12 | -9 | Busy | 1968 | 1968 | 1 | 0 | 0 | 2268.42 | 0
Release Pre-Production Specs | 2021-08-17 13:12 | 6 | 2021-08-25 13:12 | -11 | Busy | 4920 | 3280.164 | 0.6667 | 0 | 0 | 5892 | 0 | 2021-07-29 | 4 | 6
PM Period 5 | 2021-08-09 08:12 | 17 | 2021-09-01 08:12 | -5 | Busy | 11760 | 7840.392 | 0.6667 | 0 | 0 | 13260 | 0 | 2021-07-21 | 10 | 15
Milestone 5 | 2021-09-01 08:12 | 0 | 2021-09-01 08:12 | -22 | Busy | 0 | 0 | 0 | 0 | 0 | 15000 | 0
Totals | [6 empty] | 156368.556 |  |  | 137695.68 |  | 177835.746
CPI | 0.7743
SPI | 0.8806
ETC | 24115.8156
EAC | 201951.5616
Formulas:
Network Days to Analysis Date = NETWORKDAYS([Real Start Date],D3)
Network Days to Analysis Date = NETWORKDAYS([Planned Start Date],D3)

## Period 5
Period 5 |  | Analysis Date at 17:00
2021-08-26
Task | Real Start Date | Real Duration | Real End Date | Network Days to Analysis Date | Complete/Busy | Full Budget | Planned Value | %Sched Completion | %Actual Completion | Earned Value | Actual Cost | Actual Cost at Analysis Date | Planned Start Date | Network Days to Analysis Date | Planned Duration
Evaluate Market | 2021-03-31 09:00 | 6.69 | 2021-04-08 15:31 | 107 | Complete | 7728 | 7728 | 1 | 1 | 7728 | 8563.2 | 8563.2
Develop Business Opportunity | 2021-04-08 15:31 | 8.06 | 2021-04-20 16:00 | 101 | Complete | 9016 | 9016 | 1 | 1 | 9016 | 10316.8 | 10316.8
Customer Preference Study | 2021-04-20 16:00 | 12.13 | 2021-05-07 08:02 | 93 | Complete | 13524 | 13524 | 1 | 1 | 13524 | 14240 | 14240
Business Evaluation (NPV, etc.) | 2021-05-07 08:02 | 2.38 | 2021-05-11 11:05 | 80 | Complete | 2576 | 2576 | 1 | 1 | 2576 | 4973 | 4973
PM Period 1 | 2021-03-31 09:00 | 18.06 | 2021-04-26 09:29 | 107 | Complete | 12300 | 12300 | 1 | 1 | 12300 | 17734.92 | 17734.92
Milestone 1 | 2021-05-11 11:05 | 0 | 2021-05-11 11:05 | 78 | Complete | 0 | 0 | 1 | 1 | 0 | 0 | 0
Design and Development Plan | 2021-05-11 11:05 | 3.88 | 2021-05-17 10:07 | 78 | Complete | 2352 | 2352 | 1 | 1 | 2352 | 3585.12 | 3585.12
Design Specs | 2021-05-17 10:07 | 13.75 | 2021-06-04 08:07 | 74 | Complete | 8624 | 8624 | 1 | 1 | 8624 | 12705 | 12705
Develop Prelim Marketing Plan | 2021-05-11 11:05 | 2.81 | 2021-05-14 09:34 | 78 | Complete | 3220 | 3220 | 1 | 1 | 3220 | 3596.8 | 3596.8
Develop Marketing Program | 2021-05-14 09:34 | 8.44 | 2021-05-26 14:05 | 75 | Complete | 9660 | 9660 | 1 | 1 | 9660 | 10803.2 | 10803.2
PM Period 2 | 2021-05-11 11:05 | 10.06 | 2021-05-25 11:34 | 78 | Complete | 6888 | 6888 | 1 | 1 | 6888 | 9878.92 | 9878.92
Milestone 2 | 2021-06-04 08:07 | 0 | 2021-06-04 08:07 | 60 | Complete | 0 | 0 | 1 | 1 | 0 | 5000 | 5000
Identify Testing Requirements | 2021-06-04 08:07 | 6.25 | 2021-06-14 10:07 | 60 | Complete | 3920 | 3920 | 1 | 1 | 3920 | 5775 | 5775
Risk Analysis | 2021-06-14 10:07 | 7.06 | 2021-06-23 10:36 | 54 | Complete | 3920 | 3920 | 1 | 1 | 3920 | 6523.44 | 6523.44
Train Sales Team | 2021-06-04 08:07 | 24.88 | 2021-07-08 16:10 | 60 | Complete | 11088 | 11088 | 1 | 1 | 11088 | 12440 | 12440
Advertising Campaign | 2021-06-04 08:07 | 31.38 | 2021-07-19 11:10 | 60 | Complete | 21952 | 21952 | 1 | 1 | 21952 | 24476.4 | 24476.4
PM Period 3 | 2021-06-04 08:07 | 10.13 | 2021-06-18 09:10 | 60 | Complete | 6888 | 6888 | 1 | 1 | 6888 | 9947.66 | 9947.66
Milestone 3 | 2021-07-19 11:10 | 0 | 2021-07-19 11:10 | 29 | Complete | 0 | 0 | 1 | 1 | 0 | 0 | 0
Design Labelling | 2021-07-14 08:07 | 3.25 | 2021-07-19 10:07 | 32 | Complete | 1960 | 1960 | 1 | 1 | 1960 | 3003 | 3003
Approve Design | 2021-07-19 10:07 | 2.63 | 2021-07-21 16:10 | 29 | Complete | 1568 | 1568 | 1 | 1 | 1568 | 2430.12 | 2430.12
Initial Engineering Specs | 2021-07-21 16:10 | 2.88 | 2021-07-26 15:12 | 27 | Complete | 2460 | 2460 | 1 | 1 | 2460 | 2828.16 | 2828.16
PM Period 4 | 2021-07-19 11:10 | 14.63 | 2021-08-09 08:12 | 29 | Complete | 10192 | 10192 | 1 | 1 | 10192 | 11411.4 | 11411.4
Milestone 4 | 2021-08-09 08:12 | 0 | 2021-08-09 08:12 | 14 | Complete | 0 | 0 | 1 | 1 | 0 | -50000 | -50000
Design Verification Activities | 2021-08-09 08:12 | 4.19 | 2021-08-13 09:43 | 14 | Complete | 3444 | 3444 | 1 | 1 | 3444 | 4114.58 | 4114.58
Verification Design Review | 2021-08-13 09:43 | 2.31 | 2021-08-17 13:12 | 10 | Complete | 1968 | 1968 | 1 | 1 | 1968 | 2268.42 | 2268.42
Release Pre-Production Specs | 2021-08-17 13:12 | 6 | 2021-08-25 13:12 | 8 | Complete | 4920 | 4920 | 1 | 1 | 4920 | 5892 | 5892
PM Period 5 | 2021-08-09 08:12 | 17 | 2021-09-01 08:12 | 14 | Busy | 11760 | 11760 | 1 | 0.82 | 9643.2 | 13260 | 10873.2
Milestone 5 | 2021-09-01 08:12 | 0 | 2021-09-01 08:12 | -5 | Busy | 0 | 0 | 0 | 0 | 0 | 15000 | 0
Identify Vendors | 2021-09-01 08:12 | 4.5 | 2021-09-07 13:12 | -5 | Busy | 2800 | 2800 | 1 | 0 | 0 | 3528 | 0
Develop and Issue RFQ | 2021-09-07 13:12 | 3.88 | 2021-09-13 09:02 | -9 | Busy | 2400 | 1999.92 | 0.8333 | 0 | 0 | 3041.92 | 0 | 2021-08-20 | 5 | 6
Build Functional Model | 2021-09-01 08:12 | 11.25 | 2021-09-16 10:12 | -5 | Busy | 8856 | 8856 | 1 | 0 | 0 | 11047.5 | 0
Evaluate Design Specs | 2021-09-01 08:12 | 14.88 | 2021-09-21 16:14 | -5 | Busy | 6000 | 6000 | 1 | 0 | 0 | 8928 | 0
PM Period 6 | 2021-09-01 08:12 | 10.25 | 2021-09-15 10:12 | -5 | Busy | 7056 | 7056 | 1 | 0 | 0 | 7995 | 0
Milestone 6 | 2021-09-15 10:12 | 0 | 2021-09-15 10:12 | -15 | Busy | 0 | 0 | 0 | 0 | 0 | 0 | 0
Totals | [6 empty] | 188639.92 |  |  | 159811.2 |  | 153380.34
CPI | 1.0419
SPI | 0.8472
ETC | 27669.3733
EAC | 181049.7133
Formulas:
Network Days to Analysis Date = NETWORKDAYS([Real Start Date],D3)
Network Days to Analysis Date = NETWORKDAYS([Planned Start Date],D3)

## Period 6
Period 6 |  | Analysis Date at 17:00
2021-09-15
Task | Real Start Date | Real Duration | Real End Date | Network Days to Analysis Date | Complete/Busy | Full Budget | Planned Value | %Sched Completion | %Actual Completion | Earned Value | Actual Cost | Actual Cost at Analysis Date | Planned Start Date | Network Days to Analysis Date | Planned Duration
Evaluate Market | 2021-03-31 09:00 | 6.69 | 2021-04-08 15:31 | 121 | Complete | 7728 | 7728 | 1 | 1 | 7728 | 8563.2 | 8563.2
Develop Business Opportunity | 2021-04-08 15:31 | 8.06 | 2021-04-20 16:00 | 115 | Complete | 9016 | 9016 | 1 | 1 | 9016 | 10316.8 | 10316.8
Customer Preference Study | 2021-04-20 16:00 | 12.13 | 2021-05-07 08:02 | 107 | Complete | 13524 | 13524 | 1 | 1 | 13524 | 14240 | 14240
Business Evaluation (NPV, etc.) | 2021-05-07 08:02 | 2.38 | 2021-05-11 11:05 | 94 | Complete | 2576 | 2576 | 1 | 1 | 2576 | 4973 | 4973
PM Period 1 | 2021-03-31 09:00 | 18.06 | 2021-04-26 09:29 | 121 | Complete | 12300 | 12300 | 1 | 1 | 12300 | 17734.92 | 17734.92
Milestone 1 | 2021-05-11 11:05 | 0 | 2021-05-11 11:05 | 92 | Complete | 0 | 0 | 1 | 1 | 0 | 0 | 0
Design and Development Plan | 2021-05-11 11:05 | 3.88 | 2021-05-17 10:07 | 92 | Complete | 2352 | 2352 | 1 | 1 | 2352 | 3585.12 | 3585.12
Design Specs | 2021-05-17 10:07 | 13.75 | 2021-06-04 08:07 | 88 | Complete | 8624 | 8624 | 1 | 1 | 8624 | 12705 | 12705
Develop Prelim Marketing Plan | 2021-05-11 11:05 | 2.81 | 2021-05-14 09:34 | 92 | Complete | 3220 | 3220 | 1 | 1 | 3220 | 3596.8 | 3596.8
Develop Marketing Program | 2021-05-14 09:34 | 8.44 | 2021-05-26 14:05 | 89 | Complete | 9660 | 9660 | 1 | 1 | 9660 | 10803.2 | 10803.2
PM Period 2 | 2021-05-11 11:05 | 10.06 | 2021-05-25 11:34 | 92 | Complete | 6888 | 6888 | 1 | 1 | 6888 | 9878.92 | 9878.92
Milestone 2 | 2021-06-04 08:07 | 0 | 2021-06-04 08:07 | 74 | Complete | 0 | 0 | 1 | 1 | 0 | 5000 | 5000
Identify Testing Requirements | 2021-06-04 08:07 | 6.25 | 2021-06-14 10:07 | 74 | Complete | 3920 | 3920 | 1 | 1 | 3920 | 5775 | 5775
Risk Analysis | 2021-06-14 10:07 | 7.06 | 2021-06-23 10:36 | 68 | Complete | 3920 | 3920 | 1 | 1 | 3920 | 6523.44 | 6523.44
Train Sales Team | 2021-06-04 08:07 | 24.88 | 2021-07-08 16:10 | 74 | Complete | 11088 | 11088 | 1 | 1 | 11088 | 12440 | 12440
Advertising Campaign | 2021-06-04 08:07 | 31.38 | 2021-07-19 11:10 | 74 | Complete | 21952 | 21952 | 1 | 1 | 21952 | 24476.4 | 24476.4
PM Period 3 | 2021-06-04 08:07 | 10.13 | 2021-06-18 09:10 | 74 | Complete | 6888 | 6888 | 1 | 1 | 6888 | 9947.66 | 9947.66
Milestone 3 | 2021-07-19 11:10 | 0 | 2021-07-19 11:10 | 43 | Complete | 0 | 0 | 1 | 1 | 0 | 0 | 0
Design Labelling | 2021-07-14 08:07 | 3.25 | 2021-07-19 10:07 | 46 | Complete | 1960 | 1960 | 1 | 1 | 1960 | 3003 | 3003
Approve Design | 2021-07-19 10:07 | 2.63 | 2021-07-21 16:10 | 43 | Complete | 1568 | 1568 | 1 | 1 | 1568 | 2430.12 | 2430.12
Initial Engineering Specs | 2021-07-21 16:10 | 2.88 | 2021-07-26 15:12 | 41 | Complete | 2460 | 2460 | 1 | 1 | 2460 | 2828.16 | 2828.16
PM Period 4 | 2021-07-19 11:10 | 14.63 | 2021-08-09 08:12 | 43 | Complete | 10192 | 10192 | 1 | 1 | 10192 | 11411.4 | 11411.4
Milestone 4 | 2021-08-09 08:12 | 0 | 2021-08-09 08:12 | 28 | Complete | 0 | 0 | 1 | 1 | 0 | -50000 | -50000
Design Verification Activities | 2021-08-09 08:12 | 4.19 | 2021-08-13 09:43 | 28 | Complete | 3444 | 3444 | 1 | 1 | 3444 | 4114.58 | 4114.58
Verification Design Review | 2021-08-13 09:43 | 2.31 | 2021-08-17 13:12 | 24 | Complete | 1968 | 1968 | 1 | 1 | 1968 | 2268.42 | 2268.42
Release Pre-Production Specs | 2021-08-17 13:12 | 6 | 2021-08-25 13:12 | 22 | Complete | 4920 | 4920 | 1 | 1 | 4920 | 5892 | 5892
PM Period 5 | 2021-08-09 08:12 | 17 | 2021-09-01 08:12 | 28 | Complete | 11760 | 11760 | 1 | 1 | 11760 | 13260 | 13260
Milestone 5 | 2021-09-01 08:12 | 0 | 2021-09-01 08:12 | 11 | Complete | 0 | 0 | 1 | 1 | 0 | 15000 | 15000
Identify Vendors | 2021-09-01 08:12 | 4.5 | 2021-09-07 13:12 | 11 | Complete | 2800 | 2800 | 1 | 1 | 2800 | 3528 | 3528
Develop and Issue RFQ | 2021-09-07 13:12 | 3.88 | 2021-09-13 09:02 | 7 | Complete | 2400 | 2400 | 1 | 1 | 2400 | 3041.92 | 3041.92
Build Functional Model | 2021-09-01 08:12 | 11.25 | 2021-09-16 10:12 | 11 | Busy | 8856 | 8856 | 1 | 1 | 8856 | 11047.5 | 11047.5
Evaluate Design Specs | 2021-09-01 08:12 | 14.88 | 2021-09-21 16:14 | 11 | Busy | 6000 | 6000 | 1 | 0.74 | 4440 | 8928 | 6606.72
PM Period 6 | 2021-09-01 08:12 | 10.25 | 2021-09-15 10:12 | 11 | Complete | 7056 | 7056 | 1 | 1 | 7056 | 7995 | 7995
Milestone 6 | 2021-09-21 16:14 | 0 | 2021-09-21 16:14 | -5 | Busy | 0 | 0 | 1 | 0 | 0 | 0 | 0
Issue Sample | 2021-09-21 16:14 | 7.5 | 2021-10-01 11:14 | -5 | Busy | 3000 | 3000 | 1 | 0 | 0 | 4500 | 0
Perform Supplier Process Capability | 2021-10-01 11:14 | 17.13 | 2021-10-26 13:17 | -13 | Busy | 6608 | 6608 | 1 | 0 | 0 | 9250 | 0
Develop Testing Protocol for Prototype | 2021-09-21 16:14 | 10.25 | 2021-10-06 09:14 | -5 | Busy | 3520 | 3520 | 1 | 0 | 0 | 4530.5 | 0
PM Period 7 | 2021-09-21 16:14 | 12.5 | 2021-10-08 11:14 | -5 | Busy | 8624 | 8624 | 1 | 0 | 0 | 9750 | 0
Milestone 7 | 2021-09-21 16:14 | 0 | 2021-09-21 16:14 | -5 | Busy | 0 | 0 | 1 | 0 | 0 | 35000 | 0
Approve Sample Parts | 2021-10-26 13:17 | 10.13 | 2021-11-09 14:19 | -30 | Busy | 4352 | 544 | 0.125 | 0 | 0 | 6078 | 0 | 2021-09-15 | 1 | 8
Design Validation Activities | 2021-11-12 10:17 | 3.06 | 2021-11-16 16:02 | -43 | Busy | 2200 | 440 | 0.2 | 0 | 0 | 5635.52 | 0 | 2021-09-15 | 1 | 5
Test Prototype | 2021-10-26 13:17 | 12.75 | 2021-11-12 10:17 | -30 | Busy | 6000 | 600 | 0.1 | 0 | 0 | 5635.5 | 0 | 2021-09-15 | 1 | 10
Process Engineering Plan | 2021-10-26 13:17 | 17.63 | 2021-11-19 09:19 | -30 | Busy | 6000 | 400.2 | 0.0667 | 0 | 0 | 7811.1 | 0 | 2021-09-15 | 1 | 15
Show Functional Model at Trade Show | 2021-11-01 08:00 | 3.25 | 2021-11-04 10:00 | -34 | Busy | 2352 | 0 | 0 | 0 | 0 | 2535 | 0
PM Period 8 | 2021-10-26 13:17 | 3.38 | 2021-10-29 16:19 | -30 | Busy | 2352 | 783.9216 | 0.3333 | 0 | 0 | 2636.4 | 0 | 2021-09-15 | 1 | 3
Milestone 8 | 2021-11-19 09:19 | 0 | 2021-11-19 09:19 | -48 | Busy | 0 | 0 | 0 | 0 | 0 | 0 | 0
Totals | [6 empty] | 213560.1216 |  |  | 187480 |  | 202986.28
CPI | 0.9236
SPI | 0.8779
ETC | 28237.4638
EAC | 231223.7438
Formulas:
Network Days to Analysis Date = NETWORKDAYS([Real Start Date],D3)
Network Days to Analysis Date = NETWORKDAYS([Planned Start Date],D3)

## Period 7
Period 7 |  | Analysis Date at 17:00
2021-10-20
Task | Real Start Date | Real Duration | Real End Date | Network Days to Analysis Date | Complete/Busy | Full Budget | Planned Value | %Sched Completion | %Actual Completion | Earned Value | Actual Cost | Actual Cost at Analysis Date | Planned Start Date | Network Days to Analysis Date | Planned Duration
Evaluate Market | 2021-03-31 09:00 | 6.69 | 2021-04-08 15:31 | 146 | Complete | 7728 | 7728 | 1 | 1 | 7728 | 8563.2 | 8563.2
Develop Business Opportunity | 2021-04-08 15:31 | 8.06 | 2021-04-20 16:00 | 140 | Complete | 9016 | 9016 | 1 | 1 | 9016 | 10316.8 | 10316.8
Customer Preference Study | 2021-04-20 16:00 | 12.13 | 2021-05-07 08:02 | 132 | Complete | 13524 | 13524 | 1 | 1 | 13524 | 14240 | 14240
Business Evaluation (NPV, etc.) | 2021-05-07 08:02 | 2.38 | 2021-05-11 11:05 | 119 | Complete | 2576 | 2576 | 1 | 1 | 2576 | 4973 | 4973
PM Period 1 | 2021-03-31 09:00 | 18.06 | 2021-04-26 09:29 | 146 | Complete | 12300 | 12300 | 1 | 1 | 12300 | 17734.92 | 17734.92
Milestone 1 | 2021-05-11 11:05 | 0 | 2021-05-11 11:05 | 117 | Complete | 0 | 0 | 1 | 1 | 0 | 0 | 0
Design and Development Plan | 2021-05-11 11:05 | 3.88 | 2021-05-17 10:07 | 117 | Complete | 2352 | 2352 | 1 | 1 | 2352 | 3585.12 | 3585.12
Design Specs | 2021-05-17 10:07 | 13.75 | 2021-06-04 08:07 | 113 | Complete | 8624 | 8624 | 1 | 1 | 8624 | 12705 | 12705
Develop Prelim Marketing Plan | 2021-05-11 11:05 | 2.81 | 2021-05-14 09:34 | 117 | Complete | 3220 | 3220 | 1 | 1 | 3220 | 3596.8 | 3596.8
Develop Marketing Program | 2021-05-14 09:34 | 8.44 | 2021-05-26 14:05 | 114 | Complete | 9660 | 9660 | 1 | 1 | 9660 | 10803.2 | 10803.2
PM Period 2 | 2021-05-11 11:05 | 10.06 | 2021-05-25 11:34 | 117 | Complete | 6888 | 6888 | 1 | 1 | 6888 | 9878.92 | 9878.92
Milestone 2 | 2021-06-04 08:07 | 0 | 2021-06-04 08:07 | 99 | Complete | 0 | 0 | 1 | 1 | 0 | 5000 | 5000
Identify Testing Requirements | 2021-06-04 08:07 | 6.25 | 2021-06-14 10:07 | 99 | Complete | 3920 | 3920 | 1 | 1 | 3920 | 5775 | 5775
Risk Analysis | 2021-06-14 10:07 | 7.06 | 2021-06-23 10:36 | 93 | Complete | 3920 | 3920 | 1 | 1 | 3920 | 6523.44 | 6523.44
Train Sales Team | 2021-06-04 08:07 | 24.88 | 2021-07-08 16:10 | 99 | Complete | 11088 | 11088 | 1 | 1 | 11088 | 12440 | 12440
Advertising Campaign | 2021-06-04 08:07 | 31.38 | 2021-07-19 11:10 | 99 | Complete | 21952 | 21952 | 1 | 1 | 21952 | 24476.4 | 24476.4
PM Period 3 | 2021-06-04 08:07 | 10.13 | 2021-06-18 09:10 | 99 | Complete | 6888 | 6888 | 1 | 1 | 6888 | 9947.66 | 9947.66
Milestone 3 | 2021-07-19 11:10 | 0 | 2021-07-19 11:10 | 68 | Complete | 0 | 0 | 1 | 1 | 0 | 0 | 0
Design Labelling | 2021-07-14 08:07 | 3.25 | 2021-07-19 10:07 | 71 | Complete | 1960 | 1960 | 1 | 1 | 1960 | 3003 | 3003
Approve Design | 2021-07-19 10:07 | 2.63 | 2021-07-21 16:10 | 68 | Complete | 1568 | 1568 | 1 | 1 | 1568 | 2430.12 | 2430.12
Initial Engineering Specs | 2021-07-21 16:10 | 2.88 | 2021-07-26 15:12 | 66 | Complete | 2460 | 2460 | 1 | 1 | 2460 | 2828.16 | 2828.16
PM Period 4 | 2021-07-19 11:10 | 14.63 | 2021-08-09 08:12 | 68 | Complete | 10192 | 10192 | 1 | 1 | 10192 | 11411.4 | 11411.4
Milestone 4 | 2021-08-09 08:12 | 0 | 2021-08-09 08:12 | 53 | Complete | 0 | 0 | 1 | 1 | 0 | -50000 | -50000
Design Verification Activities | 2021-08-09 08:12 | 4.19 | 2021-08-13 09:43 | 53 | Complete | 3444 | 3444 | 1 | 1 | 3444 | 4114.58 | 4114.58
Verification Design Review | 2021-08-13 09:43 | 2.31 | 2021-08-17 13:12 | 49 | Complete | 1968 | 1968 | 1 | 1 | 1968 | 2268.42 | 2268.42
Release Pre-Production Specs | 2021-08-17 13:12 | 6 | 2021-08-25 13:12 | 47 | Complete | 4920 | 4920 | 1 | 1 | 4920 | 5892 | 5892
PM Period 5 | 2021-08-09 08:12 | 17 | 2021-09-01 08:12 | 53 | Complete | 11760 | 11760 | 1 | 1 | 11760 | 13260 | 13260
Milestone 5 | 2021-09-01 08:12 | 0 | 2021-09-01 08:12 | 36 | Complete | 0 | 0 | 1 | 1 | 0 | 15000 | 15000
Identify Vendors | 2021-09-01 08:12 | 4.5 | 2021-09-07 13:12 | 36 | Complete | 2800 | 2800 | 1 | 1 | 2800 | 3528 | 3528
Develop and Issue RFQ | 2021-09-07 13:12 | 3.88 | 2021-09-13 09:02 | 32 | Complete | 2400 | 2400 | 1 | 1 | 2400 | 3041.92 | 3041.92
Build Functional Model | 2021-09-01 08:12 | 11.25 | 2021-09-16 10:12 | 36 | Complete | 8856 | 8856 | 1 | 1 | 8856 | 11047.5 | 11047.5
Evaluate Design Specs | 2021-09-01 08:12 | 14.88 | 2021-09-21 16:14 | 36 | Complete | 6000 | 6000 | 1 | 1 | 6000 | 8928 | 8928
PM Period 6 | 2021-09-01 08:12 | 10.25 | 2021-09-15 10:12 | 36 | Complete | 7056 | 7056 | 1 | 1 | 7056 | 7995 | 7995
Milestone 6 | 2021-09-21 16:14 | 0 | 2021-09-21 16:14 | 22 | Complete | 0 | 0 | 1 | 1 | 0 | 0 | 0
Issue Sample | 2021-09-21 16:14 | 7.5 | 2021-10-01 11:14 | 22 | Complete | 3000 | 3000 | 1 | 1 | 3000 | 4500 | 4500
Perform Supplier Process Capability | 2021-10-01 11:14 | 17.13 | 2021-10-26 13:17 | 14 | Busy | 6608 | 6608 | 1 | 0.79 | 5220.32 | 9250 | 7307.5
Develop Testing Protocol for Prototype | 2021-09-21 16:14 | 10.25 | 2021-10-06 09:14 | 22 | Complete | 3520 | 3520 | 1 | 1 | 3520 | 4530.5 | 4530.5
PM Period 7 | 2021-09-21 16:14 | 12.5 | 2021-10-08 11:14 | 22 | Complete | 8624 | 8624 | 1 | 1 | 8624 | 9750 | 9750
Milestone 7 | 2021-09-21 16:14 | 0 | 2021-09-21 16:14 | 22 | Complete | 0 | 0 | 1 | 0 | 0 | 35000 | 0
Approve Sample Parts | 2021-10-26 13:17 | 10.13 | 2021-11-09 14:19 | -5 | Busy | 4352 | 4352 | 1 | 0 | 0 | 6078 | 0
Design Validation Activities | 2021-11-12 10:17 | 3.06 | 2021-11-16 16:02 | -18 | Busy | 2200 | 2200 | 1 | 0 | 0 | 3188.5 | 0
Test Prototype | 2021-10-26 13:17 | 12.75 | 2021-11-12 10:17 | -5 | Busy | 6000 | 6000 | 1 | 0 | 0 | 5635.52 | 0
Process Engineering Plan | 2021-10-26 13:17 | 17.63 | 2021-11-19 09:19 | -5 | Busy | 6000 | 6000 | 1 | 0 | 0 | 7811.1 | 0
Show Functional Model at Trade Show | 2021-11-01 08:00 | 3.25 | 2021-11-04 10:00 | -9 | Busy | 2352 | 2352 | 1 | 0 | 0 | 2535 | 0
PM Period 8 | 2021-10-26 13:17 | 3.38 | 2021-10-29 16:19 | -5 | Busy | 2352 | 2352 | 1 | 0 | 0 | 2636.4 | 0
Milestone 8 | 2021-11-19 09:19 | 0 | 2021-11-19 09:19 | -23 | Busy | 0 | 0 | 1 | 0 | 0 | 0 | 0
Validation Design Review | 2021-11-19 09:19 | 4.75 | 2021-11-25 16:19 | -23 | Busy | 1968 | 1968 | 1 | 0 | 0 | 2565 | 0
Approve Model Design | 2021-11-25 16:19 | 5.13 | 2021-12-03 08:22 | -27 | Busy | 1968 | 1968 | 1 | 0 | 0 | 2267.46 | 0
Evaluate Test Results | 2021-11-19 09:19 | 7.38 | 2021-11-30 13:22 | -23 | Busy | 3600 | 3600 | 1 | 0 | 0 | 4428 | 0
PM Period 9 | 2021-11-19 09:19 | 4.63 | 2021-11-25 15:22 | -23 | Busy | 3136 | 3136 | 1 | 0 | 0 | 3611.4 | 0
Milestone 9 | 2021-12-03 08:22 | 0 | 2021-12-03 08:22 | -33 | Busy | 0 | 0 | 1 | 0 | 0 | 0 | 0
Qualify Supplier | 2021-12-03 08:22 | 12.5 | 2021-12-21 13:22 | -33 | Busy | 6000 | 3000 | 0.5 | 0 | 0 | 7500 | 0 | 2021-10-14 | 5 | 10
Design Transfer Activities | 2021-12-03 08:22 | 8.25 | 2021-12-15 10:22 | -33 | Busy | 4200 | 3000.06 | 0.7143 | 0 | 0 | 4455 | 0 | 2021-10-14 | 5 | 7
Product Release Meetings | 2021-12-15 10:22 | 3.38 | 2021-12-20 14:24 | -41 | Busy | 3000 | 0 | 0 | 0 | 0 | 2636 | 0
Develop Production Plan | 2021-12-03 08:22 | 8.25 | 2021-12-15 10:22 | -33 | Busy | 2400 | 1999.92 | 0.8333 | 0 | 0 | 3646.5 | 0 | 2021-10-14 | 5 | 6
PM Period 10 | 2021-12-03 08:22 | 5.63 | 2021-12-10 14:24 | -33 | Busy | 3920 | 3920 | 1 | 0 | 0 | 4391.4 | 0 | 2021-10-14 | 5 | 5
Milestone 10 | 2021-12-21 13:22 | 0 | 2021-12-21 13:22 | -45 | Busy | 0 | 0 | 1 | 0 | 0 | 10000 | 0
Totals | [6 empty] | 234048 |  |  | 209404.32 |  | 231395.56
CPI | 0.905
SPI | 0.8947
ETC | 27230.5856
EAC | 258626.1456
Formulas:
Network Days to Analysis Date = NETWORKDAYS([Real Start Date],D3)
Network Days to Analysis Date = NETWORKDAYS([Planned Start Date],D3)

## Period 8
Period 8 |  | Analysis Date at 17:00
2021-11-15
Task | Real Start Date | Real Duration | Real End Date | Network Days to Analysis Date | Complete/Busy | Full Budget | Planned Value | %Sched Completion | %Actual Completion | Earned Value | Actual Cost | Actual Cost at Analysis Date | Planned Start Date | Network Days to Analysis Date | Planned Duration
Evaluate Market | 2021-03-31 09:00 | 6.69 | 2021-04-08 15:31 | 164 | Complete | 7728 | 7728 | 1 | 1 | 7728 | 8563.2 | 8563.2
Develop Business Opportunity | 2021-04-08 15:31 | 8.06 | 2021-04-20 16:00 | 158 | Complete | 9016 | 9016 | 1 | 1 | 9016 | 10316.8 | 10316.8
Customer Preference Study | 2021-04-20 16:00 | 12.13 | 2021-05-07 08:02 | 150 | Complete | 13524 | 13524 | 1 | 1 | 13524 | 14240 | 14240
Business Evaluation (NPV, etc.) | 2021-05-07 08:02 | 2.38 | 2021-05-11 11:05 | 137 | Complete | 2576 | 2576 | 1 | 1 | 2576 | 4973 | 4973
PM Period 1 | 2021-03-31 09:00 | 18.06 | 2021-04-26 09:29 | 164 | Complete | 12300 | 12300 | 1 | 1 | 12300 | 17734.92 | 17734.92
Milestone 1 | 2021-05-11 11:05 | 0 | 2021-05-11 11:05 | 135 | Complete | 0 | 0 | 1 | 1 | 0 | 0 | 0
Design and Development Plan | 2021-05-11 11:05 | 3.88 | 2021-05-17 10:07 | 135 | Complete | 2352 | 2352 | 1 | 1 | 2352 | 3585.12 | 3585.12
Design Specs | 2021-05-17 10:07 | 13.75 | 2021-06-04 08:07 | 131 | Complete | 8624 | 8624 | 1 | 1 | 8624 | 12705 | 12705
Develop Prelim Marketing Plan | 2021-05-11 11:05 | 2.81 | 2021-05-14 09:34 | 135 | Complete | 3220 | 3220 | 1 | 1 | 3220 | 3596.8 | 3596.8
Develop Marketing Program | 2021-05-14 09:34 | 8.44 | 2021-05-26 14:05 | 132 | Complete | 9660 | 9660 | 1 | 1 | 9660 | 10803.2 | 10803.2
PM Period 2 | 2021-05-11 11:05 | 10.06 | 2021-05-25 11:34 | 135 | Complete | 6888 | 6888 | 1 | 1 | 6888 | 9878.92 | 9878.92
Milestone 2 | 2021-06-04 08:07 | 0 | 2021-06-04 08:07 | 117 | Complete | 0 | 0 | 1 | 1 | 0 | 5000 | 5000
Identify Testing Requirements | 2021-06-04 08:07 | 6.25 | 2021-06-14 10:07 | 117 | Complete | 3920 | 3920 | 1 | 1 | 3920 | 5775 | 5775
Risk Analysis | 2021-06-14 10:07 | 7.06 | 2021-06-23 10:36 | 111 | Complete | 3920 | 3920 | 1 | 1 | 3920 | 6523.44 | 6523.44
Train Sales Team | 2021-06-04 08:07 | 24.88 | 2021-07-08 16:10 | 117 | Complete | 11088 | 11088 | 1 | 1 | 11088 | 12440 | 12440
Advertising Campaign | 2021-06-04 08:07 | 31.38 | 2021-07-19 11:10 | 117 | Complete | 21952 | 21952 | 1 | 1 | 21952 | 24476.4 | 24476.4
PM Period 3 | 2021-06-04 08:07 | 10.13 | 2021-06-18 09:10 | 117 | Complete | 6888 | 6888 | 1 | 1 | 6888 | 9947.66 | 9947.66
Milestone 3 | 2021-07-19 11:10 | 0 | 2021-07-19 11:10 | 86 | Complete | 0 | 0 | 1 | 1 | 0 | 0 | 0
Design Labelling | 2021-07-14 08:07 | 3.25 | 2021-07-19 10:07 | 89 | Complete | 1960 | 1960 | 1 | 1 | 1960 | 3003 | 3003
Approve Design | 2021-07-19 10:07 | 2.63 | 2021-07-21 16:10 | 86 | Complete | 1568 | 1568 | 1 | 1 | 1568 | 2430.12 | 2430.12
Initial Engineering Specs | 2021-07-21 16:10 | 2.88 | 2021-07-26 15:12 | 84 | Complete | 2460 | 2460 | 1 | 1 | 2460 | 2828.16 | 2828.16
PM Period 4 | 2021-07-19 11:10 | 14.63 | 2021-08-09 08:12 | 86 | Complete | 10192 | 10192 | 1 | 1 | 10192 | 11411.4 | 11411.4
Milestone 4 | 2021-08-09 08:12 | 0 | 2021-08-09 08:12 | 71 | Complete | 0 | 0 | 1 | 1 | 0 | -50000 | -50000
Design Verification Activities | 2021-08-09 08:12 | 4.19 | 2021-08-13 09:43 | 71 | Complete | 3444 | 3444 | 1 | 1 | 3444 | 4114.58 | 4114.58
Verification Design Review | 2021-08-13 09:43 | 2.31 | 2021-08-17 13:12 | 67 | Complete | 1968 | 1968 | 1 | 1 | 1968 | 2268.42 | 2268.42
Release Pre-Production Specs | 2021-08-17 13:12 | 6 | 2021-08-25 13:12 | 65 | Complete | 4920 | 4920 | 1 | 1 | 4920 | 5892 | 5892
PM Period 5 | 2021-08-09 08:12 | 17 | 2021-09-01 08:12 | 71 | Complete | 11760 | 11760 | 1 | 1 | 11760 | 13260 | 13260
Milestone 5 | 2021-09-01 08:12 | 0 | 2021-09-01 08:12 | 54 | Complete | 0 | 0 | 1 | 1 | 0 | 15000 | 15000
Identify Vendors | 2021-09-01 08:12 | 4.5 | 2021-09-07 13:12 | 54 | Complete | 2800 | 2800 | 1 | 1 | 2800 | 3528 | 3528
Develop and Issue RFQ | 2021-09-07 13:12 | 3.88 | 2021-09-13 09:02 | 50 | Complete | 2400 | 2400 | 1 | 1 | 2400 | 3041.92 | 3041.92
Build Functional Model | 2021-09-01 08:12 | 11.25 | 2021-09-16 10:12 | 54 | Complete | 8856 | 8856 | 1 | 1 | 8856 | 11047.5 | 11047.5
Evaluate Design Specs | 2021-09-01 08:12 | 14.88 | 2021-09-21 16:14 | 54 | Complete | 6000 | 6000 | 1 | 1 | 6000 | 8928 | 8928
PM Period 6 | 2021-09-01 08:12 | 10.25 | 2021-09-15 10:12 | 54 | Complete | 7056 | 7056 | 1 | 1 | 7056 | 7995 | 7995
Milestone 6 | 2021-09-21 16:14 | 0 | 2021-09-21 16:14 | 40 | Complete | 0 | 0 | 1 | 1 | 0 | 0 | 0
Issue Sample | 2021-09-21 16:14 | 7.5 | 2021-10-01 11:14 | 40 | Complete | 3000 | 3000 | 1 | 1 | 3000 | 4500 | 4500
Perform Supplier Process Capability | 2021-10-01 11:14 | 17.13 | 2021-10-26 13:17 | 32 | Complete | 6608 | 6608 | 1 | 1 | 6608 | 9250 | 9250
Develop Testing Protocol for Prototype | 2021-09-21 16:14 | 10.25 | 2021-10-06 09:14 | 40 | Complete | 3520 | 3520 | 1 | 1 | 3520 | 4530.5 | 4530.5
PM Period 7 | 2021-09-21 16:14 | 12.5 | 2021-10-08 11:14 | 40 | Complete | 8624 | 8624 | 1 | 1 | 8624 | 9750 | 9750
Milestone 7 | 2021-09-21 16:14 | 0 | 2021-09-21 16:14 | 40 | Complete | 0 | 0 | 1 | 1 | 0 | 35000 | 35000
Approve Sample Parts | 2021-10-26 13:17 | 10.13 | 2021-11-09 14:19 | 15 | Complete | 4352 | 4352 | 1 | 1 | 4352 | 6078 | 6078
Design Validation Activities | 2021-11-12 10:17 | 3.06 | 2021-11-16 16:02 | 2 | Busy | 2200 | 2200 | 1 | 0.71 | 1562 | 3188.5 | 2263.835
Test Prototype | 2021-10-26 13:17 | 12.75 | 2021-11-12 10:17 | 15 | Complete | 6000 | 6000 | 1 | 1 | 6000 | 5635.52 | 5635.52
Process Engineering Plan | 2021-10-26 13:17 | 17.63 | 2021-11-19 09:19 | 15 | Busy | 6000 | 6000 | 1 | 0.82 | 4920 | 7811.1 | 6405.102
Show Functional Model at Trade Show | 2021-11-01 08:00 | 3.25 | 2021-11-04 10:00 | 11 | Complete | 2352 | 2352 | 1 | 1 | 2352 | 2535 | 2535
PM Period 8 | 2021-10-26 13:17 | 3.38 | 2021-10-29 16:19 | 15 | Complete | 2352 | 2352 | 1 | 1 | 2352 | 2636.4 | 2636.4
Milestone 8 | 2021-11-19 09:19 | 0 | 2021-11-19 09:19 | -5 | Busy | 0 | 0 | 1 | 0 | 0 | 0 | 0
Validation Design Review | 2021-11-19 09:19 | 4.75 | 2021-11-25 16:19 | -5 | Busy | 1968 | 1968 | 1 | 0 | 0 | 2565 | 0
Approve Model Design | 2021-11-25 16:19 | 5.13 | 2021-12-03 08:22 | -9 | Busy | 1968 | 1968 | 1 | 0 | 0 | 2267.46 | 0
Evaluate Test Results | 2021-11-19 09:19 | 7.38 | 2021-11-30 13:22 | -5 | Busy | 3600 | 3600 | 1 | 0 | 0 | 4428 | 0
PM Period 9 | 2021-11-19 09:19 | 4.63 | 2021-11-25 15:22 | -5 | Busy | 3136 | 3136 | 1 | 0 | 0 | 3611.4 | 0
Milestone 9 | 2021-12-03 08:22 | 0 | 2021-12-03 08:22 | -15 | Busy | 0 | 0 | 1 | 0 | 0 | 0 | 0
Qualify Supplier | 2021-12-03 08:22 | 12.5 | 2021-12-21 13:22 | -15 | Busy | 6000 | 6000 | 1 | 0 | 0 | 7500 | 0
Design Transfer Activities | 2021-12-03 08:22 | 8.25 | 2021-12-15 10:22 | -15 | Busy | 4200 | 4200 | 1 | 0 | 0 | 4455 | 0
Product Release Meetings | 2021-12-15 10:22 | 3.38 | 2021-12-20 14:24 | -23 | Busy | 3000 | 3000 | 1 | 0 | 0 | 2636 | 0
Develop Production Plan | 2021-12-03 08:22 | 8.25 | 2021-12-15 10:22 | -15 | Busy | 2400 | 2400 | 1 | 0 | 0 | 3646.5 | 0
PM Period 10 | 2021-12-03 08:22 | 5.63 | 2021-12-10 14:24 | -15 | Busy | 3920 | 3920 | 1 | 0 | 0 | 4391.4 | 0
Milestone 10 | 2021-12-21 13:22 | 0 | 2021-12-21 13:22 | -27 | Busy | 0 | 0 | 1 | 0 | 0 | 10000 | 0
Assess RFQ Responses | 2021-12-21 13:22 | 6.06 | 2021-12-29 13:50 | -27 | Busy | 6000 | 1200 | 0.2 | 0 | 0 | 6908.4 | 0 | 2021-11-12 | 2 | 10
Develop Production Control Plan | 2021-12-21 13:22 | 11.13 | 2022-01-05 14:24 | -27 | Busy | 3400 | 800.02 | 0.2353 | 0 | 0 | 4919.46 | 0 | 2021-11-12 | 2 | 8.5
Approve Production Parts | 2022-01-05 14:24 | 3.31 | 2022-01-10 16:53 | -38 | Busy | 2000 | 0 | 0 | 0 | 0 | 3250.42 | 0
Contracting for Deliveries | 2022-01-10 16:53 | 5.13 | 2022-01-18 08:55 | -41 | Busy | 3200 | 0 | 0 | 0 | 0 | 5037.66 | 0
PM Period 11 | 2021-12-21 13:22 | 14.75 | 2022-01-11 10:22 | -27 | Busy | 5720 | 879.736 | 0.1538 | 0 | 0 | 11505 | 0 | 2021-11-12 | 2 | 13
Milestone 11 | 2022-01-18 08:55 | 0 | 2022-01-18 08:55 | -47 | Busy | 0 | 0 | 0 | 0 | 0 | 0 | 0
Totals | [6 empty] | 267119.756 |  |  | 232330 |  | 293891.917
CPI | 0.7905
SPI | 0.8698
ETC | 44009.8115
EAC | 337901.7285
Formulas:
Network Days to Analysis Date = NETWORKDAYS([Real Start Date],D3)
Network Days to Analysis Date = NETWORKDAYS([Planned Start Date],D3)

## Period 9
Period 9 |  | Analysis Date at 17:00
2021-11-29
Task | Real Start Date | Real Duration | Real End Date | Network Days to Analysis Date | Complete/Busy | Full Budget | Planned Value | %Sched Completion | %Actual Completion | Earned Value | Actual Cost | Actual Cost at Analysis Date | Planned Start Date | Network Days to Analysis Date | Planned Duration
Evaluate Market | 2021-03-31 09:00 | 6.69 | 2021-04-08 15:31 | 174 | Complete | 7728 | 7728 | 1 | 1 | 7728 | 8563.2 | 8563.2
Develop Business Opportunity | 2021-04-08 15:31 | 8.06 | 2021-04-20 16:00 | 168 | Complete | 9016 | 9016 | 1 | 1 | 9016 | 10316.8 | 10316.8
Customer Preference Study | 2021-04-20 16:00 | 12.13 | 2021-05-07 08:02 | 160 | Complete | 13524 | 13524 | 1 | 1 | 13524 | 14240 | 14240
Business Evaluation (NPV, etc.) | 2021-05-07 08:02 | 2.38 | 2021-05-11 11:05 | 147 | Complete | 2576 | 2576 | 1 | 1 | 2576 | 4973 | 4973
PM Period 1 | 2021-03-31 09:00 | 18.06 | 2021-04-26 09:29 | 174 | Complete | 12300 | 12300 | 1 | 1 | 12300 | 17734.92 | 17734.92
Milestone 1 | 2021-05-11 11:05 | 0 | 2021-05-11 11:05 | 145 | Complete | 0 | 0 | 1 | 1 | 0 | 0 | 0
Design and Development Plan | 2021-05-11 11:05 | 3.88 | 2021-05-17 10:07 | 145 | Complete | 2352 | 2352 | 1 | 1 | 2352 | 3585.12 | 3585.12
Design Specs | 2021-05-17 10:07 | 13.75 | 2021-06-04 08:07 | 141 | Complete | 8624 | 8624 | 1 | 1 | 8624 | 12705 | 12705
Develop Prelim Marketing Plan | 2021-05-11 11:05 | 2.81 | 2021-05-14 09:34 | 145 | Complete | 3220 | 3220 | 1 | 1 | 3220 | 3596.8 | 3596.8
Develop Marketing Program | 2021-05-14 09:34 | 8.44 | 2021-05-26 14:05 | 142 | Complete | 9660 | 9660 | 1 | 1 | 9660 | 10803.2 | 10803.2
PM Period 2 | 2021-05-11 11:05 | 10.06 | 2021-05-25 11:34 | 145 | Complete | 6888 | 6888 | 1 | 1 | 6888 | 9878.92 | 9878.92
Milestone 2 | 2021-06-04 08:07 | 0 | 2021-06-04 08:07 | 127 | Complete | 0 | 0 | 1 | 1 | 0 | 5000 | 5000
Identify Testing Requirements | 2021-06-04 08:07 | 6.25 | 2021-06-14 10:07 | 127 | Complete | 3920 | 3920 | 1 | 1 | 3920 | 5775 | 5775
Risk Analysis | 2021-06-14 10:07 | 7.06 | 2021-06-23 10:36 | 121 | Complete | 3920 | 3920 | 1 | 1 | 3920 | 6523.44 | 6523.44
Train Sales Team | 2021-06-04 08:07 | 24.88 | 2021-07-08 16:10 | 127 | Complete | 11088 | 11088 | 1 | 1 | 11088 | 12440 | 12440
Advertising Campaign | 2021-06-04 08:07 | 31.38 | 2021-07-19 11:10 | 127 | Complete | 21952 | 21952 | 1 | 1 | 21952 | 24476.4 | 24476.4
PM Period 3 | 2021-06-04 08:07 | 10.13 | 2021-06-18 09:10 | 127 | Complete | 6888 | 6888 | 1 | 1 | 6888 | 9947.66 | 9947.66
Milestone 3 | 2021-07-19 11:10 | 0 | 2021-07-19 11:10 | 96 | Complete | 0 | 0 | 1 | 1 | 0 | 0 | 0
Design Labelling | 2021-07-14 08:07 | 3.25 | 2021-07-19 10:07 | 99 | Complete | 1960 | 1960 | 1 | 1 | 1960 | 3003 | 3003
Approve Design | 2021-07-19 10:07 | 2.63 | 2021-07-21 16:10 | 96 | Complete | 1568 | 1568 | 1 | 1 | 1568 | 2430.12 | 2430.12
Initial Engineering Specs | 2021-07-21 16:10 | 2.88 | 2021-07-26 15:12 | 94 | Complete | 2460 | 2460 | 1 | 1 | 2460 | 2828.16 | 2828.16
PM Period 4 | 2021-07-19 11:10 | 14.63 | 2021-08-09 08:12 | 96 | Complete | 10192 | 10192 | 1 | 1 | 10192 | 11411.4 | 11411.4
Milestone 4 | 2021-08-09 08:12 | 0 | 2021-08-09 08:12 | 81 | Complete | 0 | 0 | 1 | 1 | 0 | -50000 | -50000
Design Verification Activities | 2021-08-09 08:12 | 4.19 | 2021-08-13 09:43 | 81 | Complete | 3444 | 3444 | 1 | 1 | 3444 | 4114.58 | 4114.58
Verification Design Review | 2021-08-13 09:43 | 2.31 | 2021-08-17 13:12 | 77 | Complete | 1968 | 1968 | 1 | 1 | 1968 | 2268.42 | 2268.42
Release Pre-Production Specs | 2021-08-17 13:12 | 6 | 2021-08-25 13:12 | 75 | Complete | 4920 | 4920 | 1 | 1 | 4920 | 5892 | 5892
PM Period 5 | 2021-08-09 08:12 | 17 | 2021-09-01 08:12 | 81 | Complete | 11760 | 11760 | 1 | 1 | 11760 | 13260 | 13260
Milestone 5 | 2021-09-01 08:12 | 0 | 2021-09-01 08:12 | 64 | Complete | 0 | 0 | 1 | 1 | 0 | 15000 | 15000
Identify Vendors | 2021-09-01 08:12 | 4.5 | 2021-09-07 13:12 | 64 | Complete | 2800 | 2800 | 1 | 1 | 2800 | 3528 | 3528
Develop and Issue RFQ | 2021-09-07 13:12 | 3.88 | 2021-09-13 09:02 | 60 | Complete | 2400 | 2400 | 1 | 1 | 2400 | 3041.92 | 3041.92
Build Functional Model | 2021-09-01 08:12 | 11.25 | 2021-09-16 10:12 | 64 | Complete | 8856 | 8856 | 1 | 1 | 8856 | 11047.5 | 11047.5
Evaluate Design Specs | 2021-09-01 08:12 | 14.88 | 2021-09-21 16:14 | 64 | Complete | 6000 | 6000 | 1 | 1 | 6000 | 8928 | 8928
PM Period 6 | 2021-09-01 08:12 | 10.25 | 2021-09-15 10:12 | 64 | Complete | 7056 | 7056 | 1 | 1 | 7056 | 7995 | 7995
Milestone 6 | 2021-09-21 16:14 | 0 | 2021-09-21 16:14 | 50 | Complete | 0 | 0 | 1 | 1 | 0 | 0 | 0
Issue Sample | 2021-09-21 16:14 | 7.5 | 2021-10-01 11:14 | 50 | Complete | 3000 | 3000 | 1 | 1 | 3000 | 4500 | 4500
Perform Supplier Process Capability | 2021-10-01 11:14 | 17.13 | 2021-10-26 13:17 | 42 | Complete | 6608 | 6608 | 1 | 1 | 6608 | 9250 | 9250
Develop Testing Protocol for Prototype | 2021-09-21 16:14 | 10.25 | 2021-10-06 09:14 | 50 | Complete | 3520 | 3520 | 1 | 1 | 3520 | 4530.5 | 4530.5
PM Period 7 | 2021-09-21 16:14 | 12.5 | 2021-10-08 11:14 | 50 | Complete | 8624 | 8624 | 1 | 1 | 8624 | 9750 | 9750
Milestone 7 | 2021-09-21 16:14 | 0 | 2021-09-21 16:14 | 50 | Complete | 0 | 0 | 1 | 1 | 0 | 35000 | 35000
Approve Sample Parts | 2021-10-26 13:17 | 10.13 | 2021-11-09 14:19 | 25 | Complete | 4352 | 4352 | 1 | 1 | 4352 | 6078 | 6078
Design Validation Activities | 2021-11-12 10:17 | 3.06 | 2021-11-16 16:02 | 12 | Complete | 2200 | 2200 | 1 | 1 | 2200 | 3188.5 | 3188.5
Test Prototype | 2021-10-26 13:17 | 12.75 | 2021-11-12 10:17 | 25 | Complete | 6000 | 6000 | 1 | 1 | 6000 | 5635.52 | 5635.52
Process Engineering Plan | 2021-10-26 13:17 | 17.63 | 2021-11-19 09:19 | 25 | Complete | 6000 | 6000 | 1 | 1 | 6000 | 7811.1 | 7811.1
Show Functional Model at Trade Show | 2021-11-01 08:00 | 3.25 | 2021-11-04 10:00 | 21 | Complete | 2352 | 2352 | 1 | 1 | 2352 | 2535 | 2535
PM Period 8 | 2021-10-26 13:17 | 3.38 | 2021-10-29 16:19 | 25 | Complete | 2352 | 2352 | 1 | 1 | 2352 | 2636.4 | 2636.4
Milestone 8 | 2021-11-19 09:19 | 0 | 2021-11-19 09:19 | 7 | Complete | 0 | 0 | 1 | 0 | 0 | 0 | 0
Validation Design Review | 2021-11-19 09:19 | 4.75 | 2021-11-25 16:19 | 7 | Complete | 1968 | 1968 | 1 | 1 | 1968 | 2565 | 2565
Approve Model Design | 2021-11-25 16:19 | 5.13 | 2021-12-03 08:22 | 3 | Busy | 1968 | 1968 | 1 | 0.41 | 806.88 | 2267.46 | 929.6586
Evaluate Test Results | 2021-11-19 09:19 | 7.38 | 2021-11-30 13:22 | 7 | Busy | 3600 | 3600 | 1 | 0.93 | 3348 | 4428 | 4118.04
PM Period 9 | 2021-11-19 09:19 | 4.63 | 2021-11-25 15:22 | 7 | Complete | 3136 | 3136 | 1 | 1 | 3136 | 3611.4 | 3611.4
Milestone 9 | 2021-12-03 08:22 | 0 | 2021-12-03 08:22 | -5 | Busy | 0 | 0 | 1 | 0 | 0 | 0 | 0
Qualify Supplier | 2021-12-03 08:22 | 12.5 | 2021-12-21 13:22 | -5 | Busy | 6000 | 6000 | 1 | 0 | 0 | 7500 | 0
Design Transfer Activities | 2021-12-03 08:22 | 8.25 | 2021-12-15 10:22 | -5 | Busy | 4200 | 4200 | 1 | 0 | 0 | 4455 | 0
Product Release Meetings | 2021-12-15 10:22 | 3.38 | 2021-12-20 14:24 | -13 | Busy | 3000 | 3000 | 1 | 0 | 0 | 2636 | 0
Develop Production Plan | 2021-12-03 08:22 | 8.25 | 2021-12-15 10:22 | -5 | Busy | 2400 | 2400 | 1 | 0 | 0 | 3646.5 | 0
PM Period 10 | 2021-12-03 08:22 | 5.63 | 2021-12-10 14:24 | -5 | Busy | 3920 | 3920 | 1 | 0 | 0 | 4391.4 | 0
Milestone 10 | 2021-12-21 13:22 | 0 | 2021-12-21 13:22 | -17 | Busy | 0 | 0 | 1 | 0 | 0 | 10000 | 0
Assess RFQ Responses | 2021-12-21 13:22 | 6.06 | 2021-12-29 13:50 | -17 | Busy | 6000 | 6000 | 1 | 0 | 0 | 6908.4 | 0 | 2021-11-12 | 12 | 10
Develop Production Control Plan | 2021-12-21 13:22 | 11.13 | 2022-01-05 14:24 | -17 | Busy | 3400 | 3400 | 1 | 0 | 0 | 4919.46 | 0 | 2021-11-12 | 12 | 8.5
Approve Production Parts | 2022-01-05 14:24 | 3.31 | 2022-01-10 16:53 | -28 | Busy | 2000 | 1200 | 0.6 | 0 | 0 | 3250.42 | 0 | 2021-11-25 | 3 | 5
Contracting for Deliveries | 2022-01-10 16:53 | 5.13 | 2022-01-18 08:55 | -31 | Busy | 3200 | 0 | 0 | 0 | 0 | 5037.66 | 0
PM Period 11 | 2021-12-21 13:22 | 14.75 | 2022-01-11 10:22 | -17 | Busy | 5720 | 5280.132 | 0.9231 | 0 | 0 | 11505 | 0 | 2021-11-12 | 12 | 13
Milestone 11 | 2022-01-18 08:55 | 0 | 2022-01-18 08:55 | -37 | Busy | 0 | 0 | 0 | 0 | 0 | 0 | 0
Totals | [6 empty] | 280120.132 |  |  | 243306.88 |  | 307446.6786
CPI | 0.7914
SPI | 0.8686
ETC | 46516.6187
EAC | 353963.2973
Formulas:
Network Days to Analysis Date = NETWORKDAYS([Real Start Date],D3)
Network Days to Analysis Date = NETWORKDAYS([Planned Start Date],D3)

## Period 10
Period 10 |  | Analysis Date at 17:00
2021-12-15
Task | Real Start Date | Real Duration | Real End Date | Network Days to Analysis Date | Complete/Busy | Full Budget | Planned Value | %Sched Completion | %Actual Completion | Earned Value | Actual Cost | Actual Cost at Analysis Date | Planned Start Date | Network Days to Analysis Date | Planned Duration
Evaluate Market | 2021-03-31 09:00 | 6.69 | 2021-04-08 15:31 | 186 | Complete | 7728 | 7728 | 1 | 1 | 7728 | 8563.2 | 8563.2
Develop Business Opportunity | 2021-04-08 15:31 | 8.06 | 2021-04-20 16:00 | 180 | Complete | 9016 | 9016 | 1 | 1 | 9016 | 10316.8 | 10316.8
Customer Preference Study | 2021-04-20 16:00 | 12.13 | 2021-05-07 08:02 | 172 | Complete | 13524 | 13524 | 1 | 1 | 13524 | 14240 | 14240
Business Evaluation (NPV, etc.) | 2021-05-07 08:02 | 2.38 | 2021-05-11 11:05 | 159 | Complete | 2576 | 2576 | 1 | 1 | 2576 | 4973 | 4973
PM Period 1 | 2021-03-31 09:00 | 18.06 | 2021-04-26 09:29 | 186 | Complete | 12300 | 12300 | 1 | 1 | 12300 | 17734.92 | 17734.92
Milestone 1 | 2021-05-11 11:05 | 0 | 2021-05-11 11:05 | 157 | Complete | 0 | 0 | 1 | 1 | 0 | 0 | 0
Design and Development Plan | 2021-05-11 11:05 | 3.88 | 2021-05-17 10:07 | 157 | Complete | 2352 | 2352 | 1 | 1 | 2352 | 3585.12 | 3585.12
Design Specs | 2021-05-17 10:07 | 13.75 | 2021-06-04 08:07 | 153 | Complete | 8624 | 8624 | 1 | 1 | 8624 | 12705 | 12705
Develop Prelim Marketing Plan | 2021-05-11 11:05 | 2.81 | 2021-05-14 09:34 | 157 | Complete | 3220 | 3220 | 1 | 1 | 3220 | 3596.8 | 3596.8
Develop Marketing Program | 2021-05-14 09:34 | 8.44 | 2021-05-26 14:05 | 154 | Complete | 9660 | 9660 | 1 | 1 | 9660 | 10803.2 | 10803.2
PM Period 2 | 2021-05-11 11:05 | 10.06 | 2021-05-25 11:34 | 157 | Complete | 6888 | 6888 | 1 | 1 | 6888 | 9878.92 | 9878.92
Milestone 2 | 2021-06-04 08:07 | 0 | 2021-06-04 08:07 | 139 | Complete | 0 | 0 | 1 | 1 | 0 | 5000 | 5000
Identify Testing Requirements | 2021-06-04 08:07 | 6.25 | 2021-06-14 10:07 | 139 | Complete | 3920 | 3920 | 1 | 1 | 3920 | 5775 | 5775
Risk Analysis | 2021-06-14 10:07 | 7.06 | 2021-06-23 10:36 | 133 | Complete | 3920 | 3920 | 1 | 1 | 3920 | 6523.44 | 6523.44
Train Sales Team | 2021-06-04 08:07 | 24.88 | 2021-07-08 16:10 | 139 | Complete | 11088 | 11088 | 1 | 1 | 11088 | 12440 | 12440
Advertising Campaign | 2021-06-04 08:07 | 31.38 | 2021-07-19 11:10 | 139 | Complete | 21952 | 21952 | 1 | 1 | 21952 | 24476.4 | 24476.4
PM Period 3 | 2021-06-04 08:07 | 10.13 | 2021-06-18 09:10 | 139 | Complete | 6888 | 6888 | 1 | 1 | 6888 | 9947.66 | 9947.66
Milestone 3 | 2021-07-19 11:10 | 0 | 2021-07-19 11:10 | 108 | Complete | 0 | 0 | 1 | 1 | 0 | 0 | 0
Design Labelling | 2021-07-14 08:07 | 3.25 | 2021-07-19 10:07 | 111 | Complete | 1960 | 1960 | 1 | 1 | 1960 | 3003 | 3003
Approve Design | 2021-07-19 10:07 | 2.63 | 2021-07-21 16:10 | 108 | Complete | 1568 | 1568 | 1 | 1 | 1568 | 2430.12 | 2430.12
Initial Engineering Specs | 2021-07-21 16:10 | 2.88 | 2021-07-26 15:12 | 106 | Complete | 2460 | 2460 | 1 | 1 | 2460 | 2828.16 | 2828.16
PM Period 4 | 2021-07-19 11:10 | 14.63 | 2021-08-09 08:12 | 108 | Complete | 10192 | 10192 | 1 | 1 | 10192 | 11411.4 | 11411.4
Milestone 4 | 2021-08-09 08:12 | 0 | 2021-08-09 08:12 | 93 | Complete | 0 | 0 | 1 | 1 | 0 | -50000 | -50000
Design Verification Activities | 2021-08-09 08:12 | 4.19 | 2021-08-13 09:43 | 93 | Complete | 3444 | 3444 | 1 | 1 | 3444 | 4114.58 | 4114.58
Verification Design Review | 2021-08-13 09:43 | 2.31 | 2021-08-17 13:12 | 89 | Complete | 1968 | 1968 | 1 | 1 | 1968 | 2268.42 | 2268.42
Release Pre-Production Specs | 2021-08-17 13:12 | 6 | 2021-08-25 13:12 | 87 | Complete | 4920 | 4920 | 1 | 1 | 4920 | 5892 | 5892
PM Period 5 | 2021-08-09 08:12 | 17 | 2021-09-01 08:12 | 93 | Complete | 11760 | 11760 | 1 | 1 | 11760 | 13260 | 13260
Milestone 5 | 2021-09-01 08:12 | 0 | 2021-09-01 08:12 | 76 | Complete | 0 | 0 | 1 | 1 | 0 | 15000 | 15000
Identify Vendors | 2021-09-01 08:12 | 4.5 | 2021-09-07 13:12 | 76 | Complete | 2800 | 2800 | 1 | 1 | 2800 | 3528 | 3528
Develop and Issue RFQ | 2021-09-07 13:12 | 3.88 | 2021-09-13 09:02 | 72 | Complete | 2400 | 2400 | 1 | 1 | 2400 | 3041.92 | 3041.92
Build Functional Model | 2021-09-01 08:12 | 11.25 | 2021-09-16 10:12 | 76 | Complete | 8856 | 8856 | 1 | 1 | 8856 | 11047.5 | 11047.5
Evaluate Design Specs | 2021-09-01 08:12 | 14.88 | 2021-09-21 16:14 | 76 | Complete | 6000 | 6000 | 1 | 1 | 6000 | 8928 | 8928
PM Period 6 | 2021-09-01 08:12 | 10.25 | 2021-09-15 10:12 | 76 | Complete | 7056 | 7056 | 1 | 1 | 7056 | 7995 | 7995
Milestone 6 | 2021-09-21 16:14 | 0 | 2021-09-21 16:14 | 62 | Complete | 0 | 0 | 1 | 1 | 0 | 0 | 0
Issue Sample | 2021-09-21 16:14 | 7.5 | 2021-10-01 11:14 | 62 | Complete | 3000 | 3000 | 1 | 1 | 3000 | 4500 | 4500
Perform Supplier Process Capability | 2021-10-01 11:14 | 17.13 | 2021-10-26 13:17 | 54 | Complete | 6608 | 6608 | 1 | 1 | 6608 | 9250 | 9250
Develop Testing Protocol for Prototype | 2021-09-21 16:14 | 10.25 | 2021-10-06 09:14 | 62 | Complete | 3520 | 3520 | 1 | 1 | 3520 | 4530.5 | 4530.5
PM Period 7 | 2021-09-21 16:14 | 12.5 | 2021-10-08 11:14 | 62 | Complete | 8624 | 8624 | 1 | 1 | 8624 | 9750 | 9750
Milestone 7 | 2021-09-21 16:14 | 0 | 2021-09-21 16:14 | 62 | Complete | 0 | 0 | 1 | 1 | 0 | 35000 | 35000
Approve Sample Parts | 2021-10-26 13:17 | 10.13 | 2021-11-09 14:19 | 37 | Complete | 4352 | 4352 | 1 | 1 | 4352 | 6078 | 6078
Design Validation Activities | 2021-11-12 10:17 | 3.06 | 2021-11-16 16:02 | 24 | Complete | 2200 | 2200 | 1 | 1 | 2200 | 3188.5 | 3188.5
Test Prototype | 2021-10-26 13:17 | 12.75 | 2021-11-12 10:17 | 37 | Complete | 6000 | 6000 | 1 | 1 | 6000 | 5635.52 | 5635.52
Process Engineering Plan | 2021-10-26 13:17 | 17.63 | 2021-11-19 09:19 | 37 | Complete | 6000 | 6000 | 1 | 1 | 6000 | 7811.1 | 7811.1
Show Functional Model at Trade Show | 2021-11-01 08:00 | 3.25 | 2021-11-04 10:00 | 33 | Complete | 2352 | 2352 | 1 | 1 | 2352 | 2535 | 2535
PM Period 8 | 2021-10-26 13:17 | 3.38 | 2021-10-29 16:19 | 37 | Complete | 2352 | 2352 | 1 | 1 | 2352 | 2636.4 | 2636.4
Milestone 8 | 2021-11-19 09:19 | 0 | 2021-11-19 09:19 | 19 | Complete | 0 | 0 | 1 | 1 | 0 | 0 | 0
Validation Design Review | 2021-11-19 09:19 | 4.75 | 2021-11-25 16:19 | 19 | Complete | 1968 | 1968 | 1 | 1 | 1968 | 2565 | 2565
Approve Model Design | 2021-11-25 16:19 | 5.13 | 2021-12-03 08:22 | 15 | Complete | 1968 | 1968 | 1 | 1 | 1968 | 2267.46 | 2267.46
Evaluate Test Results | 2021-11-19 09:19 | 7.38 | 2021-11-30 13:22 | 19 | Complete | 3600 | 3600 | 1 | 1 | 3600 | 4428 | 4428
PM Period 9 | 2021-11-19 09:19 | 4.63 | 2021-11-25 15:22 | 19 | Complete | 3136 | 3136 | 1 | 1 | 3136 | 3611.4 | 3611.4
Milestone 9 | 2021-12-03 08:22 | 0 | 2021-12-03 08:22 | 9 | Complete | 0 | 0 | 1 | 1 | 0 | 0 | 0
Qualify Supplier | 2021-12-03 08:22 | 12.5 | 2021-12-21 13:22 | 9 | Busy | 6000 | 6000 | 1 | 0.72 | 4320 | 7500 | 5400
Design Transfer Activities | 2021-12-03 08:22 | 8.25 | 2021-12-15 10:22 | 9 | Complete | 4200 | 4200 | 1 | 1 | 4200 | 4455 | 4455
Product Release Meetings | 2021-12-15 10:22 | 3.38 | 2021-12-20 14:24 | 1 | Busy | 3000 | 3000 | 1 | 0.21 | 630 | 2636 | 553.56
Develop Production Plan | 2021-12-03 08:22 | 8.25 | 2021-12-15 10:22 | 9 | Complete | 2400 | 2400 | 1 | 1 | 2400 | 3646.5 | 3646.5
PM Period 10 | 2021-12-03 08:22 | 5.63 | 2021-12-10 14:24 | 9 | Complete | 3920 | 3920 | 1 | 1 | 3920 | 4391.4 | 4391.4
Milestone 10 | 2021-12-21 13:22 | 0 | 2021-12-21 13:22 | -5 | Busy | 0 | 0 | 1 | 0 | 0 | 10000 | 0
Assess RFQ Responses | 2021-12-21 13:22 | 6.06 | 2021-12-29 13:50 | -5 | Busy | 6000 | 6000 | 1 | 0 | 0 | 6908.4 | 0
Develop Production Control Plan | 2021-12-21 13:22 | 11.13 | 2022-01-05 14:24 | -5 | Busy | 3400 | 3400 | 1 | 0 | 0 | 4919.46 | 0
Approve Production Parts | 2022-01-05 14:24 | 3.31 | 2022-01-10 16:53 | -16 | Busy | 2000 | 2000 | 1 | 0 | 0 | 3250.42 | 0
Contracting for Deliveries | 2022-01-10 16:53 | 5.13 | 2022-01-18 08:55 | -19 | Busy | 3200 | 3200 | 1 | 0 | 0 | 5037.66 | 0
PM Period 11 | 2021-12-21 13:22 | 14.75 | 2022-01-11 10:22 | -5 | Busy | 5720 | 5720 | 1 | 0 | 0 | 11505 | 0
Milestone 11 | 2022-01-18 08:55 | 0 | 2022-01-18 08:55 | -25 | Busy | 0 | 0 | 0 | 0 | 0 | 0 | 0
Submit Production Purchase Order | 2022-01-18 08:55 | 1.31 | 2022-01-19 11:24 | -25 | Busy | 800 | 800 | 1 | 0 | 0 | 1286.42 | 0 | 2021-12-14 | 2 | 2
Production Pilot Test | 2022-01-19 11:24 | 3.19 | 2022-01-24 13:55 | -26 | Busy | 2000 | 0 | 0 | 0 | 0 | 3132.58 | 0
Debugging Production System | 2022-01-24 13:55 | 2.44 | 2022-01-27 08:26 | -29 | Busy | 1600 | 0 | 0 | 0 | 0 | 2396.08 | 0
Production Release | 2022-01-27 08:26 | 2 | 2022-01-31 08:26 | -32 | Busy | 1200 | 0 | 0 | 0 | 0 | 1964 | 0
Product Launch | 2022-02-02 11:58 | 3.38 | 2022-02-07 16:00 | -36 | Busy | 1512 | 0 | 0 | 0 | 0 | 2636.4 | 0
PM Period 12 | 2022-01-18 08:55 | 11.38 | 2022-02-02 11:58 | -25 | Busy | 4400 | 880 | 0.2 | 0 | 0 | 8876.4 | 0 | 2021-12-14 | 2 | 10
Milestone 12 | 2022-02-07 16:00 | 0 | 2022-02-07 16:00 | -39 | Busy | 0 | 0 | 0 | 0 | 0 | 0 | 0
Totals | [6 empty] | 286240 |  |  | 260190 |  | 327540.9
CPI | 0.7944
SPI | 0.909
ETC | 32792.0443
EAC | 360332.9443
Formulas:
Network Days to Analysis Date = NETWORKDAYS([Real Start Date],D3)
Network Days to Analysis Date = NETWORKDAYS([Planned Start Date],D3)

## Period 11
Period 11 |  | Analysis Date at 17:00
2022-01-12
Task | Real Start Date | Real Duration | Real End Date | Network Days to Analysis Date | Complete/Busy | Full Budget | Planned Value | %Sched Completion | %Actual Completion | Earned Value | Actual Cost | Actual Cost at Analysis Date | Planned Start Date | Network Days to Analysis Date | Planned Duration
Evaluate Market | 2021-03-31 09:00 | 6.69 | 2021-04-08 15:31 | 206 | Complete | 7728 | 7728 | 1 | 1 | 7728 | 8563.2 | 8563.2
Develop Business Opportunity | 2021-04-08 15:31 | 8.06 | 2021-04-20 16:00 | 200 | Complete | 9016 | 9016 | 1 | 1 | 9016 | 10316.8 | 10316.8
Customer Preference Study | 2021-04-20 16:00 | 12.13 | 2021-05-07 08:02 | 192 | Complete | 13524 | 13524 | 1 | 1 | 13524 | 14240 | 14240
Business Evaluation (NPV, etc.) | 2021-05-07 08:02 | 2.38 | 2021-05-11 11:05 | 179 | Complete | 2576 | 2576 | 1 | 1 | 2576 | 4973 | 4973
PM Period 1 | 2021-03-31 09:00 | 18.06 | 2021-04-26 09:29 | 206 | Complete | 12300 | 12300 | 1 | 1 | 12300 | 17734.92 | 17734.92
Milestone 1 | 2021-05-11 11:05 | 0 | 2021-05-11 11:05 | 177 | Complete | 0 | 0 | 1 | 1 | 0 | 0 | 0
Design and Development Plan | 2021-05-11 11:05 | 3.88 | 2021-05-17 10:07 | 177 | Complete | 2352 | 2352 | 1 | 1 | 2352 | 3585.12 | 3585.12
Design Specs | 2021-05-17 10:07 | 13.75 | 2021-06-04 08:07 | 173 | Complete | 8624 | 8624 | 1 | 1 | 8624 | 12705 | 12705
Develop Prelim Marketing Plan | 2021-05-11 11:05 | 2.81 | 2021-05-14 09:34 | 177 | Complete | 3220 | 3220 | 1 | 1 | 3220 | 3596.8 | 3596.8
Develop Marketing Program | 2021-05-14 09:34 | 8.44 | 2021-05-26 14:05 | 174 | Complete | 9660 | 9660 | 1 | 1 | 9660 | 10803.2 | 10803.2
PM Period 2 | 2021-05-11 11:05 | 10.06 | 2021-05-25 11:34 | 177 | Complete | 6888 | 6888 | 1 | 1 | 6888 | 9878.92 | 9878.92
Milestone 2 | 2021-06-04 08:07 | 0 | 2021-06-04 08:07 | 159 | Complete | 0 | 0 | 1 | 1 | 0 | 5000 | 5000
Identify Testing Requirements | 2021-06-04 08:07 | 6.25 | 2021-06-14 10:07 | 159 | Complete | 3920 | 3920 | 1 | 1 | 3920 | 5775 | 5775
Risk Analysis | 2021-06-14 10:07 | 7.06 | 2021-06-23 10:36 | 153 | Complete | 3920 | 3920 | 1 | 1 | 3920 | 6523.44 | 6523.44
Train Sales Team | 2021-06-04 08:07 | 24.88 | 2021-07-08 16:10 | 159 | Complete | 11088 | 11088 | 1 | 1 | 11088 | 12440 | 12440
Advertising Campaign | 2021-06-04 08:07 | 31.38 | 2021-07-19 11:10 | 159 | Complete | 21952 | 21952 | 1 | 1 | 21952 | 24476.4 | 24476.4
PM Period 3 | 2021-06-04 08:07 | 10.13 | 2021-06-18 09:10 | 159 | Complete | 6888 | 6888 | 1 | 1 | 6888 | 9947.66 | 9947.66
Milestone 3 | 2021-07-19 11:10 | 0 | 2021-07-19 11:10 | 128 | Complete | 0 | 0 | 1 | 1 | 0 | 0 | 0
Design Labelling | 2021-07-14 08:07 | 3.25 | 2021-07-19 10:07 | 131 | Complete | 1960 | 1960 | 1 | 1 | 1960 | 3003 | 3003
Approve Design | 2021-07-19 10:07 | 2.63 | 2021-07-21 16:10 | 128 | Complete | 1568 | 1568 | 1 | 1 | 1568 | 2430.12 | 2430.12
Initial Engineering Specs | 2021-07-21 16:10 | 2.88 | 2021-07-26 15:12 | 126 | Complete | 2460 | 2460 | 1 | 1 | 2460 | 2828.16 | 2828.16
PM Period 4 | 2021-07-19 11:10 | 14.63 | 2021-08-09 08:12 | 128 | Complete | 10192 | 10192 | 1 | 1 | 10192 | 11411.4 | 11411.4
Milestone 4 | 2021-08-09 08:12 | 0 | 2021-08-09 08:12 | 113 | Complete | 0 | 0 | 1 | 1 | 0 | -50000 | -50000
Design Verification Activities | 2021-08-09 08:12 | 4.19 | 2021-08-13 09:43 | 113 | Complete | 3444 | 3444 | 1 | 1 | 3444 | 4114.58 | 4114.58
Verification Design Review | 2021-08-13 09:43 | 2.31 | 2021-08-17 13:12 | 109 | Complete | 1968 | 1968 | 1 | 1 | 1968 | 2268.42 | 2268.42
Release Pre-Production Specs | 2021-08-17 13:12 | 6 | 2021-08-25 13:12 | 107 | Complete | 4920 | 4920 | 1 | 1 | 4920 | 5892 | 5892
PM Period 5 | 2021-08-09 08:12 | 17 | 2021-09-01 08:12 | 113 | Complete | 11760 | 11760 | 1 | 1 | 11760 | 13260 | 13260
Milestone 5 | 2021-09-01 08:12 | 0 | 2021-09-01 08:12 | 96 | Complete | 0 | 0 | 1 | 1 | 0 | 15000 | 15000
Identify Vendors | 2021-09-01 08:12 | 4.5 | 2021-09-07 13:12 | 96 | Complete | 2800 | 2800 | 1 | 1 | 2800 | 3528 | 3528
Develop and Issue RFQ | 2021-09-07 13:12 | 3.88 | 2021-09-13 09:02 | 92 | Complete | 2400 | 2400 | 1 | 1 | 2400 | 3041.92 | 3041.92
Build Functional Model | 2021-09-01 08:12 | 11.25 | 2021-09-16 10:12 | 96 | Complete | 8856 | 8856 | 1 | 1 | 8856 | 11047.5 | 11047.5
Evaluate Design Specs | 2021-09-01 08:12 | 14.88 | 2021-09-21 16:14 | 96 | Complete | 6000 | 6000 | 1 | 1 | 6000 | 8928 | 8928
PM Period 6 | 2021-09-01 08:12 | 10.25 | 2021-09-15 10:12 | 96 | Complete | 7056 | 7056 | 1 | 1 | 7056 | 7995 | 7995
Milestone 6 | 2021-09-21 16:14 | 0 | 2021-09-21 16:14 | 82 | Complete | 0 | 0 | 1 | 1 | 0 | 0 | 0
Issue Sample | 2021-09-21 16:14 | 7.5 | 2021-10-01 11:14 | 82 | Complete | 3000 | 3000 | 1 | 1 | 3000 | 4500 | 4500
Perform Supplier Process Capability | 2021-10-01 11:14 | 17.13 | 2021-10-26 13:17 | 74 | Complete | 6608 | 6608 | 1 | 1 | 6608 | 9250 | 9250
Develop Testing Protocol for Prototype | 2021-09-21 16:14 | 10.25 | 2021-10-06 09:14 | 82 | Complete | 3520 | 3520 | 1 | 1 | 3520 | 4530.5 | 4530.5
PM Period 7 | 2021-09-21 16:14 | 12.5 | 2021-10-08 11:14 | 82 | Complete | 8624 | 8624 | 1 | 1 | 8624 | 9750 | 9750
Milestone 7 | 2021-09-21 16:14 | 0 | 2021-09-21 16:14 | 82 | Complete | 0 | 0 | 1 | 1 | 0 | 35000 | 35000
Approve Sample Parts | 2021-10-26 13:17 | 10.13 | 2021-11-09 14:19 | 57 | Complete | 4352 | 4352 | 1 | 1 | 4352 | 6078 | 6078
Design Validation Activities | 2021-11-12 10:17 | 3.06 | 2021-11-16 16:02 | 44 | Complete | 2200 | 2200 | 1 | 1 | 2200 | 3188.5 | 3188.5
Test Prototype | 2021-10-26 13:17 | 12.75 | 2021-11-12 10:17 | 57 | Complete | 6000 | 6000 | 1 | 1 | 6000 | 5635.52 | 5635.52
Process Engineering Plan | 2021-10-26 13:17 | 17.63 | 2021-11-19 09:19 | 57 | Complete | 6000 | 6000 | 1 | 1 | 6000 | 7811.1 | 7811.1
Show Functional Model at Trade Show | 2021-11-01 08:00 | 3.25 | 2021-11-04 10:00 | 53 | Complete | 2352 | 2352 | 1 | 1 | 2352 | 2535 | 2535
PM Period 8 | 2021-10-26 13:17 | 3.38 | 2021-10-29 16:19 | 57 | Complete | 2352 | 2352 | 1 | 1 | 2352 | 2636.4 | 2636.4
Milestone 8 | 2021-11-19 09:19 | 0 | 2021-11-19 09:19 | 39 | Complete | 0 | 0 | 1 | 0 | 0 | 0 | 0
Validation Design Review | 2021-11-19 09:19 | 4.75 | 2021-11-25 16:19 | 39 | Complete | 1968 | 1968 | 1 | 1 | 1968 | 2565 | 2565
Approve Model Design | 2021-11-25 16:19 | 5.13 | 2021-12-03 08:22 | 35 | Complete | 1968 | 1968 | 1 | 1 | 1968 | 2267.46 | 2267.46
Evaluate Test Results | 2021-11-19 09:19 | 7.38 | 2021-11-30 13:22 | 39 | Complete | 3600 | 3600 | 1 | 1 | 3600 | 4428 | 4428
PM Period 9 | 2021-11-19 09:19 | 4.63 | 2021-11-25 15:22 | 39 | Complete | 3136 | 3136 | 1 | 1 | 3136 | 3611.4 | 3611.4
Milestone 9 | 2021-12-03 08:22 | 0 | 2021-12-03 08:22 | 29 | Complete | 0 | 0 | 1 | 1 | 0 | 0 | 0
Qualify Supplier | 2021-12-03 08:22 | 12.5 | 2021-12-21 13:22 | 29 | Complete | 6000 | 6000 | 1 | 1 | 6000 | 7500 | 7500
Design Transfer Activities | 2021-12-03 08:22 | 8.25 | 2021-12-15 10:22 | 29 | Complete | 4200 | 4200 | 1 | 1 | 4200 | 4455 | 4455
Product Release Meetings | 2021-12-15 10:22 | 3.38 | 2021-12-20 14:24 | 21 | Complete | 3000 | 3000 | 1 | 1 | 3000 | 2636 | 2636
Develop Production Plan | 2021-12-03 08:22 | 8.25 | 2021-12-15 10:22 | 29 | Complete | 2400 | 2400 | 1 | 1 | 2400 | 3646.5 | 3646.5
PM Period 10 | 2021-12-03 08:22 | 5.63 | 2021-12-10 14:24 | 29 | Complete | 3920 | 3920 | 1 | 1 | 3920 | 4391.4 | 4391.4
Milestone 10 | 2021-12-21 13:22 | 0 | 2021-12-21 13:22 | 17 | Complete | 0 | 0 | 1 | 1 | 0 | 10000 | 10000
Assess RFQ Responses | 2021-12-21 13:22 | 6.06 | 2021-12-29 13:50 | 17 | Complete | 6000 | 6000 | 1 | 1 | 6000 | 6908.4 | 6908.4
Develop Production Control Plan | 2021-12-21 13:22 | 11.13 | 2022-01-05 14:24 | 17 | Complete | 3400 | 3400 | 1 | 1 | 3400 | 4919.46 | 4919.46
Approve Production Parts | 2022-01-05 14:24 | 3.31 | 2022-01-10 16:53 | 6 | Complete | 2000 | 2000 | 1 | 1 | 2000 | 3250.42 | 3250.42
Contracting for Deliveries | 2022-01-10 16:53 | 5.13 | 2022-01-18 08:55 | 3 | Busy | 3200 | 3200 | 1 | 0.39 | 1248 | 5037.66 | 1964.6874
PM Period 11 | 2021-12-21 13:22 | 14.75 | 2022-01-11 10:22 | 17 | Complete | 5720 | 5720 | 1 | 1 | 5720 | 11505 | 11505
Milestone 11 | 2022-01-18 08:55 | 0 | 2022-01-18 08:55 | -5 | Busy | 0 | 0 | 1 | 0 | 0 | 0 | 0
Submit Production Purchase Order | 2022-01-18 08:55 | 1.31 | 2022-01-19 11:24 | -5 | Busy | 800 | 800 | 1 | 0 | 0 | 1286.42 | 0
Production Pilot Test | 2022-01-19 11:24 | 3.19 | 2022-01-24 13:55 | -6 | Busy | 2000 | 2000 | 1 | 0 | 0 | 3132.58 | 0
Debugging Production System | 2022-01-24 13:55 | 2.44 | 2022-01-27 08:26 | -9 | Busy | 1600 | 1600 | 1 | 0 | 0 | 2396.08 | 0
Production Release | 2022-01-27 08:26 | 2 | 2022-01-31 08:26 | -12 | Busy | 1200 | 1200 | 1 | 0 | 0 | 1964 | 0
Product Launch | 2022-02-02 11:58 | 3.38 | 2022-02-07 16:00 | -16 | Busy | 1512 | 1512 | 1 | 0 | 0 | 2636.4 | 0
PM Period 12 | 2022-01-18 08:55 | 11.38 | 2022-02-02 11:58 | -5 | Busy | 4400 | 4400 | 1 | 0 | 0 | 8876.4 | 0
Milestone 12 | 2022-02-07 16:00 | 0 | 2022-02-07 16:00 | -19 | Busy | 0 | 0 | 1 | 0 | 0 | 0 | 0
Totals | [6 empty] | 296072 |  |  | 282608 |  | 370271.3074
CPI | 0.7632
SPI | 0.9545
ETC | 17641.5094
EAC | 387912.8168
Formulas:
Network Days to Analysis Date = NETWORKDAYS([Real Start Date],D3)

## Period 12
Period 12 |  | Analysis Date at 17:00
2022-02-01
Task | Real Start Date | Real Duration | Real End Date | Network Days to Analysis Date | Complete/Busy | Full Budget | Planned Value | %Sched Completion | %Actual Completion | Earned Value | Actual Cost | Actual Cost at Analysis Date | Planned Start Date | Network Days to Analysis Date | Planned Duration
Evaluate Market | 2021-03-31 09:00 | 6.69 | 2021-04-08 15:31 | 220 | Complete | 7728 | 7728 | 1 | 1 | 7728 | 8563.2 | 8563.2
Develop Business Opportunity | 2021-04-08 15:31 | 8.06 | 2021-04-20 16:00 | 214 | Complete | 9016 | 9016 | 1 | 1 | 9016 | 10316.8 | 10316.8
Customer Preference Study | 2021-04-20 16:00 | 12.13 | 2021-05-07 08:02 | 206 | Complete | 13524 | 13524 | 1 | 1 | 13524 | 14240 | 14240
Business Evaluation (NPV, etc.) | 2021-05-07 08:02 | 2.38 | 2021-05-11 11:05 | 193 | Complete | 2576 | 2576 | 1 | 1 | 2576 | 4973 | 4973
PM Period 1 | 2021-03-31 09:00 | 18.06 | 2021-04-26 09:29 | 220 | Complete | 12300 | 12300 | 1 | 1 | 12300 | 17734.92 | 17734.92
Milestone 1 | 2021-05-11 11:05 | 0 | 2021-05-11 11:05 | 191 | Complete | 0 | 0 | 1 | 1 | 0 | 0 | 0
Design and Development Plan | 2021-05-11 11:05 | 3.88 | 2021-05-17 10:07 | 191 | Complete | 2352 | 2352 | 1 | 1 | 2352 | 3585.12 | 3585.12
Design Specs | 2021-05-17 10:07 | 13.75 | 2021-06-04 08:07 | 187 | Complete | 8624 | 8624 | 1 | 1 | 8624 | 12705 | 12705
Develop Prelim Marketing Plan | 2021-05-11 11:05 | 2.81 | 2021-05-14 09:34 | 191 | Complete | 3220 | 3220 | 1 | 1 | 3220 | 3596.8 | 3596.8
Develop Marketing Program | 2021-05-14 09:34 | 8.44 | 2021-05-26 14:05 | 188 | Complete | 9660 | 9660 | 1 | 1 | 9660 | 10803.2 | 10803.2
PM Period 2 | 2021-05-11 11:05 | 10.06 | 2021-05-25 11:34 | 191 | Complete | 6888 | 6888 | 1 | 1 | 6888 | 9878.92 | 9878.92
Milestone 2 | 2021-06-04 08:07 | 0 | 2021-06-04 08:07 | 173 | Complete | 0 | 0 | 1 | 1 | 0 | 5000 | 5000
Identify Testing Requirements | 2021-06-04 08:07 | 6.25 | 2021-06-14 10:07 | 173 | Complete | 3920 | 3920 | 1 | 1 | 3920 | 5775 | 5775
Risk Analysis | 2021-06-14 10:07 | 7.06 | 2021-06-23 10:36 | 167 | Complete | 3920 | 3920 | 1 | 1 | 3920 | 6523.44 | 6523.44
Train Sales Team | 2021-06-04 08:07 | 24.88 | 2021-07-08 16:10 | 173 | Complete | 11088 | 11088 | 1 | 1 | 11088 | 12440 | 12440
Advertising Campaign | 2021-06-04 08:07 | 31.38 | 2021-07-19 11:10 | 173 | Complete | 21952 | 21952 | 1 | 1 | 21952 | 24476.4 | 24476.4
PM Period 3 | 2021-06-04 08:07 | 10.13 | 2021-06-18 09:10 | 173 | Complete | 6888 | 6888 | 1 | 1 | 6888 | 9947.66 | 9947.66
Milestone 3 | 2021-07-19 11:10 | 0 | 2021-07-19 11:10 | 142 | Complete | 0 | 0 | 1 | 1 | 0 | 0 | 0
Design Labelling | 2021-07-14 08:07 | 3.25 | 2021-07-19 10:07 | 145 | Complete | 1960 | 1960 | 1 | 1 | 1960 | 3003 | 3003
Approve Design | 2021-07-19 10:07 | 2.63 | 2021-07-21 16:10 | 142 | Complete | 1568 | 1568 | 1 | 1 | 1568 | 2430.12 | 2430.12
Initial Engineering Specs | 2021-07-21 16:10 | 2.88 | 2021-07-26 15:12 | 140 | Complete | 2460 | 2460 | 1 | 1 | 2460 | 2828.16 | 2828.16
PM Period 4 | 2021-07-19 11:10 | 14.63 | 2021-08-09 08:12 | 142 | Complete | 10192 | 10192 | 1 | 1 | 10192 | 11411.4 | 11411.4
Milestone 4 | 2021-08-09 08:12 | 0 | 2021-08-09 08:12 | 127 | Complete | 0 | 0 | 1 | 1 | 0 | -50000 | -50000
Design Verification Activities | 2021-08-09 08:12 | 4.19 | 2021-08-13 09:43 | 127 | Complete | 3444 | 3444 | 1 | 1 | 3444 | 4114.58 | 4114.58
Verification Design Review | 2021-08-13 09:43 | 2.31 | 2021-08-17 13:12 | 123 | Complete | 1968 | 1968 | 1 | 1 | 1968 | 2268.42 | 2268.42
Release Pre-Production Specs | 2021-08-17 13:12 | 6 | 2021-08-25 13:12 | 121 | Complete | 4920 | 4920 | 1 | 1 | 4920 | 5892 | 5892
PM Period 5 | 2021-08-09 08:12 | 17 | 2021-09-01 08:12 | 127 | Complete | 11760 | 11760 | 1 | 1 | 11760 | 13260 | 13260
Milestone 5 | 2021-09-01 08:12 | 0 | 2021-09-01 08:12 | 110 | Complete | 0 | 0 | 1 | 1 | 0 | 15000 | 15000
Identify Vendors | 2021-09-01 08:12 | 4.5 | 2021-09-07 13:12 | 110 | Complete | 2800 | 2800 | 1 | 1 | 2800 | 3528 | 3528
Develop and Issue RFQ | 2021-09-07 13:12 | 3.88 | 2021-09-13 09:02 | 106 | Complete | 2400 | 2400 | 1 | 1 | 2400 | 3041.92 | 3041.92
Build Functional Model | 2021-09-01 08:12 | 11.25 | 2021-09-16 10:12 | 110 | Complete | 8856 | 8856 | 1 | 1 | 8856 | 11047.5 | 11047.5
Evaluate Design Specs | 2021-09-01 08:12 | 14.88 | 2021-09-21 16:14 | 110 | Complete | 6000 | 6000 | 1 | 1 | 6000 | 8928 | 8928
PM Period 6 | 2021-09-01 08:12 | 10.25 | 2021-09-15 10:12 | 110 | Complete | 7056 | 7056 | 1 | 1 | 7056 | 7995 | 7995
Milestone 6 | 2021-09-21 16:14 | 0 | 2021-09-21 16:14 | 96 | Complete | 0 | 0 | 1 | 1 | 0 | 0 | 0
Issue Sample | 2021-09-21 16:14 | 7.5 | 2021-10-01 11:14 | 96 | Complete | 3000 | 3000 | 1 | 1 | 3000 | 4500 | 4500
Perform Supplier Process Capability | 2021-10-01 11:14 | 17.13 | 2021-10-26 13:17 | 88 | Complete | 6608 | 6608 | 1 | 1 | 6608 | 9250 | 9250
Develop Testing Protocol for Prototype | 2021-09-21 16:14 | 10.25 | 2021-10-06 09:14 | 96 | Complete | 3520 | 3520 | 1 | 1 | 3520 | 4530.5 | 4530.5
PM Period 7 | 2021-09-21 16:14 | 12.5 | 2021-10-08 11:14 | 96 | Complete | 8624 | 8624 | 1 | 1 | 8624 | 9750 | 9750
Milestone 7 | 2021-09-21 16:14 | 0 | 2021-09-21 16:14 | 96 | Complete | 0 | 0 | 1 | 1 | 0 | 35000 | 35000
Approve Sample Parts | 2021-10-26 13:17 | 10.13 | 2021-11-09 14:19 | 71 | Complete | 4352 | 4352 | 1 | 1 | 4352 | 6078 | 6078
Design Validation Activities | 2021-11-12 10:17 | 3.06 | 2021-11-16 16:02 | 58 | Complete | 2200 | 2200 | 1 | 1 | 2200 | 3188.5 | 3188.5
Test Prototype | 2021-10-26 13:17 | 12.75 | 2021-11-12 10:17 | 71 | Complete | 6000 | 6000 | 1 | 1 | 6000 | 5635.52 | 5635.52
Process Engineering Plan | 2021-10-26 13:17 | 17.63 | 2021-11-19 09:19 | 71 | Complete | 6000 | 6000 | 1 | 1 | 6000 | 7811.1 | 7811.1
Show Functional Model at Trade Show | 2021-11-01 08:00 | 3.25 | 2021-11-04 10:00 | 67 | Complete | 2352 | 2352 | 1 | 1 | 2352 | 2535 | 2535
PM Period 8 | 2021-10-26 13:17 | 3.38 | 2021-10-29 16:19 | 71 | Complete | 2352 | 2352 | 1 | 1 | 2352 | 2636.4 | 2636.4
Milestone 8 | 2021-11-19 09:19 | 0 | 2021-11-19 09:19 | 53 | Complete | 0 | 0 | 1 | 1 | 0 | 0 | 0
Validation Design Review | 2021-11-19 09:19 | 4.75 | 2021-11-25 16:19 | 53 | Complete | 1968 | 1968 | 1 | 1 | 1968 | 2565 | 2565
Approve Model Design | 2021-11-25 16:19 | 5.13 | 2021-12-03 08:22 | 49 | Complete | 1968 | 1968 | 1 | 1 | 1968 | 2267.46 | 2267.46
Evaluate Test Results | 2021-11-19 09:19 | 7.38 | 2021-11-30 13:22 | 53 | Complete | 3600 | 3600 | 1 | 1 | 3600 | 4428 | 4428
PM Period 9 | 2021-11-19 09:19 | 4.63 | 2021-11-25 15:22 | 53 | Complete | 3136 | 3136 | 1 | 1 | 3136 | 3611.4 | 3611.4
Milestone 9 | 2021-12-03 08:22 | 0 | 2021-12-03 08:22 | 43 | Complete | 0 | 0 | 1 | 1 | 0 | 0 | 0
Qualify Supplier | 2021-12-03 08:22 | 12.5 | 2021-12-21 13:22 | 43 | Complete | 6000 | 6000 | 1 | 1 | 6000 | 7500 | 7500
Design Transfer Activities | 2021-12-03 08:22 | 8.25 | 2021-12-15 10:22 | 43 | Complete | 4200 | 4200 | 1 | 1 | 4200 | 4455 | 4455
Product Release Meetings | 2021-12-15 10:22 | 3.38 | 2021-12-20 14:24 | 35 | Complete | 3000 | 3000 | 1 | 1 | 3000 | 2636 | 2636
Develop Production Plan | 2021-12-03 08:22 | 8.25 | 2021-12-15 10:22 | 43 | Complete | 2400 | 2400 | 1 | 1 | 2400 | 3646.5 | 3646.5
PM Period 10 | 2021-12-03 08:22 | 5.63 | 2021-12-10 14:24 | 43 | Complete | 3920 | 3920 | 1 | 1 | 3920 | 4391.4 | 4391.4
Milestone 10 | 2021-12-21 13:22 | 0 | 2021-12-21 13:22 | 31 | Complete | 0 | 0 | 1 | 1 | 0 | 10000 | 10000
Assess RFQ Responses | 2021-12-21 13:22 | 6.06 | 2021-12-29 13:50 | 31 | Complete | 6000 | 6000 | 1 | 1 | 6000 | 6908.4 | 6908.4
Develop Production Control Plan | 2021-12-21 13:22 | 11.13 | 2022-01-05 14:24 | 31 | Complete | 3400 | 3400 | 1 | 1 | 3400 | 4919.46 | 4919.46
Approve Production Parts | 2022-01-05 14:24 | 3.31 | 2022-01-10 16:53 | 20 | Complete | 2000 | 2000 | 1 | 1 | 2000 | 3250.42 | 3250.42
Contracting for Deliveries | 2022-01-10 16:53 | 5.13 | 2022-01-18 08:55 | 17 | Complete | 3200 | 3200 | 1 | 1 | 3200 | 5037.66 | 5037.66
PM Period 11 | 2021-12-21 13:22 | 14.75 | 2022-01-11 10:22 | 31 | Complete | 5720 | 5720 | 1 | 1 | 5720 | 11505 | 11505
Milestone 11 | 2022-01-18 08:55 | 0 | 2022-01-18 08:55 | 11 | Complete | 0 | 0 | 1 | 1 | 0 | 0 | 0
Submit Production Purchase Order | 2022-01-18 08:55 | 1.31 | 2022-01-19 11:24 | 11 | Complete | 800 | 800 | 1 | 1 | 800 | 1286.42 | 1286.42
Production Pilot Test | 2022-01-19 11:24 | 3.19 | 2022-01-24 13:55 | 10 | Complete | 2000 | 2000 | 1 | 1 | 2000 | 3132.58 | 3132.58
Debugging Production System | 2022-01-24 13:55 | 2.44 | 2022-01-27 08:26 | 7 | Complete | 1600 | 1600 | 1 | 1 | 1600 | 2396.08 | 2396.08
Production Release | 2022-01-27 08:26 | 2 | 2022-01-31 08:26 | 4 | Complete | 1200 | 1200 | 1 | 1 | 1200 | 1964 | 1964
Product Launch | 2022-02-02 11:58 | 3.38 | 2022-02-07 16:00 | -2 | Busy | 1512 | 1512 | 1 | 0.39 | 589.68 | 2636.4 | 1028.196
PM Period 12 | 2022-01-18 08:55 | 11.38 | 2022-02-02 11:58 | 11 | Busy | 4400 | 4400 | 1 | 1 | 4400 | 8876.4 | 8876.4
Milestone 12 | 2022-02-07 16:00 | 0 | 2022-02-07 16:00 | -5 | Busy | 0 | 0 | 1 | 0 | 0 | 0 | 0
Totals | [6 empty] | 296072 |  |  | 295149.68 |  | 392027.956
CPI | 0.7529
SPI | 0.9969
ETC | 1225.0232
EAC | 393252.9792
Formulas:
Network Days to Analysis Date = NETWORKDAYS([Real Start Date],D3)