## Summary
EVA Measures |  | Abbrev. | Formula |  |  |  | Note:
Baseline Cost |  | BC
Planned Value |  | PV | BC * PlannedComplete% |  |  |  | Managerial actions and unallocated resource costs are assumed to take place at the end of their respective periods
Earned Value |  | EV | BC * Complete%
Actual Cost |  | AC
Cost Performance Index |  | CPI | EV/AC
Schedule Performance Index |  | SPI | EV/PV
Estimated Cost to Complete |  | ETC | (BC(total)-EV)/CPI
Estimated Cost at Completion |  | EAC | AC+EAC
Period | Milestone Date | PV | EV | AC | CPI | SPI | ETC | EAC
1 | 2021-05-11 | 48200.2168 | 41447.5037 | 50854.92 | 0.815 | 0.8599 | 312422.6948 | 363277.6148
2 | 2021-06-04 | 91169.028 | 73997.2533 | 93071.285 | 0.7951 | 0.8116 | 279304.1714 | 372375.4564
3 | 2021-07-19 | 135916.1568 | 121281.3061 | 152671.485 | 0.7944 | 0.8923 | 220028.5673 | 372700.0523
4 | 2021-08-09 | 156368.556 | 137728.051 | 172691.79 | 0.7975 | 0.8808 | 198550.4062 | 371242.1962
5 | 2021-09-01 | 188639.92 | 159835.4118 | 198891.19 | 0.8036 | 0.8473 | 169532.8375 | 368424.0275
6 | 2021-09-21 | 213560.1216 | 187248.9232 | 238029.06 | 0.7867 | 0.8768 | 138328.5582 | 376357.6182
7 | 2021-10-26 | 257839.92 | 209428.6741 | 271402.2013 | 0.7717 | 0.8122 | 112275.918 | 383678.1193
8 | 2021-11-19 | 267119.756 | 232342.0997 | 303330.6026 | 0.766 | 0.8698 | 83198.3033 | 386528.9059
9 | 2021-12-03 | 280120.132 | 243286.3691 | 316883.5342 | 0.7677 | 0.8685 | 68758.1489 | 385641.6831
Status Discussion At the end of period 9, the project is both behind schedule and over budget (seen in CPI < 1 and SPI <1). The estimated cost at project completion (EAC) is also above the 380 000 budget. The CPI is decreasing as the project progresses, this probably indicates that the resources of this project are costing too much relative to the work that they deliver. Therefore, cheaper alternative resources should be considered at this stage. The CPI has also been negatively affected by the fact that an operations specialist was not secured. This lead to more expensive resources being assigned to tasks that were budgeted for cheaper resources, leading to higher actual costs in later periods (as seen by the increasing gap on the AC/EV graph) and a lower CPI. The SPI is reasonably consistent across the 9 periods. While an SPI less than 1 indicates that the project is behind schedule, in this case it is probably due to the fact that the baseline plan is very optimistic and does not take worker inefficiency into account. Therefore, it is not neccesary to take corrective action as at the current SPI, the project should still finish before the March 2022 deadline.
PV Discussion The PV is above the EV for this project so far, therefore the project is behind schedule, a fact that is also reflected on the SPI/CPI graph below. The gap between these curves has remained relatively constant up to period 7, where it became larger. This is probably due to the quality engineer underperforming and due to the fact that an operations specialist was not secured, leading to a higher workload on the other resources. Luckily, this gap has started to shrink and corrective action does not have to be taken.
AC Discussion
The AC is also above the EV up to period 9, meaning that the project is over budget. A similar trend to the PV can be seen with regards to the gap between the AC and EV curves, with the gap widening in period 7. This is also probably due to the fact that an operations specialist was not secured, leading to tasks being allocated to more expensive resources such as the Quality Engineer and the second, overbid enigneer. Unlike the PV, this gap is not shrinking and there is a risk of the project running over budget. Therfore, corrective action must be considered to reduce project costs if feasible.

## Full Analysis
Period | Milestone Date | PV | EV | AC | CPI | SPI | ETC | EAC
1 | 2021-05-11 | 48200.2168 | 41447.5037 | 50854.92 | 0.815 | 0.8599 | 312422.6948 | 363277.6148
2 | 2021-06-04 | 91169.028 | 73997.2533 | 93071.285 | 0.7951 | 0.8116 | 279304.1714 | 372375.4564
3 | 2021-07-19 | 135916.1568 | 121281.3061 | 152671.485 | 0.7944 | 0.8923 | 220028.5673 | 372700.0523
4 | 2021-08-09 | 156368.556 | 137728.051 | 172691.79 | 0.7975 | 0.8808 | 198550.4062 | 371242.1962
5 | 2021-09-01 | 188639.92 | 159835.4118 | 198891.19 | 0.8036 | 0.8473 | 169532.8375 | 368424.0275
6 | 2021-09-21 | 213560.1216 | 187248.9232 | 238029.06 | 0.7867 | 0.8768 | 138328.5582 | 376357.6182
7 | 2021-10-26 | 257839.92 | 209428.6741 | 271402.2013 | 0.7717 | 0.8122 | 112275.918 | 383678.1193
8 | 2021-11-19 | 267119.756 | 232342.0997 | 303330.6026 | 0.766 | 0.8698 | 83198.3033 | 386528.9059
9 | 2021-12-03 | 280120.132 | 243286.3691 | 316883.5342 | 0.7677 | 0.8685 | 68758.1489 | 385641.6831
10 | 2021-12-21 | 286240 | 260163 | 337210.5567 | 0.7715 | 0.9089 | 46544.394 | 383754.9507
11 | 2022-01-18 | 296072 | 282616.6602 | 370026.4908 | 0.7638 | 0.9546 | 17616.3129 | 387642.8037
12 | 2022-02-07 | 296072 | 296072 | 393417.71 | 0.7526 | 1 | 0 | 393417.71

## Team Performance
Period | Efficiency | Cohesion | Composition | Longevity
1 | 79 | 94 | 87 | 100
2 | 78 | 87 | 89 | 76
3 | 79 | 85 | 89 | 71
4 | 76 | 75 | 89 | 63
5 | 78 | 75 | 89 | 60
6 | 77 | 72 | 89 | 46
7 | 78 | 69 | 90 | 48
8 | 78 | 65 | 88 | 44
9 | 79 | 66 | 88 | 43
10 | 81 | 67 | 88 | 41
11 | 83 | 68 | 88 | 40
12 | 85 | 68 | 87 | 38

## Period 1
Period 2 |  | Analysis Date at 17:00
2021-05-05 17:00
Task | Real Start Date | Real Duration | Real End Date | Network Days to Analysis Date | Complete/Busy | Full Budget | Planned Value | %Sched Completion | %Actual Completion | Earned Value | Actual Cost | Actual Cost at Analysis Date | Planned Start Date | Network Days to Analysis Date | Planned Duration
Evaluate Market | 2021-03-31 09:00 | 6.69 | 2021-04-08 15:31 | 26 | Complete | 7728 | 7728 | 1 | 1 | 7728 | 8563.2 | 8563.2
Develop Business Opportunity | 2021-04-08 15:31 | 8.06 | 2021-04-20 16:00 | 20 | Complete | 9016 | 9016 | 1 | 1 | 9016 | 10316.8 | 10316.8
Customer Preference Study | 2021-04-20 16:00 | 12.13 | 2021-05-07 08:02 | 12 | Busy | 13524 | 13524 | 1 | 0.91715 | 12403.5037 | 15526.4 | 14240
Business Evaluation (NPV, etc.) | 2021-05-07 08:02 | 2.38 | 2021-05-11 11:05 | -3 | Busy | 2576 | 2576 | 1 | 0 | 0 | 3046.4 | 0
PM Period 1 | 2021-03-31 09:00 | 18.06 | 2021-04-26 09:29 | 26 | Complete | 12300 | 12300 | 1 | 1 | 12300 | 17734.92 | 17734.92
Milestone 1 | 2021-05-11 11:05 | 0 | 2021-05-11 11:05 | -5 | Busy | 0 | 0 | 1 | 0 | 0 | 40 | 0
Design and Development Plan | 2021-05-11 11:05 | 3.88 | 2021-05-17 10:07 | -5 | Busy | 2352 | 783.9216 | 0.3333 | 0 | 0 | 3585.12 | 0 | 2021-05-05 | 1 | 3
Design Specs | 2021-05-17 10:07 | 13.75 | 2021-06-04 08:07 | -9 | Busy | 8624 | 0 | 0 | 0 | 0 | 12705 | 0
Develop Prelim Marketing Plan | 2021-05-11 11:05 | 2.81 | 2021-05-14 09:34 | -5 | Busy | 3220 | 1288 | 0.4 | 0 | 0 | 3596.8 | 0 | 2021-05-05 | 1 | 2.5
Develop Marketing Program | 2021-05-14 09:34 | 8.44 | 2021-05-26 14:05 | -8 | Busy | 9660 | 0 | 0 | 0 | 0 | 10803.2 | 0
PM Period 2 | 2021-05-11 11:05 | 10.06 | 2021-05-25 11:34 | -5 | Busy | 6888 | 984.2952 | 0.1429 | 0 | 0 | 9878.92 | 0 | 2021-05-05 | 1 | 7
Milestone 2 | 2021-06-04 08:07 | 0 | 2021-06-04 08:07 | -23 | Busy | 0 | 0 | 0 | 0 | 0 | 360 | 0
Totals | [6 empty] | 48200.2168 |  |  | 41447.5037 |  | 50854.92
CPI | 0.815
SPI | 0.8599
ETC | 312422.6948
EAC | 363277.6148
Formulas:
Network Days to Analysis Date = NETWORKDAYS([Real Start Date],D3)
Network Days to Analysis Date = NETWORKDAYS([Planned Start Date],D3)

## Period 2
Period 2 |  | Analysis Date at 17:00
2021-05-31 17:00
Task | Real Start Date | Real Duration | Real End Date | Network Days to Analysis Date | Complete/Busy | Full Budget | Planned Value | %Sched Completion | %Actual Completion | Earned Value | Actual Cost | Actual Cost at Analysis Date | Planned Start Date | Network Days to Analysis Date | Planned Duration
Evaluate Market | 2021-03-31 09:00 | 6.69 | 2021-04-08 15:31 | 44 | Complete | 7728 | 7728 | 1 | 1 | 7728 | 8563.2 | 8563.2
Develop Business Opportunity | 2021-04-08 15:31 | 8.06 | 2021-04-20 16:00 | 38 | Complete | 9016 | 9016 | 1 | 1 | 9016 | 10316.8 | 10316.8
Customer Preference Study | 2021-04-20 16:00 | 12.13 | 2021-05-07 08:02 | 30 | Complete | 13524 | 13524 | 1 | 1 | 13524 | 15526.4 | 15526.4
Business Evaluation (NPV, etc.) | 2021-05-07 08:02 | 2.38 | 2021-05-11 11:05 | 17 | Complete | 2576 | 2576 | 1 | 1 | 2576 | 3046.4 | 3046.4
PM Period 1 | 2021-03-31 09:00 | 18.06 | 2021-04-26 09:29 | 44 | Complete | 12300 | 12300 | 1 | 1 | 12300 | 17734.92 | 17734.92
Milestone 1 | 2021-05-11 11:05 | 0 | 2021-05-11 11:05 | 15 | Complete | 0 | 0 | 1 | 1 | 0 | 40 | 40
Design and Development Plan | 2021-05-11 11:05 | 3.88 | 2021-05-17 10:07 | 15 | Complete | 2352 | 2352 | 1 | 1 | 2352 | 3585.12 | 3585.12
Design Specs | 2021-05-17 10:07 | 13.75 | 2021-06-04 08:07 | 11 | Busy | 8624 | 8624 | 1 | 0.78076 | 6733.2533 | 12705 | 9919.525
Develop Prelim Marketing Plan | 2021-05-11 11:05 | 2.81 | 2021-05-14 09:34 | 15 | Complete | 3220 | 3220 | 1 | 1 | 3220 | 3596.8 | 3596.8
Develop Marketing Program | 2021-05-14 09:34 | 8.44 | 2021-05-26 14:05 | 12 | Complete | 9660 | 9660 | 1 | 1 | 9660 | 10803.2 | 10803.2
PM Period 2 | 2021-05-11 11:05 | 10.06 | 2021-05-25 11:34 | 15 | Complete | 6888 | 6888 | 1 | 1 | 6888 | 9878.92 | 9878.92
Milestone 2 | 2021-06-04 08:07 | 0 | 2021-06-04 08:07 | -5 | Busy | 0 | 0 | 1 | 0 | 0 | 360 | 0
Identify Testing Requirements | 2021-06-04 08:07 | 6.25 | 2021-06-14 10:07 | -5 | Busy | 3920 | 3920 | 1 | 0 | 0 | 5775 | 0 | 2021-05-25 | 5 | 5
Risk Analysis | 2021-06-14 10:07 | 7.06 | 2021-06-23 10:36 | -11 | Busy | 3920 | 0 | 0 | 0 | 0 | 6523.44 | 0
Train Sales Team | 2021-06-04 08:07 | 24.88 | 2021-07-08 16:10 | -5 | Busy | 11088 | 2520.3024 | 0.2273 | 0 | 0 | 12440 | 0 | 2021-05-25 | 5 | 22
Advertising Campaign | 2021-06-04 08:07 | 31.38 | 2021-07-19 11:10 | -5 | Busy | 21952 | 3920.6272 | 0.1786 | 0 | 0 | 24476.4 | 0 | 2021-05-25 | 5 | 28
PM Period 3 | 2021-06-04 08:07 | 10.13 | 2021-06-18 09:10 | -5 | Busy | 6888 | 4920.0984 | 0.7143 | 0 | 0 | 9947.66 | 0 | 2021-05-25 | 5 | 7
Milestone 3 | 2021-07-19 11:10 | 0 | 2021-07-19 11:10 | -36 | Busy | 0 | 0 | 1 | 1 | 0 | 60 | 60
Totals | [6 empty] | 91169.028 |  |  | 73997.2533 |  | 93071.285
CPI | 0.7951
SPI | 0.8116
ETC | 279304.1714
EAC | 372375.4564
Formulas:
Network Days to Analysis Date = NETWORKDAYS([Real Start Date],D3)
Network Days to Analysis Date = NETWORKDAYS([Planned Start Date],D3)

## Period 3
Period 3 |  | Analysis Date at 17:00
2021-07-13 17:00
Task | Real Start Date | Real Duration | Real End Date | Network Days to Analysis Date | Complete/Busy | Full Budget | Planned Value | %Sched Completion | %Actual Completion | Earned Value | Actual Cost | Actual Cost at Analysis Date | Planned Start Date | Network Days to Analysis Date | Planned Duration
Evaluate Market | 2021-03-31 09:00 | 6.69 | 2021-04-08 15:31 | 75 | Complete | 7728 | 7728 | 1 | 1 | 7728 | 8563.2 | 8563.2
Develop Business Opportunity | 2021-04-08 15:31 | 8.06 | 2021-04-20 16:00 | 69 | Complete | 9016 | 9016 | 1 | 1 | 9016 | 10316.8 | 10316.8
Customer Preference Study | 2021-04-20 16:00 | 12.13 | 2021-05-07 08:02 | 61 | Complete | 13524 | 13524 | 1 | 1 | 13524 | 15526.4 | 15526.4
Business Evaluation (NPV, etc.) | 2021-05-07 08:02 | 2.38 | 2021-05-11 11:05 | 48 | Complete | 2576 | 2576 | 1 | 1 | 2576 | 3046.4 | 3046.4
PM Period 1 | 2021-03-31 09:00 | 18.06 | 2021-04-26 09:29 | 75 | Complete | 12300 | 12300 | 1 | 1 | 12300 | 17734.92 | 17734.92
Milestone 1 | 2021-05-11 11:05 | 0 | 2021-05-11 11:05 | 46 | Complete | 0 | 0 | 1 | 1 | 0 | 40 | 40
Design and Development Plan | 2021-05-11 11:05 | 3.88 | 2021-05-17 10:07 | 46 | Complete | 2352 | 2352 | 1 | 1 | 2352 | 3585.12 | 3585.12
Design Specs | 2021-05-17 10:07 | 13.75 | 2021-06-04 08:07 | 42 | Complete | 8624 | 8624 | 1 | 1 | 8624 | 12705 | 12705
Develop Prelim Marketing Plan | 2021-05-11 11:05 | 2.81 | 2021-05-14 09:34 | 46 | Complete | 3220 | 3220 | 1 | 1 | 3220 | 3596.8 | 3596.8
Develop Marketing Program | 2021-05-14 09:34 | 8.44 | 2021-05-26 14:05 | 43 | Complete | 9660 | 9660 | 1 | 1 | 9660 | 10803.2 | 10803.2
PM Period 2 | 2021-05-11 11:05 | 10.06 | 2021-05-25 11:34 | 46 | Complete | 6888 | 6888 | 1 | 1 | 6888 | 9878.92 | 9878.92
Milestone 2 | 2021-06-04 08:07 | 0 | 2021-06-04 08:07 | 28 | Complete | 0 | 0 | 1 | 1 | 0 | 360 | 360
Identify Testing Requirements | 2021-06-04 08:07 | 6.25 | 2021-06-14 10:07 | 28 | Complete | 3920 | 3920 | 1 | 1 | 3920 | 5775 | 5775
Risk Analysis | 2021-06-14 10:07 | 7.06 | 2021-06-23 10:36 | 22 | Complete | 3920 | 3920 | 1 | 1 | 3920 | 6523.44 | 6523.44
Train Sales Team | 2021-06-04 08:07 | 24.88 | 2021-07-08 16:10 | 28 | Complete | 11088 | 11088 | 1 | 1 | 11088 | 12440 | 12440
Advertising Campaign | 2021-06-04 08:07 | 31.38 | 2021-07-19 11:10 | 28 | Busy | 21952 | 21952 | 1 | 0.89182 | 19577.3061 | 24476.4 | 21828.625
PM Period 3 | 2021-06-04 08:07 | 10.13 | 2021-06-18 09:10 | 28 | Complete | 6888 | 6888 | 1 | 1 | 6888 | 9947.66 | 9947.66
Milestone 3 | 2021-07-19 11:10 | 0 | 2021-07-19 11:10 | -5 | Busy | 0 | 0 | 1 | 0 | 0 | 60 | 0
Design Labelling | 2021-07-14 08:07 | 3.25 | 2021-07-19 10:07 | -2 | Busy | 1960 | 1960 | 1 | 0 | 0 | 3003 | 0
Approve Design | 2021-07-19 10:07 | 2.63 | 2021-07-21 16:10 | -5 | Busy | 1568 | 1568 | 1 | 0 | 0 | 2430.12 | 0
Initial Engineering Specs | 2021-07-21 16:10 | 2.88 | 2021-07-26 15:12 | -7 | Busy | 2460 | 2460 | 1 | 0 | 0 | 2828.16 | 0
PM Period 4 | 2021-07-19 11:10 | 14.63 | 2021-08-09 08:12 | -5 | Busy | 10192 | 6272.1568 | 0.6154 | 0 | 0 | 11411.4 | 0 | 2021-07-02 | 8 | 13
Milestone 4 | 2021-08-09 08:12 | 0 | 2021-08-09 08:12 | -20 | Busy | 0 | 0 | 1 | 0 | 0 | 663.75 | 0
Totals | [6 empty] | 135916.1568 |  |  | 121281.3061 |  | 152671.485
CPI | 0.7944
SPI | 0.8923
ETC | 220028.5673
EAC | 372700.0523
Formulas:
Network Days to Analysis Date = NETWORKDAYS([Real Start Date],D3)
Network Days to Analysis Date = NETWORKDAYS([Planned Start Date],D3)

## Period 4
Period 4 |  | Analysis Date at 17:00
2021-08-03 17:00
Task | Real Start Date | Real Duration | Real End Date | Network Days to Analysis Date | Complete/Busy | Full Budget | Planned Value | %Sched Completion | %Actual Completion | Earned Value | Actual Cost | Actual Cost at Analysis Date | Planned Start Date | Network Days to Analysis Date | Planned Duration
Evaluate Market | 2021-03-31 09:00 | 6.69 | 2021-04-08 15:31 | 90 | Complete | 7728 | 7728 | 1 | 1 | 7728 | 8563.2 | 8563.2
Develop Business Opportunity | 2021-04-08 15:31 | 8.06 | 2021-04-20 16:00 | 84 | Complete | 9016 | 9016 | 1 | 1 | 9016 | 10316.8 | 10316.8
Customer Preference Study | 2021-04-20 16:00 | 12.13 | 2021-05-07 08:02 | 76 | Complete | 13524 | 13524 | 1 | 1 | 13524 | 15526.4 | 15526.4
Business Evaluation (NPV, etc.) | 2021-05-07 08:02 | 2.38 | 2021-05-11 11:05 | 63 | Complete | 2576 | 2576 | 1 | 1 | 2576 | 3046.4 | 3046.4
PM Period 1 | 2021-03-31 09:00 | 18.06 | 2021-04-26 09:29 | 90 | Complete | 12300 | 12300 | 1 | 1 | 12300 | 17734.92 | 17734.92
Milestone 1 | 2021-05-11 11:05 | 0 | 2021-05-11 11:05 | 61 | Complete | 0 | 0 | 1 | 1 | 0 | 40 | 40
Design and Development Plan | 2021-05-11 11:05 | 3.88 | 2021-05-17 10:07 | 61 | Complete | 2352 | 2352 | 1 | 1 | 2352 | 3585.12 | 3585.12
Design Specs | 2021-05-17 10:07 | 13.75 | 2021-06-04 08:07 | 57 | Complete | 8624 | 8624 | 1 | 1 | 8624 | 12705 | 12705
Develop Prelim Marketing Plan | 2021-05-11 11:05 | 2.81 | 2021-05-14 09:34 | 61 | Complete | 3220 | 3220 | 1 | 1 | 3220 | 3596.8 | 3596.8
Develop Marketing Program | 2021-05-14 09:34 | 8.44 | 2021-05-26 14:05 | 58 | Complete | 9660 | 9660 | 1 | 1 | 9660 | 10803.2 | 10803.2
PM Period 2 | 2021-05-11 11:05 | 10.06 | 2021-05-25 11:34 | 61 | Complete | 6888 | 6888 | 1 | 1 | 6888 | 9878.92 | 9878.92
Milestone 2 | 2021-06-04 08:07 | 0 | 2021-06-04 08:07 | 43 | Complete | 0 | 0 | 1 | 1 | 0 | 360 | 360
Identify Testing Requirements | 2021-06-04 08:07 | 6.25 | 2021-06-14 10:07 | 43 | Complete | 3920 | 3920 | 1 | 1 | 3920 | 5775 | 5775
Risk Analysis | 2021-06-14 10:07 | 7.06 | 2021-06-23 10:36 | 37 | Complete | 3920 | 3920 | 1 | 1 | 3920 | 6523.44 | 6523.44
Train Sales Team | 2021-06-04 08:07 | 24.88 | 2021-07-08 16:10 | 43 | Complete | 11088 | 11088 | 1 | 1 | 11088 | 12440 | 12440
Advertising Campaign | 2021-06-04 08:07 | 31.38 | 2021-07-19 11:10 | 43 | Complete | 21952 | 21952 | 1 | 1 | 21952 | 24476.4 | 24476.4
PM Period 3 | 2021-06-04 08:07 | 10.13 | 2021-06-18 09:10 | 43 | Complete | 6888 | 6888 | 1 | 1 | 6888 | 9947.66 | 9947.66
Milestone 3 | 2021-07-19 11:10 | 0 | 2021-07-19 11:10 | 12 | Complete | 0 | 0 | 1 | 1 | 0 | 60 | 60
Design Labelling | 2021-07-14 08:07 | 3.25 | 2021-07-19 10:07 | 15 | Complete | 1960 | 1960 | 1 | 1 | 1960 | 3003 | 3003
Approve Design | 2021-07-19 10:07 | 2.63 | 2021-07-21 16:10 | 12 | Complete | 1568 | 1568 | 1 | 1 | 1568 | 2430.12 | 2430.12
Initial Engineering Specs | 2021-07-21 16:10 | 2.88 | 2021-07-26 15:12 | 10 | Complete | 2460 | 2460 | 1 | 1 | 2460 | 2828.16 | 2828.16
PM Period 4 | 2021-07-19 11:10 | 14.63 | 2021-08-09 08:12 | 12 | Busy | 10192 | 10192 | 1 | 0.79318 | 8084.051 | 11411.4 | 9051.25
Milestone 4 | 2021-08-09 08:12 | 0 | 2021-08-09 08:12 | -5 | Busy | 0 | 0 | 1 | 0 | 0 | 663.75 | 0
Design Verification Activities | 2021-08-09 08:12 | 4.19 | 2021-08-13 09:43 | -5 | Busy | 3444 | 3444 | 1 | 0 | 0 | 4114.58 | 0
Verification Design Review | 2021-08-13 09:43 | 2.31 | 2021-08-17 13:12 | -9 | Busy | 1968 | 1968 | 1 | 0 | 0 | 2268.42 | 0
Release Pre-Production Specs | 2021-08-17 13:12 | 6 | 2021-08-25 13:12 | -11 | Busy | 4920 | 3280.164 | 0.6667 | 0 | 0 | 5892 | 0 | 2021-07-29 | 4 | 6
PM Period 5 | 2021-08-09 08:12 | 17 | 2021-09-01 08:12 | -5 | Busy | 11760 | 7840.392 | 0.6667 | 0 | 0 | 13260 | 0 | 2021-07-21 | 10 | 15
Milestone 5 | 2021-09-01 08:12 | 0 | 2021-09-01 08:12 | -22 | Busy | 0 | 0 | 0 | 0 | 0 | 4851 | 0
Totals | [6 empty] | 156368.556 |  |  | 137728.051 |  | 172691.79
CPI | 0.7975
SPI | 0.8808
ETC | 198550.4062
EAC | 371242.1962
Formulas:
Network Days to Analysis Date = NETWORKDAYS([Real Start Date],D3)
Network Days to Analysis Date = NETWORKDAYS([Planned Start Date],D3)

## Period 5
Period 5 |  | Analysis Date at 17:00
2021-08-26 17:00
Task | Real Start Date | Real Duration | Real End Date | Network Days to Analysis Date | Complete/Busy | Full Budget | Planned Value | %Sched Completion | %Actual Completion | Earned Value | Actual Cost | Actual Cost at Analysis Date | Planned Start Date | Network Days to Analysis Date | Planned Duration
Evaluate Market | 2021-03-31 09:00 | 6.69 | 2021-04-08 15:31 | 107 | Complete | 7728 | 7728 | 1 | 1 | 7728 | 8563.2 | 8563.2
Develop Business Opportunity | 2021-04-08 15:31 | 8.06 | 2021-04-20 16:00 | 101 | Complete | 9016 | 9016 | 1 | 1 | 9016 | 10316.8 | 10316.8
Customer Preference Study | 2021-04-20 16:00 | 12.13 | 2021-05-07 08:02 | 93 | Complete | 13524 | 13524 | 1 | 1 | 13524 | 15526.4 | 15526.4
Business Evaluation (NPV, etc.) | 2021-05-07 08:02 | 2.38 | 2021-05-11 11:05 | 80 | Complete | 2576 | 2576 | 1 | 1 | 2576 | 3046.4 | 3046.4
PM Period 1 | 2021-03-31 09:00 | 18.06 | 2021-04-26 09:29 | 107 | Complete | 12300 | 12300 | 1 | 1 | 12300 | 17734.92 | 17734.92
Milestone 1 | 2021-05-11 11:05 | 0 | 2021-05-11 11:05 | 78 | Complete | 0 | 0 | 1 | 1 | 0 | 40 | 40
Design and Development Plan | 2021-05-11 11:05 | 3.88 | 2021-05-17 10:07 | 78 | Complete | 2352 | 2352 | 1 | 1 | 2352 | 3585.12 | 3585.12
Design Specs | 2021-05-17 10:07 | 13.75 | 2021-06-04 08:07 | 74 | Complete | 8624 | 8624 | 1 | 1 | 8624 | 12705 | 12705
Develop Prelim Marketing Plan | 2021-05-11 11:05 | 2.81 | 2021-05-14 09:34 | 78 | Complete | 3220 | 3220 | 1 | 1 | 3220 | 3596.8 | 3596.8
Develop Marketing Program | 2021-05-14 09:34 | 8.44 | 2021-05-26 14:05 | 75 | Complete | 9660 | 9660 | 1 | 1 | 9660 | 10803.2 | 10803.2
PM Period 2 | 2021-05-11 11:05 | 10.06 | 2021-05-25 11:34 | 78 | Complete | 6888 | 6888 | 1 | 1 | 6888 | 9878.92 | 9878.92
Milestone 2 | 2021-06-04 08:07 | 0 | 2021-06-04 08:07 | 60 | Complete | 0 | 0 | 1 | 1 | 0 | 360 | 360
Identify Testing Requirements | 2021-06-04 08:07 | 6.25 | 2021-06-14 10:07 | 60 | Complete | 3920 | 3920 | 1 | 1 | 3920 | 5775 | 5775
Risk Analysis | 2021-06-14 10:07 | 7.06 | 2021-06-23 10:36 | 54 | Complete | 3920 | 3920 | 1 | 1 | 3920 | 6523.44 | 6523.44
Train Sales Team | 2021-06-04 08:07 | 24.88 | 2021-07-08 16:10 | 60 | Complete | 11088 | 11088 | 1 | 1 | 11088 | 12440 | 12440
Advertising Campaign | 2021-06-04 08:07 | 31.38 | 2021-07-19 11:10 | 60 | Complete | 21952 | 21952 | 1 | 1 | 21952 | 24476.4 | 24476.4
PM Period 3 | 2021-06-04 08:07 | 10.13 | 2021-06-18 09:10 | 60 | Complete | 6888 | 6888 | 1 | 1 | 6888 | 9947.66 | 9947.66
Milestone 3 | 2021-07-19 11:10 | 0 | 2021-07-19 11:10 | 29 | Complete | 0 | 0 | 1 | 1 | 0 | 60 | 60
Design Labelling | 2021-07-14 08:07 | 3.25 | 2021-07-19 10:07 | 32 | Complete | 1960 | 1960 | 1 | 1 | 1960 | 3003 | 3003
Approve Design | 2021-07-19 10:07 | 2.63 | 2021-07-21 16:10 | 29 | Complete | 1568 | 1568 | 1 | 1 | 1568 | 2430.12 | 2430.12
Initial Engineering Specs | 2021-07-21 16:10 | 2.88 | 2021-07-26 15:12 | 27 | Complete | 2460 | 2460 | 1 | 1 | 2460 | 2828.16 | 2828.16
PM Period 4 | 2021-07-19 11:10 | 14.63 | 2021-08-09 08:12 | 29 | Complete | 10192 | 10192 | 1 | 1 | 10192 | 11411.4 | 11411.4
Milestone 4 | 2021-08-09 08:12 | 0 | 2021-08-09 08:12 | 14 | Complete | 0 | 0 | 1 | 1 | 0 | 663.75 | 663.75
Design Verification Activities | 2021-08-09 08:12 | 4.19 | 2021-08-13 09:43 | 14 | Complete | 3444 | 3444 | 1 | 1 | 3444 | 4114.58 | 4114.58
Verification Design Review | 2021-08-13 09:43 | 2.31 | 2021-08-17 13:12 | 10 | Complete | 1968 | 1968 | 1 | 1 | 1968 | 2268.42 | 2268.42
Release Pre-Production Specs | 2021-08-17 13:12 | 6 | 2021-08-25 13:12 | 8 | Complete | 4920 | 4920 | 1 | 1 | 4920 | 5892 | 5892
PM Period 5 | 2021-08-09 08:12 | 17 | 2021-09-01 08:12 | 14 | Busy | 11760 | 11760 | 1 | 0.82206 | 9667.4118 | 13260 | 10900.5
Milestone 5 | 2021-09-01 08:12 | 0 | 2021-09-01 08:12 | -5 | Busy | 0 | 0 | 0 | 0 | 0 | 4851 | 0
Identify Vendors | 2021-09-01 08:12 | 4.5 | 2021-09-07 13:12 | -5 | Busy | 2800 | 2800 | 1 | 0 | 0 | 3528 | 0
Develop and Issue RFQ | 2021-09-07 13:12 | 3.88 | 2021-09-13 09:02 | -9 | Busy | 2400 | 1999.92 | 0.8333 | 0 | 0 | 3041.92 | 0 | 2021-08-20 | 5 | 6
Build Functional Model | 2021-09-01 08:12 | 11.25 | 2021-09-16 10:12 | -5 | Busy | 8856 | 8856 | 1 | 0 | 0 | 11047.5 | 0
Evaluate Design Specs | 2021-09-01 08:12 | 14.88 | 2021-09-21 16:14 | -5 | Busy | 6000 | 6000 | 1 | 0 | 0 | 8928 | 0
PM Period 6 | 2021-09-01 08:12 | 10.25 | 2021-09-15 10:12 | -5 | Busy | 7056 | 7056 | 1 | 0 | 0 | 7995 | 0
Milestone 6 | 2021-09-15 10:12 | 0 | 2021-09-15 10:12 | -15 | Busy | 0 | 0 | 0 | 0 | 0 | 4638 | 0
Totals | [6 empty] | 188639.92 |  |  | 159835.4118 |  | 198891.19
CPI | 0.8036
SPI | 0.8473
ETC | 169532.8375
EAC | 368424.0275
Formulas:
Network Days to Analysis Date = NETWORKDAYS([Real Start Date],D3)
Network Days to Analysis Date = NETWORKDAYS([Planned Start Date],D3)

## Period 6
Period 6 |  | Analysis Date at 17:00
2021-09-15 17:00
Task | Real Start Date | Real Duration | Real End Date | Network Days to Analysis Date | Complete/Busy | Full Budget | Planned Value | %Sched Completion | %Actual Completion | Earned Value | Actual Cost | Actual Cost at Analysis Date | Planned Start Date | Network Days to Analysis Date | Planned Duration
Evaluate Market | 2021-03-31 09:00 | 6.69 | 2021-04-08 15:31 | 121 | Complete | 7728 | 7728 | 1 | 1 | 7728 | 8563.2 | 8563.2
Develop Business Opportunity | 2021-04-08 15:31 | 8.06 | 2021-04-20 16:00 | 115 | Complete | 9016 | 9016 | 1 | 1 | 9016 | 10316.8 | 10316.8
Customer Preference Study | 2021-04-20 16:00 | 12.13 | 2021-05-07 08:02 | 107 | Complete | 13524 | 13524 | 1 | 1 | 13524 | 15526.4 | 15526.4
Business Evaluation (NPV, etc.) | 2021-05-07 08:02 | 2.38 | 2021-05-11 11:05 | 94 | Complete | 2576 | 2576 | 1 | 1 | 2576 | 3046.4 | 3046.4
PM Period 1 | 2021-03-31 09:00 | 18.06 | 2021-04-26 09:29 | 121 | Complete | 12300 | 12300 | 1 | 1 | 12300 | 17734.92 | 17734.92
Milestone 1 | 2021-05-11 11:05 | 0 | 2021-05-11 11:05 | 92 | Complete | 0 | 0 | 1 | 1 | 0 | 40 | 40
Design and Development Plan | 2021-05-11 11:05 | 3.88 | 2021-05-17 10:07 | 92 | Complete | 2352 | 2352 | 1 | 1 | 2352 | 3585.12 | 3585.12
Design Specs | 2021-05-17 10:07 | 13.75 | 2021-06-04 08:07 | 88 | Complete | 8624 | 8624 | 1 | 1 | 8624 | 12705 | 12705
Develop Prelim Marketing Plan | 2021-05-11 11:05 | 2.81 | 2021-05-14 09:34 | 92 | Complete | 3220 | 3220 | 1 | 1 | 3220 | 3596.8 | 3596.8
Develop Marketing Program | 2021-05-14 09:34 | 8.44 | 2021-05-26 14:05 | 89 | Complete | 9660 | 9660 | 1 | 1 | 9660 | 10803.2 | 10803.2
PM Period 2 | 2021-05-11 11:05 | 10.06 | 2021-05-25 11:34 | 92 | Complete | 6888 | 6888 | 1 | 1 | 6888 | 9878.92 | 9878.92
Milestone 2 | 2021-06-04 08:07 | 0 | 2021-06-04 08:07 | 74 | Complete | 0 | 0 | 1 | 1 | 0 | 360 | 360
Identify Testing Requirements | 2021-06-04 08:07 | 6.25 | 2021-06-14 10:07 | 74 | Complete | 3920 | 3920 | 1 | 1 | 3920 | 5775 | 5775
Risk Analysis | 2021-06-14 10:07 | 7.06 | 2021-06-23 10:36 | 68 | Complete | 3920 | 3920 | 1 | 1 | 3920 | 6523.44 | 6523.44
Train Sales Team | 2021-06-04 08:07 | 24.88 | 2021-07-08 16:10 | 74 | Complete | 11088 | 11088 | 1 | 1 | 11088 | 12440 | 12440
Advertising Campaign | 2021-06-04 08:07 | 31.38 | 2021-07-19 11:10 | 74 | Complete | 21952 | 21952 | 1 | 1 | 21952 | 24476.4 | 24476.4
PM Period 3 | 2021-06-04 08:07 | 10.13 | 2021-06-18 09:10 | 74 | Complete | 6888 | 6888 | 1 | 1 | 6888 | 9947.66 | 9947.66
Milestone 3 | 2021-07-19 11:10 | 0 | 2021-07-19 11:10 | 43 | Complete | 0 | 0 | 1 | 1 | 0 | 60 | 60
Design Labelling | 2021-07-14 08:07 | 3.25 | 2021-07-19 10:07 | 46 | Complete | 1960 | 1960 | 1 | 1 | 1960 | 3003 | 3003
Approve Design | 2021-07-19 10:07 | 2.63 | 2021-07-21 16:10 | 43 | Complete | 1568 | 1568 | 1 | 1 | 1568 | 2430.12 | 2430.12
Initial Engineering Specs | 2021-07-21 16:10 | 2.88 | 2021-07-26 15:12 | 41 | Complete | 2460 | 2460 | 1 | 1 | 2460 | 2828.16 | 2828.16
PM Period 4 | 2021-07-19 11:10 | 14.63 | 2021-08-09 08:12 | 43 | Complete | 10192 | 10192 | 1 | 1 | 10192 | 11411.4 | 11411.4
Milestone 4 | 2021-08-09 08:12 | 0 | 2021-08-09 08:12 | 28 | Complete | 0 | 0 | 1 | 1 | 0 | 663.75 | 663.75
Design Verification Activities | 2021-08-09 08:12 | 4.19 | 2021-08-13 09:43 | 28 | Complete | 3444 | 3444 | 1 | 1 | 3444 | 4114.58 | 4114.58
Verification Design Review | 2021-08-13 09:43 | 2.31 | 2021-08-17 13:12 | 24 | Complete | 1968 | 1968 | 1 | 1 | 1968 | 2268.42 | 2268.42
Release Pre-Production Specs | 2021-08-17 13:12 | 6 | 2021-08-25 13:12 | 22 | Complete | 4920 | 4920 | 1 | 1 | 4920 | 5892 | 5892
PM Period 5 | 2021-08-09 08:12 | 17 | 2021-09-01 08:12 | 28 | Complete | 11760 | 11760 | 1 | 1 | 11760 | 13260 | 13260
Milestone 5 | 2021-09-01 08:12 | 0 | 2021-09-01 08:12 | 11 | Complete | 0 | 0 | 1 | 1 | 0 | 4851 | 4851
Identify Vendors | 2021-09-01 08:12 | 4.5 | 2021-09-07 13:12 | 11 | Complete | 2800 | 2800 | 1 | 1 | 2800 | 3528 | 3528
Develop and Issue RFQ | 2021-09-07 13:12 | 3.88 | 2021-09-13 09:02 | 7 | Complete | 2400 | 2400 | 1 | 1 | 2400 | 3041.92 | 3041.92
Build Functional Model | 2021-09-01 08:12 | 11.25 | 2021-09-16 10:12 | 11 | Busy | 8856 | 8856 | 1 | 0.97556 | 8639.52 | 11047.5 | 10777.45
Evaluate Design Specs | 2021-09-01 08:12 | 14.88 | 2021-09-21 16:14 | 11 | Busy | 6000 | 6000 | 1 | 0.73757 | 4425.4032 | 8928 | 6585
PM Period 6 | 2021-09-01 08:12 | 10.25 | 2021-09-15 10:12 | 11 | Complete | 7056 | 7056 | 1 | 1 | 7056 | 7995 | 7995
Milestone 6 | 2021-09-21 16:14 | 0 | 2021-09-21 16:14 | -5 | Busy | 0 | 0 | 1 | 0 | 0 | 4638 | 0
Issue Sample | 2021-09-21 16:14 | 7.5 | 2021-10-01 11:14 | -5 | Busy | 3000 | 3000 | 1 | 0 | 0 | 4500 | 0
Perform Supplier Process Capability | 2021-10-01 11:14 | 17.13 | 2021-10-26 13:17 | -13 | Busy | 6608 | 6608 | 1 | 0 | 0 | 9250 | 0
Develop Testing Protocol for Prototype | 2021-09-21 16:14 | 10.25 | 2021-10-06 09:14 | -5 | Busy | 3520 | 3520 | 1 | 0 | 0 | 4530.5 | 0
PM Period 7 | 2021-09-21 16:14 | 12.5 | 2021-10-08 11:14 | -5 | Busy | 8624 | 8624 | 1 | 0 | 0 | 9750 | 0
Milestone 7 | 2021-09-21 16:14 | 0 | 2021-09-21 16:14 | -5 | Busy | 0 | 0 | 1 | 0 | 0 | 4449 | 0
Approve Sample Parts | 2021-10-26 13:17 | 10.13 | 2021-11-09 14:19 | -30 | Busy | 4352 | 544 | 0.125 | 0 | 0 | 6078 | 0 | 2021-09-15 | 1 | 8
Design Validation Activities | 2021-11-12 10:17 | 3.06 | 2021-11-16 16:02 | -43 | Busy | 2200 | 440 | 0.2 | 0 | 0 | 5635.52 | 0 | 2021-09-15 | 1 | 5
Test Prototype | 2021-10-26 13:17 | 12.75 | 2021-11-12 10:17 | -30 | Busy | 6000 | 600 | 0.1 | 0 | 0 | 5635.5 | 0 | 2021-09-15 | 1 | 10
Process Engineering Plan | 2021-10-26 13:17 | 17.63 | 2021-11-19 09:19 | -30 | Busy | 6000 | 400.2 | 0.0667 | 0 | 0 | 7811.1 | 0 | 2021-09-15 | 1 | 15
Show Functional Model at Trade Show | 2021-11-01 08:00 | 3.25 | 2021-11-04 10:00 | -34 | Busy | 2352 | 0 | 0 | 0 | 0 | 2535 | 0
PM Period 8 | 2021-10-26 13:17 | 3.38 | 2021-10-29 16:19 | -30 | Busy | 2352 | 783.9216 | 0.3333 | 0 | 0 | 2636.4 | 0 | 2021-09-15 | 1 | 3
Milestone 8 | 2021-11-19 09:19 | 0 | 2021-11-19 09:19 | -48 | Busy | 0 | 0 | 0 | 0 | 0 | 40 | 0
Totals | [6 empty] | 213560.1216 |  |  | 187248.9232 |  | 238029.06
CPI | 0.7867
SPI | 0.8768
ETC | 138328.5582
EAC | 376357.6182
Formulas:
Network Days to Analysis Date = NETWORKDAYS([Real Start Date],D3)
Network Days to Analysis Date = NETWORKDAYS([Planned Start Date],D3)

## Period 7
Period 7 |  | Analysis Date at 17:00
2021-10-20 17:00
Task | Real Start Date | Real Duration | Real End Date | Network Days to Analysis Date | Complete/Busy | Full Budget | Planned Value | %Sched Completion | %Actual Completion | Earned Value | Actual Cost | Actual Cost at Analysis Date | Planned Start Date | Network Days to Analysis Date | Planned Duration
Evaluate Market | 2021-03-31 09:00 | 6.69 | 2021-04-08 15:31 | 146 | Complete | 7728 | 7728 | 1 | 1 | 7728 | 8563.2 | 8563.2
Develop Business Opportunity | 2021-04-08 15:31 | 8.06 | 2021-04-20 16:00 | 140 | Complete | 9016 | 9016 | 1 | 1 | 9016 | 10316.8 | 10316.8
Customer Preference Study | 2021-04-20 16:00 | 12.13 | 2021-05-07 08:02 | 132 | Complete | 13524 | 13524 | 1 | 1 | 13524 | 15526.4 | 15526.4
Business Evaluation (NPV, etc.) | 2021-05-07 08:02 | 2.38 | 2021-05-11 11:05 | 119 | Complete | 2576 | 2576 | 1 | 1 | 2576 | 3046.4 | 3046.4
PM Period 1 | 2021-03-31 09:00 | 18.06 | 2021-04-26 09:29 | 146 | Complete | 12300 | 12300 | 1 | 1 | 12300 | 17734.92 | 17734.92
Milestone 1 | 2021-05-11 11:05 | 0 | 2021-05-11 11:05 | 117 | Complete | 0 | 0 | 1 | 1 | 0 | 40 | 40
Design and Development Plan | 2021-05-11 11:05 | 3.88 | 2021-05-17 10:07 | 117 | Complete | 2352 | 2352 | 1 | 1 | 2352 | 3585.12 | 3585.12
Design Specs | 2021-05-17 10:07 | 13.75 | 2021-06-04 08:07 | 113 | Complete | 8624 | 8624 | 1 | 1 | 8624 | 12705 | 12705
Develop Prelim Marketing Plan | 2021-05-11 11:05 | 2.81 | 2021-05-14 09:34 | 117 | Complete | 3220 | 3220 | 1 | 1 | 3220 | 3596.8 | 3596.8
Develop Marketing Program | 2021-05-14 09:34 | 8.44 | 2021-05-26 14:05 | 114 | Complete | 9660 | 9660 | 1 | 1 | 9660 | 10803.2 | 10803.2
PM Period 2 | 2021-05-11 11:05 | 10.06 | 2021-05-25 11:34 | 117 | Complete | 6888 | 6888 | 1 | 1 | 6888 | 9878.92 | 9878.92
Milestone 2 | 2021-06-04 08:07 | 0 | 2021-06-04 08:07 | 99 | Complete | 0 | 0 | 1 | 1 | 0 | 360 | 360
Identify Testing Requirements | 2021-06-04 08:07 | 6.25 | 2021-06-14 10:07 | 99 | Complete | 3920 | 3920 | 1 | 1 | 3920 | 5775 | 5775
Risk Analysis | 2021-06-14 10:07 | 7.06 | 2021-06-23 10:36 | 93 | Complete | 3920 | 3920 | 1 | 1 | 3920 | 6523.44 | 6523.44
Train Sales Team | 2021-06-04 08:07 | 24.88 | 2021-07-08 16:10 | 99 | Complete | 11088 | 11088 | 1 | 1 | 11088 | 12440 | 12440
Advertising Campaign | 2021-06-04 08:07 | 31.38 | 2021-07-19 11:10 | 99 | Complete | 21952 | 21952 | 1 | 1 | 21952 | 24476.4 | 24476.4
PM Period 3 | 2021-06-04 08:07 | 10.13 | 2021-06-18 09:10 | 99 | Complete | 6888 | 6888 | 1 | 1 | 6888 | 9947.66 | 9947.66
Milestone 3 | 2021-07-19 11:10 | 0 | 2021-07-19 11:10 | 68 | Complete | 0 | 0 | 1 | 1 | 0 | 60 | 60
Design Labelling | 2021-07-14 08:07 | 3.25 | 2021-07-19 10:07 | 71 | Complete | 1960 | 1960 | 1 | 1 | 1960 | 3003 | 3003
Approve Design | 2021-07-19 10:07 | 2.63 | 2021-07-21 16:10 | 68 | Complete | 1568 | 1568 | 1 | 1 | 1568 | 2430.12 | 2430.12
Initial Engineering Specs | 2021-07-21 16:10 | 2.88 | 2021-07-26 15:12 | 66 | Complete | 2460 | 2460 | 1 | 1 | 2460 | 2828.16 | 2828.16
PM Period 4 | 2021-07-19 11:10 | 14.63 | 2021-08-09 08:12 | 68 | Complete | 10192 | 10192 | 1 | 1 | 10192 | 11411.4 | 11411.4
Milestone 4 | 2021-08-09 08:12 | 0 | 2021-08-09 08:12 | 53 | Complete | 0 | 0 | 1 | 1 | 0 | 663.75 | 663.75
Design Verification Activities | 2021-08-09 08:12 | 4.19 | 2021-08-13 09:43 | 53 | Complete | 3444 | 3444 | 1 | 1 | 3444 | 4114.58 | 4114.58
Verification Design Review | 2021-08-13 09:43 | 2.31 | 2021-08-17 13:12 | 49 | Complete | 1968 | 1968 | 1 | 1 | 1968 | 2268.42 | 2268.42
Release Pre-Production Specs | 2021-08-17 13:12 | 6 | 2021-08-25 13:12 | 47 | Complete | 4920 | 4920 | 1 | 1 | 4920 | 5892 | 5892
PM Period 5 | 2021-08-09 08:12 | 17 | 2021-09-01 08:12 | 53 | Complete | 11760 | 11760 | 1 | 1 | 11760 | 13260 | 13260
Milestone 5 | 2021-09-01 08:12 | 0 | 2021-09-01 08:12 | 36 | Complete | 0 | 0 | 1 | 1 | 0 | 4851 | 4851
Identify Vendors | 2021-09-01 08:12 | 4.5 | 2021-09-07 13:12 | 36 | Complete | 2800 | 2800 | 1 | 1 | 2800 | 3528 | 3528
Develop and Issue RFQ | 2021-09-07 13:12 | 3.88 | 2021-09-13 09:02 | 32 | Complete | 2400 | 2400 | 1 | 1 | 2400 | 3041.92 | 3041.92
Build Functional Model | 2021-09-01 08:12 | 11.25 | 2021-09-16 10:12 | 36 | Complete | 8856 | 8856 | 1 | 1 | 8856 | 11047.5 | 11047.5
Evaluate Design Specs | 2021-09-01 08:12 | 14.88 | 2021-09-21 16:14 | 36 | Complete | 6000 | 6000 | 1 | 1 | 6000 | 8928 | 8928
PM Period 6 | 2021-09-01 08:12 | 10.25 | 2021-09-15 10:12 | 36 | Complete | 7056 | 7056 | 1 | 1 | 7056 | 7995 | 7995
Milestone 6 | 2021-09-21 16:14 | 0 | 2021-09-21 16:14 | 22 | Complete | 0 | 0 | 1 | 1 | 0 | 4638 | 4638
Issue Sample | 2021-09-21 16:14 | 7.5 | 2021-10-01 11:14 | 22 | Complete | 3000 | 3000 | 1 | 1 | 3000 | 4500 | 4500
Perform Supplier Process Capability | 2021-10-01 11:14 | 17.13 | 2021-10-26 13:17 | 14 | Busy | 6608 | 6608 | 1 | 0.79369 | 5244.6741 | 9250 | 7341.5913
Develop Testing Protocol for Prototype | 2021-09-21 16:14 | 10.25 | 2021-10-06 09:14 | 22 | Complete | 3520 | 3520 | 1 | 1 | 3520 | 4530.5 | 4530.5
PM Period 7 | 2021-09-21 16:14 | 12.5 | 2021-10-08 11:14 | 22 | Complete | 8624 | 8624 | 1 | 1 | 8624 | 9750 | 9750
Milestone 7 | 2021-09-21 16:14 | 0 | 2021-09-21 16:14 | 22 | Complete | 0 | 0 | 1 | 0 | 0 | 4449 | 0
Approve Sample Parts | 2021-10-26 13:17 | 10.13 | 2021-11-09 14:19 | -5 | Busy | 4352 | 4352 | 1 | 0 | 0 | 6078 | 0
Design Validation Activities | 2021-11-12 10:17 | 3.06 | 2021-11-16 16:02 | -18 | Busy | 2200 | 2200 | 1 | 0 | 0 | 3188.5 | 0
Test Prototype | 2021-10-26 13:17 | 12.75 | 2021-11-12 10:17 | -5 | Busy | 6000 | 6000 | 1 | 0 | 0 | 5635.52 | 0
Process Engineering Plan | 2021-10-26 13:17 | 17.63 | 2021-11-19 09:19 | -5 | Busy | 6000 | 6000 | 1 | 0 | 0 | 7811.1 | 0
Show Functional Model at Trade Show | 2021-11-01 08:00 | 3.25 | 2021-11-04 10:00 | -9 | Busy | 2352 | 2352 | 1 | 0 | 0 | 2535 | 0
PM Period 8 | 2021-10-26 13:17 | 3.38 | 2021-10-29 16:19 | -5 | Busy | 2352 | 2352 | 1 | 0 | 0 | 2636.4 | 0
Milestone 8 | 2021-11-19 09:19 | 0 | 2021-11-19 09:19 | -23 | Busy | 0 | 0 | 1 | 0 | 0 | 40 | 0
Validation Design Review | 2021-11-19 09:19 | 4.75 | 2021-11-25 16:19 | -23 | Busy | 1968 | 1968 | 1 | 0 | 0 | 2565 | 0
Approve Model Design | 2021-11-25 16:19 | 5.13 | 2021-12-03 08:22 | -27 | Busy | 1968 | 1968 | 1 | 0 | 0 | 2267.46 | 0
Evaluate Test Results | 2021-11-19 09:19 | 7.38 | 2021-11-30 13:22 | -23 | Busy | 3600 | 3600 | 1 | 0 | 0 | 4428 | 0
PM Period 9 | 2021-11-19 09:19 | 4.63 | 2021-11-25 15:22 | -23 | Busy | 3136 | 3136 | 1 | 0 | 0 | 3611.4 | 0
Milestone 9 | 2021-12-03 08:22 | 0 | 2021-12-03 08:22 | -33 | Busy | 0 | 0 | 1 | 0 | 0 | 240 | 0
Qualify Supplier | 2021-12-03 08:22 | 12.5 | 2021-12-21 13:22 | -33 | Busy | 6000 | 3000 | 0.5 | 0 | 0 | 7500 | 0 | 2021-10-14 | 5 | 10
Design Transfer Activities | 2021-12-03 08:22 | 8.25 | 2021-12-15 10:22 | -33 | Busy | 4200 | 4200 | 1 | 0 | 0 | 4455 | 0
Product Release Meetings | 2021-12-15 10:22 | 3.38 | 2021-12-20 14:24 | -41 | Busy | 3000 | 0 | 0 | 0 | 0 | 2636 | 0
Develop Production Plan | 2021-12-03 08:22 | 8.25 | 2021-12-15 10:22 | -33 | Busy | 2400 | 1999.92 | 0.8333 | 0 | 0 | 3646.5 | 0 | 2021-10-14 | 5 | 6
PM Period 10 | 2021-12-03 08:22 | 5.63 | 2021-12-10 14:24 | -33 | Busy | 3920 | 3920 | 1 | 0 | 0 | 4391.4 | 0 | 2021-10-14 | 5 | 5
Milestone 10 | 2021-12-21 13:22 | 0 | 2021-12-21 13:22 | -45 | Busy | 0 | 0 | 1 | 0 | 0 | 40 | 0
Totals | [6 empty] | 257839.92 |  |  | 209428.6741 |  | 271402.2013
CPI | 0.7717
SPI | 0.8122
ETC | 112275.918
EAC | 383678.1193
Formulas:
Network Days to Analysis Date = NETWORKDAYS([Real Start Date],D3)
Network Days to Analysis Date = NETWORKDAYS([Planned Start Date],D3)

## Period 8
Period 8 |  | Analysis Date at 17:00
2021-11-15 17:00
Task | Real Start Date | Real Duration | Real End Date | Network Days to Analysis Date | Complete/Busy | Full Budget | Planned Value | %Sched Completion | %Actual Completion | Earned Value | Actual Cost | Actual Cost at Analysis Date | Planned Start Date | Network Days to Analysis Date | Planned Duration
Evaluate Market | 2021-03-31 09:00 | 6.69 | 2021-04-08 15:31 | 164 | Complete | 7728 | 7728 | 1 | 1 | 7728 | 8563.2 | 8563.2
Develop Business Opportunity | 2021-04-08 15:31 | 8.06 | 2021-04-20 16:00 | 158 | Complete | 9016 | 9016 | 1 | 1 | 9016 | 10316.8 | 10316.8
Customer Preference Study | 2021-04-20 16:00 | 12.13 | 2021-05-07 08:02 | 150 | Complete | 13524 | 13524 | 1 | 1 | 13524 | 15526.4 | 15526.4
Business Evaluation (NPV, etc.) | 2021-05-07 08:02 | 2.38 | 2021-05-11 11:05 | 137 | Complete | 2576 | 2576 | 1 | 1 | 2576 | 3046.4 | 3046.4
PM Period 1 | 2021-03-31 09:00 | 18.06 | 2021-04-26 09:29 | 164 | Complete | 12300 | 12300 | 1 | 1 | 12300 | 17734.92 | 17734.92
Milestone 1 | 2021-05-11 11:05 | 0 | 2021-05-11 11:05 | 135 | Complete | 0 | 0 | 1 | 1 | 0 | 40 | 40
Design and Development Plan | 2021-05-11 11:05 | 3.88 | 2021-05-17 10:07 | 135 | Complete | 2352 | 2352 | 1 | 1 | 2352 | 3585.12 | 3585.12
Design Specs | 2021-05-17 10:07 | 13.75 | 2021-06-04 08:07 | 131 | Complete | 8624 | 8624 | 1 | 1 | 8624 | 12705 | 12705
Develop Prelim Marketing Plan | 2021-05-11 11:05 | 2.81 | 2021-05-14 09:34 | 135 | Complete | 3220 | 3220 | 1 | 1 | 3220 | 3596.8 | 3596.8
Develop Marketing Program | 2021-05-14 09:34 | 8.44 | 2021-05-26 14:05 | 132 | Complete | 9660 | 9660 | 1 | 1 | 9660 | 10803.2 | 10803.2
PM Period 2 | 2021-05-11 11:05 | 10.06 | 2021-05-25 11:34 | 135 | Complete | 6888 | 6888 | 1 | 1 | 6888 | 9878.92 | 9878.92
Milestone 2 | 2021-06-04 08:07 | 0 | 2021-06-04 08:07 | 117 | Complete | 0 | 0 | 1 | 1 | 0 | 360 | 360
Identify Testing Requirements | 2021-06-04 08:07 | 6.25 | 2021-06-14 10:07 | 117 | Complete | 3920 | 3920 | 1 | 1 | 3920 | 5775 | 5775
Risk Analysis | 2021-06-14 10:07 | 7.06 | 2021-06-23 10:36 | 111 | Complete | 3920 | 3920 | 1 | 1 | 3920 | 6523.44 | 6523.44
Train Sales Team | 2021-06-04 08:07 | 24.88 | 2021-07-08 16:10 | 117 | Complete | 11088 | 11088 | 1 | 1 | 11088 | 12440 | 12440
Advertising Campaign | 2021-06-04 08:07 | 31.38 | 2021-07-19 11:10 | 117 | Complete | 21952 | 21952 | 1 | 1 | 21952 | 24476.4 | 24476.4
PM Period 3 | 2021-06-04 08:07 | 10.13 | 2021-06-18 09:10 | 117 | Complete | 6888 | 6888 | 1 | 1 | 6888 | 9947.66 | 9947.66
Milestone 3 | 2021-07-19 11:10 | 0 | 2021-07-19 11:10 | 86 | Complete | 0 | 0 | 1 | 1 | 0 | 60 | 60
Design Labelling | 2021-07-14 08:07 | 3.25 | 2021-07-19 10:07 | 89 | Complete | 1960 | 1960 | 1 | 1 | 1960 | 3003 | 3003
Approve Design | 2021-07-19 10:07 | 2.63 | 2021-07-21 16:10 | 86 | Complete | 1568 | 1568 | 1 | 1 | 1568 | 2430.12 | 2430.12
Initial Engineering Specs | 2021-07-21 16:10 | 2.88 | 2021-07-26 15:12 | 84 | Complete | 2460 | 2460 | 1 | 1 | 2460 | 2828.16 | 2828.16
PM Period 4 | 2021-07-19 11:10 | 14.63 | 2021-08-09 08:12 | 86 | Complete | 10192 | 10192 | 1 | 1 | 10192 | 11411.4 | 11411.4
Milestone 4 | 2021-08-09 08:12 | 0 | 2021-08-09 08:12 | 71 | Complete | 0 | 0 | 1 | 1 | 0 | 663.75 | 663.75
Design Verification Activities | 2021-08-09 08:12 | 4.19 | 2021-08-13 09:43 | 71 | Complete | 3444 | 3444 | 1 | 1 | 3444 | 4114.58 | 4114.58
Verification Design Review | 2021-08-13 09:43 | 2.31 | 2021-08-17 13:12 | 67 | Complete | 1968 | 1968 | 1 | 1 | 1968 | 2268.42 | 2268.42
Release Pre-Production Specs | 2021-08-17 13:12 | 6 | 2021-08-25 13:12 | 65 | Complete | 4920 | 4920 | 1 | 1 | 4920 | 5892 | 5892
PM Period 5 | 2021-08-09 08:12 | 17 | 2021-09-01 08:12 | 71 | Complete | 11760 | 11760 | 1 | 1 | 11760 | 13260 | 13260
Milestone 5 | 2021-09-01 08:12 | 0 | 2021-09-01 08:12 | 54 | Complete | 0 | 0 | 1 | 1 | 0 | 4851 | 4851
Identify Vendors | 2021-09-01 08:12 | 4.5 | 2021-09-07 13:12 | 54 | Complete | 2800 | 2800 | 1 | 1 | 2800 | 3528 | 3528
Develop and Issue RFQ | 2021-09-07 13:12 | 3.88 | 2021-09-13 09:02 | 50 | Complete | 2400 | 2400 | 1 | 1 | 2400 | 3041.92 | 3041.92
Build Functional Model | 2021-09-01 08:12 | 11.25 | 2021-09-16 10:12 | 54 | Complete | 8856 | 8856 | 1 | 1 | 8856 | 11047.5 | 11047.5
Evaluate Design Specs | 2021-09-01 08:12 | 14.88 | 2021-09-21 16:14 | 54 | Complete | 6000 | 6000 | 1 | 1 | 6000 | 8928 | 8928
PM Period 6 | 2021-09-01 08:12 | 10.25 | 2021-09-15 10:12 | 54 | Complete | 7056 | 7056 | 1 | 1 | 7056 | 7995 | 7995
Milestone 6 | 2021-09-21 16:14 | 0 | 2021-09-21 16:14 | 40 | Complete | 0 | 0 | 1 | 1 | 0 | 4638 | 4638
Issue Sample | 2021-09-21 16:14 | 7.5 | 2021-10-01 11:14 | 40 | Complete | 3000 | 3000 | 1 | 1 | 3000 | 4500 | 4500
Perform Supplier Process Capability | 2021-10-01 11:14 | 17.13 | 2021-10-26 13:17 | 32 | Complete | 6608 | 6608 | 1 | 1 | 6608 | 9250 | 9250
Develop Testing Protocol for Prototype | 2021-09-21 16:14 | 10.25 | 2021-10-06 09:14 | 40 | Complete | 3520 | 3520 | 1 | 1 | 3520 | 4530.5 | 4530.5
PM Period 7 | 2021-09-21 16:14 | 12.5 | 2021-10-08 11:14 | 40 | Complete | 8624 | 8624 | 1 | 1 | 8624 | 9750 | 9750
Milestone 7 | 2021-09-21 16:14 | 0 | 2021-09-21 16:14 | 40 | Complete | 0 | 0 | 1 | 1 | 0 | 4449 | 4449
Approve Sample Parts | 2021-10-26 13:17 | 10.13 | 2021-11-09 14:19 | 15 | Complete | 4352 | 4352 | 1 | 1 | 4352 | 6078 | 6078
Design Validation Activities | 2021-11-12 10:17 | 3.06 | 2021-11-16 16:02 | 2 | Busy | 2200 | 2200 | 1 | 0.71426 | 1571.3827 | 3188.5 | 2277.4336
Test Prototype | 2021-10-26 13:17 | 12.75 | 2021-11-12 10:17 | 15 | Complete | 6000 | 6000 | 1 | 1 | 6000 | 5635.52 | 5635.52
Process Engineering Plan | 2021-10-26 13:17 | 17.63 | 2021-11-19 09:19 | 15 | Busy | 6000 | 6000 | 1 | 0.82045 | 4922.717 | 7811.1 | 6408.6391
Show Functional Model at Trade Show | 2021-11-01 08:00 | 3.25 | 2021-11-04 10:00 | 11 | Complete | 2352 | 2352 | 1 | 1 | 2352 | 2535 | 2535
PM Period 8 | 2021-10-26 13:17 | 3.38 | 2021-10-29 16:19 | 15 | Complete | 2352 | 2352 | 1 | 1 | 2352 | 2636.4 | 2636.4
Milestone 8 | 2021-11-19 09:19 | 0 | 2021-11-19 09:19 | -5 | Busy | 0 | 0 | 1 | 0 | 0 | 40 | 0
Validation Design Review | 2021-11-19 09:19 | 4.75 | 2021-11-25 16:19 | -5 | Busy | 1968 | 1968 | 1 | 0 | 0 | 2565 | 0
Approve Model Design | 2021-11-25 16:19 | 5.13 | 2021-12-03 08:22 | -9 | Busy | 1968 | 1968 | 1 | 0 | 0 | 2267.46 | 0
Evaluate Test Results | 2021-11-19 09:19 | 7.38 | 2021-11-30 13:22 | -5 | Busy | 3600 | 3600 | 1 | 0 | 0 | 4428 | 0
PM Period 9 | 2021-11-19 09:19 | 4.63 | 2021-11-25 15:22 | -5 | Busy | 3136 | 3136 | 1 | 0 | 0 | 3611.4 | 0
Milestone 9 | 2021-12-03 08:22 | 0 | 2021-12-03 08:22 | -15 | Busy | 0 | 0 | 1 | 0 | 0 | 240 | 0
Qualify Supplier | 2021-12-03 08:22 | 12.5 | 2021-12-21 13:22 | -15 | Busy | 6000 | 6000 | 1 | 0 | 0 | 7500 | 0
Design Transfer Activities | 2021-12-03 08:22 | 8.25 | 2021-12-15 10:22 | -15 | Busy | 4200 | 4200 | 1 | 0 | 0 | 4455 | 0
Product Release Meetings | 2021-12-15 10:22 | 3.38 | 2021-12-20 14:24 | -23 | Busy | 3000 | 3000 | 1 | 0 | 0 | 2636 | 0
Develop Production Plan | 2021-12-03 08:22 | 8.25 | 2021-12-15 10:22 | -15 | Busy | 2400 | 2400 | 1 | 0 | 0 | 3646.5 | 0
PM Period 10 | 2021-12-03 08:22 | 5.63 | 2021-12-10 14:24 | -15 | Busy | 3920 | 3920 | 1 | 0 | 0 | 4391.4 | 0
Milestone 10 | 2021-12-21 13:22 | 0 | 2021-12-21 13:22 | -27 | Busy | 0 | 0 | 1 | 0 | 0 | 40 | 0
Assess RFQ Responses | 2021-12-21 13:22 | 6.06 | 2021-12-29 13:50 | -27 | Busy | 6000 | 1200 | 0.2 | 0 | 0 | 6908.4 | 0 | 2021-11-12 | 2 | 10
Develop Production Control Plan | 2021-12-21 13:22 | 11.13 | 2022-01-05 14:24 | -27 | Busy | 3400 | 800.02 | 0.2353 | 0 | 0 | 4919.46 | 0 | 2021-11-12 | 2 | 8.5
Approve Production Parts | 2022-01-05 14:24 | 3.31 | 2022-01-10 16:53 | -38 | Busy | 2000 | 0 | 0 | 0 | 0 | 3250.42 | 0
Contracting for Deliveries | 2022-01-10 16:53 | 5.13 | 2022-01-18 08:55 | -41 | Busy | 3200 | 0 | 0 | 0 | 0 | 5037.66 | 0
PM Period 11 | 2021-12-21 13:22 | 14.75 | 2022-01-11 10:22 | -27 | Busy | 5720 | 879.736 | 0.1538 | 0 | 0 | 11505 | 0 | 2021-11-12 | 2 | 13
Milestone 11 | 2022-01-18 08:55 | 0 | 2022-01-18 08:55 | -47 | Busy | 0 | 0 | 0 | 0 | 0 | 40 | 0
Totals | [6 empty] | 267119.756 |  |  | 232342.0997 |  | 303330.6026
CPI | 0.766
SPI | 0.8698
ETC | 83198.3033
EAC | 386528.9059
Formulas:
Network Days to Analysis Date = NETWORKDAYS([Real Start Date],D3)
Network Days to Analysis Date = NETWORKDAYS([Planned Start Date],D3)

## Period 9
Period 9 |  | Analysis Date at 17:00
2021-11-29 17:00
Task | Real Start Date | Real Duration | Real End Date | Network Days to Analysis Date | Complete/Busy | Full Budget | Planned Value | %Sched Completion | %Actual Completion | Earned Value | Actual Cost | Actual Cost at Analysis Date | Planned Start Date | Network Days to Analysis Date | Planned Duration
Evaluate Market | 2021-03-31 09:00 | 6.69 | 2021-04-08 15:31 | 174 | Complete | 7728 | 7728 | 1 | 1 | 7728 | 8563.2 | 8563.2
Develop Business Opportunity | 2021-04-08 15:31 | 8.06 | 2021-04-20 16:00 | 168 | Complete | 9016 | 9016 | 1 | 1 | 9016 | 10316.8 | 10316.8
Customer Preference Study | 2021-04-20 16:00 | 12.13 | 2021-05-07 08:02 | 160 | Complete | 13524 | 13524 | 1 | 1 | 13524 | 15526.4 | 15526.4
Business Evaluation (NPV, etc.) | 2021-05-07 08:02 | 2.38 | 2021-05-11 11:05 | 147 | Complete | 2576 | 2576 | 1 | 1 | 2576 | 3046.4 | 3046.4
PM Period 1 | 2021-03-31 09:00 | 18.06 | 2021-04-26 09:29 | 174 | Complete | 12300 | 12300 | 1 | 1 | 12300 | 17734.92 | 17734.92
Milestone 1 | 2021-05-11 11:05 | 0 | 2021-05-11 11:05 | 145 | Complete | 0 | 0 | 1 | 1 | 0 | 40 | 40
Design and Development Plan | 2021-05-11 11:05 | 3.88 | 2021-05-17 10:07 | 145 | Complete | 2352 | 2352 | 1 | 1 | 2352 | 3585.12 | 3585.12
Design Specs | 2021-05-17 10:07 | 13.75 | 2021-06-04 08:07 | 141 | Complete | 8624 | 8624 | 1 | 1 | 8624 | 12705 | 12705
Develop Prelim Marketing Plan | 2021-05-11 11:05 | 2.81 | 2021-05-14 09:34 | 145 | Complete | 3220 | 3220 | 1 | 1 | 3220 | 3596.8 | 3596.8
Develop Marketing Program | 2021-05-14 09:34 | 8.44 | 2021-05-26 14:05 | 142 | Complete | 9660 | 9660 | 1 | 1 | 9660 | 10803.2 | 10803.2
PM Period 2 | 2021-05-11 11:05 | 10.06 | 2021-05-25 11:34 | 145 | Complete | 6888 | 6888 | 1 | 1 | 6888 | 9878.92 | 9878.92
Milestone 2 | 2021-06-04 08:07 | 0 | 2021-06-04 08:07 | 127 | Complete | 0 | 0 | 1 | 1 | 0 | 360 | 360
Identify Testing Requirements | 2021-06-04 08:07 | 6.25 | 2021-06-14 10:07 | 127 | Complete | 3920 | 3920 | 1 | 1 | 3920 | 5775 | 5775
Risk Analysis | 2021-06-14 10:07 | 7.06 | 2021-06-23 10:36 | 121 | Complete | 3920 | 3920 | 1 | 1 | 3920 | 6523.44 | 6523.44
Train Sales Team | 2021-06-04 08:07 | 24.88 | 2021-07-08 16:10 | 127 | Complete | 11088 | 11088 | 1 | 1 | 11088 | 12440 | 12440
Advertising Campaign | 2021-06-04 08:07 | 31.38 | 2021-07-19 11:10 | 127 | Complete | 21952 | 21952 | 1 | 1 | 21952 | 24476.4 | 24476.4
PM Period 3 | 2021-06-04 08:07 | 10.13 | 2021-06-18 09:10 | 127 | Complete | 6888 | 6888 | 1 | 1 | 6888 | 9947.66 | 9947.66
Milestone 3 | 2021-07-19 11:10 | 0 | 2021-07-19 11:10 | 96 | Complete | 0 | 0 | 1 | 1 | 0 | 60 | 60
Design Labelling | 2021-07-14 08:07 | 3.25 | 2021-07-19 10:07 | 99 | Complete | 1960 | 1960 | 1 | 1 | 1960 | 3003 | 3003
Approve Design | 2021-07-19 10:07 | 2.63 | 2021-07-21 16:10 | 96 | Complete | 1568 | 1568 | 1 | 1 | 1568 | 2430.12 | 2430.12
Initial Engineering Specs | 2021-07-21 16:10 | 2.88 | 2021-07-26 15:12 | 94 | Complete | 2460 | 2460 | 1 | 1 | 2460 | 2828.16 | 2828.16
PM Period 4 | 2021-07-19 11:10 | 14.63 | 2021-08-09 08:12 | 96 | Complete | 10192 | 10192 | 1 | 1 | 10192 | 11411.4 | 11411.4
Milestone 4 | 2021-08-09 08:12 | 0 | 2021-08-09 08:12 | 81 | Complete | 0 | 0 | 1 | 1 | 0 | 663.75 | 663.75
Design Verification Activities | 2021-08-09 08:12 | 4.19 | 2021-08-13 09:43 | 81 | Complete | 3444 | 3444 | 1 | 1 | 3444 | 4114.58 | 4114.58
Verification Design Review | 2021-08-13 09:43 | 2.31 | 2021-08-17 13:12 | 77 | Complete | 1968 | 1968 | 1 | 1 | 1968 | 2268.42 | 2268.42
Release Pre-Production Specs | 2021-08-17 13:12 | 6 | 2021-08-25 13:12 | 75 | Complete | 4920 | 4920 | 1 | 1 | 4920 | 5892 | 5892
PM Period 5 | 2021-08-09 08:12 | 17 | 2021-09-01 08:12 | 81 | Complete | 11760 | 11760 | 1 | 1 | 11760 | 13260 | 13260
Milestone 5 | 2021-09-01 08:12 | 0 | 2021-09-01 08:12 | 64 | Complete | 0 | 0 | 1 | 1 | 0 | 4851 | 4851
Identify Vendors | 2021-09-01 08:12 | 4.5 | 2021-09-07 13:12 | 64 | Complete | 2800 | 2800 | 1 | 1 | 2800 | 3528 | 3528
Develop and Issue RFQ | 2021-09-07 13:12 | 3.88 | 2021-09-13 09:02 | 60 | Complete | 2400 | 2400 | 1 | 1 | 2400 | 3041.92 | 3041.92
Build Functional Model | 2021-09-01 08:12 | 11.25 | 2021-09-16 10:12 | 64 | Complete | 8856 | 8856 | 1 | 1 | 8856 | 11047.5 | 11047.5
Evaluate Design Specs | 2021-09-01 08:12 | 14.88 | 2021-09-21 16:14 | 64 | Complete | 6000 | 6000 | 1 | 1 | 6000 | 8928 | 8928
PM Period 6 | 2021-09-01 08:12 | 10.25 | 2021-09-15 10:12 | 64 | Complete | 7056 | 7056 | 1 | 1 | 7056 | 7995 | 7995
Milestone 6 | 2021-09-21 16:14 | 0 | 2021-09-21 16:14 | 50 | Complete | 0 | 0 | 1 | 1 | 0 | 4638 | 4638
Issue Sample | 2021-09-21 16:14 | 7.5 | 2021-10-01 11:14 | 50 | Complete | 3000 | 3000 | 1 | 1 | 3000 | 4500 | 4500
Perform Supplier Process Capability | 2021-10-01 11:14 | 17.13 | 2021-10-26 13:17 | 42 | Complete | 6608 | 6608 | 1 | 1 | 6608 | 9250 | 9250
Develop Testing Protocol for Prototype | 2021-09-21 16:14 | 10.25 | 2021-10-06 09:14 | 50 | Complete | 3520 | 3520 | 1 | 1 | 3520 | 4530.5 | 4530.5
PM Period 7 | 2021-09-21 16:14 | 12.5 | 2021-10-08 11:14 | 50 | Complete | 8624 | 8624 | 1 | 1 | 8624 | 9750 | 9750
Milestone 7 | 2021-09-21 16:14 | 0 | 2021-09-21 16:14 | 50 | Complete | 0 | 0 | 1 | 1 | 0 | 4449 | 4449
Approve Sample Parts | 2021-10-26 13:17 | 10.13 | 2021-11-09 14:19 | 25 | Complete | 4352 | 4352 | 1 | 1 | 4352 | 6078 | 6078
Design Validation Activities | 2021-11-12 10:17 | 3.06 | 2021-11-16 16:02 | 12 | Complete | 2200 | 2200 | 1 | 1 | 2200 | 3188.5 | 3188.5
Test Prototype | 2021-10-26 13:17 | 12.75 | 2021-11-12 10:17 | 25 | Complete | 6000 | 6000 | 1 | 1 | 6000 | 5635.52 | 5635.52
Process Engineering Plan | 2021-10-26 13:17 | 17.63 | 2021-11-19 09:19 | 25 | Complete | 6000 | 6000 | 1 | 1 | 6000 | 7811.1 | 7811.1
Show Functional Model at Trade Show | 2021-11-01 08:00 | 3.25 | 2021-11-04 10:00 | 21 | Complete | 2352 | 2352 | 1 | 1 | 2352 | 2535 | 2535
PM Period 8 | 2021-10-26 13:17 | 3.38 | 2021-10-29 16:19 | 25 | Complete | 2352 | 2352 | 1 | 1 | 2352 | 2636.4 | 2636.4
Milestone 8 | 2021-11-19 09:19 | 0 | 2021-11-19 09:19 | 7 | Complete | 0 | 0 | 1 | 1 | 0 | 40 | 40
Validation Design Review | 2021-11-19 09:19 | 4.75 | 2021-11-25 16:19 | 7 | Complete | 1968 | 1968 | 1 | 1 | 1968 | 2565 | 2565
Approve Model Design | 2021-11-25 16:19 | 5.13 | 2021-12-03 08:22 | 3 | Busy | 1968 | 1968 | 1 | 0.40651 | 800.0195 | 2267.46 | 921.7542
Evaluate Test Results | 2021-11-19 09:19 | 7.38 | 2021-11-30 13:22 | 7 | Busy | 3600 | 3600 | 1 | 0.92621 | 3334.3496 | 4428 | 4101.25
PM Period 9 | 2021-11-19 09:19 | 4.63 | 2021-11-25 15:22 | 7 | Complete | 3136 | 3136 | 1 | 1 | 3136 | 3611.4 | 3611.4
Milestone 9 | 2021-12-03 08:22 | 0 | 2021-12-03 08:22 | -5 | Busy | 0 | 0 | 1 | 0 | 0 | 240 | 0
Qualify Supplier | 2021-12-03 08:22 | 12.5 | 2021-12-21 13:22 | -5 | Busy | 6000 | 6000 | 1 | 0 | 0 | 7500 | 0
Design Transfer Activities | 2021-12-03 08:22 | 8.25 | 2021-12-15 10:22 | -5 | Busy | 4200 | 4200 | 1 | 0 | 0 | 4455 | 0
Product Release Meetings | 2021-12-15 10:22 | 3.38 | 2021-12-20 14:24 | -13 | Busy | 3000 | 3000 | 1 | 0 | 0 | 2636 | 0
Develop Production Plan | 2021-12-03 08:22 | 8.25 | 2021-12-15 10:22 | -5 | Busy | 2400 | 2400 | 1 | 0 | 0 | 3646.5 | 0
PM Period 10 | 2021-12-03 08:22 | 5.63 | 2021-12-10 14:24 | -5 | Busy | 3920 | 3920 | 1 | 0 | 0 | 4391.4 | 0
Milestone 10 | 2021-12-21 13:22 | 0 | 2021-12-21 13:22 | -17 | Busy | 0 | 0 | 1 | 0 | 0 | 40 | 0
Assess RFQ Responses | 2021-12-21 13:22 | 6.06 | 2021-12-29 13:50 | -17 | Busy | 6000 | 6000 | 1 | 0 | 0 | 6908.4 | 0 | 2021-11-12 | 12 | 10
Develop Production Control Plan | 2021-12-21 13:22 | 11.13 | 2022-01-05 14:24 | -17 | Busy | 3400 | 3400 | 1 | 0 | 0 | 4919.46 | 0 | 2021-11-12 | 12 | 8.5
Approve Production Parts | 2022-01-05 14:24 | 3.31 | 2022-01-10 16:53 | -28 | Busy | 2000 | 1200 | 0.6 | 0 | 0 | 3250.42 | 0 | 2021-11-25 | 3 | 5
Contracting for Deliveries | 2022-01-10 16:53 | 5.13 | 2022-01-18 08:55 | -31 | Busy | 3200 | 0 | 0 | 0 | 0 | 5037.66 | 0
PM Period 11 | 2021-12-21 13:22 | 14.75 | 2022-01-11 10:22 | -17 | Busy | 5720 | 5280.132 | 0.9231 | 0 | 0 | 11505 | 0 | 2021-11-12 | 12 | 13
Milestone 11 | 2022-01-18 08:55 | 0 | 2022-01-18 08:55 | -37 | Busy | 0 | 0 | 0 | 0 | 0 | 40 | 0
Totals | [6 empty] | 280120.132 |  |  | 243286.3691 |  | 316883.5342
CPI | 0.7677
SPI | 0.8685
ETC | 68758.1489
EAC | 385641.6831
Formulas:
Network Days to Analysis Date = NETWORKDAYS([Real Start Date],D3)
Network Days to Analysis Date = NETWORKDAYS([Planned Start Date],D3)

## Period 10
Period 10 |  | Analysis Date at 17:00
2021-12-15 17:00
Task | Real Start Date | Real Duration | Real End Date | Network Days to Analysis Date | Complete/Busy | Full Budget | Planned Value | %Sched Completion | %Actual Completion | Earned Value | Actual Cost | Actual Cost at Analysis Date | Planned Start Date | Network Days to Analysis Date | Planned Duration
Evaluate Market | 2021-03-31 09:00 | 6.69 | 2021-04-08 15:31 | 186 | Complete | 7728 | 7728 | 1 | 1 | 7728 | 8563.2 | 8563.2
Develop Business Opportunity | 2021-04-08 15:31 | 8.06 | 2021-04-20 16:00 | 180 | Complete | 9016 | 9016 | 1 | 1 | 9016 | 10316.8 | 10316.8
Customer Preference Study | 2021-04-20 16:00 | 12.13 | 2021-05-07 08:02 | 172 | Complete | 13524 | 13524 | 1 | 1 | 13524 | 15526.4 | 15526.4
Business Evaluation (NPV, etc.) | 2021-05-07 08:02 | 2.38 | 2021-05-11 11:05 | 159 | Complete | 2576 | 2576 | 1 | 1 | 2576 | 3046.4 | 3046.4
PM Period 1 | 2021-03-31 09:00 | 18.06 | 2021-04-26 09:29 | 186 | Complete | 12300 | 12300 | 1 | 1 | 12300 | 17734.92 | 17734.92
Milestone 1 | 2021-05-11 11:05 | 0 | 2021-05-11 11:05 | 157 | Complete | 0 | 0 | 1 | 1 | 0 | 40 | 40
Design and Development Plan | 2021-05-11 11:05 | 3.88 | 2021-05-17 10:07 | 157 | Complete | 2352 | 2352 | 1 | 1 | 2352 | 3585.12 | 3585.12
Design Specs | 2021-05-17 10:07 | 13.75 | 2021-06-04 08:07 | 153 | Complete | 8624 | 8624 | 1 | 1 | 8624 | 12705 | 12705
Develop Prelim Marketing Plan | 2021-05-11 11:05 | 2.81 | 2021-05-14 09:34 | 157 | Complete | 3220 | 3220 | 1 | 1 | 3220 | 3596.8 | 3596.8
Develop Marketing Program | 2021-05-14 09:34 | 8.44 | 2021-05-26 14:05 | 154 | Complete | 9660 | 9660 | 1 | 1 | 9660 | 10803.2 | 10803.2
PM Period 2 | 2021-05-11 11:05 | 10.06 | 2021-05-25 11:34 | 157 | Complete | 6888 | 6888 | 1 | 1 | 6888 | 9878.92 | 9878.92
Milestone 2 | 2021-06-04 08:07 | 0 | 2021-06-04 08:07 | 139 | Complete | 0 | 0 | 1 | 1 | 0 | 360 | 360
Identify Testing Requirements | 2021-06-04 08:07 | 6.25 | 2021-06-14 10:07 | 139 | Complete | 3920 | 3920 | 1 | 1 | 3920 | 5775 | 5775
Risk Analysis | 2021-06-14 10:07 | 7.06 | 2021-06-23 10:36 | 133 | Complete | 3920 | 3920 | 1 | 1 | 3920 | 6523.44 | 6523.44
Train Sales Team | 2021-06-04 08:07 | 24.88 | 2021-07-08 16:10 | 139 | Complete | 11088 | 11088 | 1 | 1 | 11088 | 12440 | 12440
Advertising Campaign | 2021-06-04 08:07 | 31.38 | 2021-07-19 11:10 | 139 | Complete | 21952 | 21952 | 1 | 1 | 21952 | 24476.4 | 24476.4
PM Period 3 | 2021-06-04 08:07 | 10.13 | 2021-06-18 09:10 | 139 | Complete | 6888 | 6888 | 1 | 1 | 6888 | 9947.66 | 9947.66
Milestone 3 | 2021-07-19 11:10 | 0 | 2021-07-19 11:10 | 108 | Complete | 0 | 0 | 1 | 1 | 0 | 60 | 60
Design Labelling | 2021-07-14 08:07 | 3.25 | 2021-07-19 10:07 | 111 | Complete | 1960 | 1960 | 1 | 1 | 1960 | 3003 | 3003
Approve Design | 2021-07-19 10:07 | 2.63 | 2021-07-21 16:10 | 108 | Complete | 1568 | 1568 | 1 | 1 | 1568 | 2430.12 | 2430.12
Initial Engineering Specs | 2021-07-21 16:10 | 2.88 | 2021-07-26 15:12 | 106 | Complete | 2460 | 2460 | 1 | 1 | 2460 | 2828.16 | 2828.16
PM Period 4 | 2021-07-19 11:10 | 14.63 | 2021-08-09 08:12 | 108 | Complete | 10192 | 10192 | 1 | 1 | 10192 | 11411.4 | 11411.4
Milestone 4 | 2021-08-09 08:12 | 0 | 2021-08-09 08:12 | 93 | Complete | 0 | 0 | 1 | 1 | 0 | 663.75 | 663.75
Design Verification Activities | 2021-08-09 08:12 | 4.19 | 2021-08-13 09:43 | 93 | Complete | 3444 | 3444 | 1 | 1 | 3444 | 4114.58 | 4114.58
Verification Design Review | 2021-08-13 09:43 | 2.31 | 2021-08-17 13:12 | 89 | Complete | 1968 | 1968 | 1 | 1 | 1968 | 2268.42 | 2268.42
Release Pre-Production Specs | 2021-08-17 13:12 | 6 | 2021-08-25 13:12 | 87 | Complete | 4920 | 4920 | 1 | 1 | 4920 | 5892 | 5892
PM Period 5 | 2021-08-09 08:12 | 17 | 2021-09-01 08:12 | 93 | Complete | 11760 | 11760 | 1 | 1 | 11760 | 13260 | 13260
Milestone 5 | 2021-09-01 08:12 | 0 | 2021-09-01 08:12 | 76 | Complete | 0 | 0 | 1 | 1 | 0 | 4851 | 4851
Identify Vendors | 2021-09-01 08:12 | 4.5 | 2021-09-07 13:12 | 76 | Complete | 2800 | 2800 | 1 | 1 | 2800 | 3528 | 3528
Develop and Issue RFQ | 2021-09-07 13:12 | 3.88 | 2021-09-13 09:02 | 72 | Complete | 2400 | 2400 | 1 | 1 | 2400 | 3041.92 | 3041.92
Build Functional Model | 2021-09-01 08:12 | 11.25 | 2021-09-16 10:12 | 76 | Complete | 8856 | 8856 | 1 | 1 | 8856 | 11047.5 | 11047.5
Evaluate Design Specs | 2021-09-01 08:12 | 14.88 | 2021-09-21 16:14 | 76 | Complete | 6000 | 6000 | 1 | 1 | 6000 | 8928 | 8928
PM Period 6 | 2021-09-01 08:12 | 10.25 | 2021-09-15 10:12 | 76 | Complete | 7056 | 7056 | 1 | 1 | 7056 | 7995 | 7995
Milestone 6 | 2021-09-21 16:14 | 0 | 2021-09-21 16:14 | 62 | Complete | 0 | 0 | 1 | 1 | 0 | 4638 | 4638
Issue Sample | 2021-09-21 16:14 | 7.5 | 2021-10-01 11:14 | 62 | Complete | 3000 | 3000 | 1 | 1 | 3000 | 4500 | 4500
Perform Supplier Process Capability | 2021-10-01 11:14 | 17.13 | 2021-10-26 13:17 | 54 | Complete | 6608 | 6608 | 1 | 1 | 6608 | 9250 | 9250
Develop Testing Protocol for Prototype | 2021-09-21 16:14 | 10.25 | 2021-10-06 09:14 | 62 | Complete | 3520 | 3520 | 1 | 1 | 3520 | 4530.5 | 4530.5
PM Period 7 | 2021-09-21 16:14 | 12.5 | 2021-10-08 11:14 | 62 | Complete | 8624 | 8624 | 1 | 1 | 8624 | 9750 | 9750
Milestone 7 | 2021-09-21 16:14 | 0 | 2021-09-21 16:14 | 62 | Complete | 0 | 0 | 1 | 1 | 0 | 4449 | 4449
Approve Sample Parts | 2021-10-26 13:17 | 10.13 | 2021-11-09 14:19 | 37 | Complete | 4352 | 4352 | 1 | 1 | 4352 | 6078 | 6078
Design Validation Activities | 2021-11-12 10:17 | 3.06 | 2021-11-16 16:02 | 24 | Complete | 2200 | 2200 | 1 | 1 | 2200 | 3188.5 | 3188.5
Test Prototype | 2021-10-26 13:17 | 12.75 | 2021-11-12 10:17 | 37 | Complete | 6000 | 6000 | 1 | 1 | 6000 | 5635.52 | 5635.52
Process Engineering Plan | 2021-10-26 13:17 | 17.63 | 2021-11-19 09:19 | 37 | Complete | 6000 | 6000 | 1 | 1 | 6000 | 7811.1 | 7811.1
Show Functional Model at Trade Show | 2021-11-01 08:00 | 3.25 | 2021-11-04 10:00 | 33 | Complete | 2352 | 2352 | 1 | 1 | 2352 | 2535 | 2535
PM Period 8 | 2021-10-26 13:17 | 3.38 | 2021-10-29 16:19 | 37 | Complete | 2352 | 2352 | 1 | 1 | 2352 | 2636.4 | 2636.4
Milestone 8 | 2021-11-19 09:19 | 0 | 2021-11-19 09:19 | 19 | Complete | 0 | 0 | 1 | 1 | 0 | 40 | 40
Validation Design Review | 2021-11-19 09:19 | 4.75 | 2021-11-25 16:19 | 19 | Complete | 1968 | 1968 | 1 | 1 | 1968 | 2565 | 2565
Approve Model Design | 2021-11-25 16:19 | 5.13 | 2021-12-03 08:22 | 15 | Complete | 1968 | 1968 | 1 | 1 | 1968 | 2267.46 | 2267.46
Evaluate Test Results | 2021-11-19 09:19 | 7.38 | 2021-11-30 13:22 | 19 | Complete | 3600 | 3600 | 1 | 1 | 3600 | 4428 | 4428
PM Period 9 | 2021-11-19 09:19 | 4.63 | 2021-11-25 15:22 | 19 | Complete | 3136 | 3136 | 1 | 1 | 3136 | 3611.4 | 3611.4
Milestone 9 | 2021-12-03 08:22 | 0 | 2021-12-03 08:22 | 9 | Complete | 0 | 0 | 1 | 1 | 0 | 240 | 240
Qualify Supplier | 2021-12-03 08:22 | 12.5 | 2021-12-21 13:22 | 9 | Busy | 6000 | 6000 | 1 | 0.71633 | 4298 | 7500 | 5372.5
Design Transfer Activities | 2021-12-03 08:22 | 8.25 | 2021-12-15 10:22 | 9 | Complete | 4200 | 4200 | 1 | 1 | 4200 | 4455 | 4455
Product Release Meetings | 2021-12-15 10:22 | 3.38 | 2021-12-20 14:24 | 1 | Busy | 3000 | 3000 | 1 | 0.20833 | 625 | 2636 | 549.1667
Develop Production Plan | 2021-12-03 08:22 | 8.25 | 2021-12-15 10:22 | 9 | Complete | 2400 | 2400 | 1 | 1 | 2400 | 3646.5 | 3646.5
PM Period 10 | 2021-12-03 08:22 | 5.63 | 2021-12-10 14:24 | 9 | Complete | 3920 | 3920 | 1 | 1 | 3920 | 4391.4 | 4391.4
Milestone 10 | 2021-12-21 13:22 | 0 | 2021-12-21 13:22 | -5 | Busy | 0 | 0 | 1 | 0 | 0 | 40 | 0
Assess RFQ Responses | 2021-12-21 13:22 | 6.06 | 2021-12-29 13:50 | -5 | Busy | 6000 | 6000 | 1 | 0 | 0 | 6908.4 | 0
Develop Production Control Plan | 2021-12-21 13:22 | 11.13 | 2022-01-05 14:24 | -5 | Busy | 3400 | 3400 | 1 | 0 | 0 | 4919.46 | 0
Approve Production Parts | 2022-01-05 14:24 | 3.31 | 2022-01-10 16:53 | -16 | Busy | 2000 | 2000 | 1 | 0 | 0 | 3250.42 | 0
Contracting for Deliveries | 2022-01-10 16:53 | 5.13 | 2022-01-18 08:55 | -19 | Busy | 3200 | 3200 | 1 | 0 | 0 | 5037.66 | 0
PM Period 11 | 2021-12-21 13:22 | 14.75 | 2022-01-11 10:22 | -5 | Busy | 5720 | 5720 | 1 | 0 | 0 | 11505 | 0
Milestone 11 | 2022-01-18 08:55 | 0 | 2022-01-18 08:55 | -25 | Busy | 0 | 0 | 0 | 0 | 0 | 40 | 0
Submit Production Purchase Order | 2022-01-18 08:55 | 1.31 | 2022-01-19 11:24 | -25 | Busy | 800 | 800 | 1 | 0 | 0 | 1286.42 | 0 | 2021-12-14 | 2 | 2
Production Pilot Test | 2022-01-19 11:24 | 3.19 | 2022-01-24 13:55 | -26 | Busy | 2000 | 0 | 0 | 0 | 0 | 3132.58 | 0
Debugging Production System | 2022-01-24 13:55 | 2.44 | 2022-01-27 08:26 | -29 | Busy | 1600 | 0 | 0 | 0 | 0 | 2396.08 | 0
Production Release | 2022-01-27 08:26 | 2 | 2022-01-31 08:26 | -32 | Busy | 1200 | 0 | 0 | 0 | 0 | 1964 | 0
Product Launch | 2022-02-02 11:58 | 3.38 | 2022-02-07 16:00 | -36 | Busy | 1512 | 0 | 0 | 0 | 0 | 2636.4 | 0
PM Period 12 | 2022-01-18 08:55 | 11.38 | 2022-02-02 11:58 | -25 | Busy | 4400 | 880 | 0.2 | 0 | 0 | 8876.4 | 0 | 2021-12-14 | 2 | 10
Milestone 12 | 2022-02-07 16:00 | 0 | 2022-02-07 16:00 | -39 | Busy | 0 | 0 | 0 | 0 | 0 | 0 | 0
Totals | [6 empty] | 286240 |  |  | 260163 |  | 337210.5567
CPI | 0.7715
SPI | 0.9089
ETC | 46544.394
EAC | 383754.9507
Formulas:
Network Days to Analysis Date = NETWORKDAYS([Real Start Date],D3)
Network Days to Analysis Date = NETWORKDAYS([Planned Start Date],D3)

## Period 11
Period 11 |  | Analysis Date at 17:00
2022-01-12 17:00
Task | Real Start Date | Real Duration | Real End Date | Network Days to Analysis Date | Complete/Busy | Full Budget | Planned Value | %Sched Completion | %Actual Completion | Earned Value | Actual Cost | Actual Cost at Analysis Date | Planned Start Date | Network Days to Analysis Date | Planned Duration
Evaluate Market | 2021-03-31 09:00 | 6.69 | 2021-04-08 15:31 | 206 | Complete | 7728 | 7728 | 1 | 1 | 7728 | 8563.2 | 8563.2
Develop Business Opportunity | 2021-04-08 15:31 | 8.06 | 2021-04-20 16:00 | 200 | Complete | 9016 | 9016 | 1 | 1 | 9016 | 10316.8 | 10316.8
Customer Preference Study | 2021-04-20 16:00 | 12.13 | 2021-05-07 08:02 | 192 | Complete | 13524 | 13524 | 1 | 1 | 13524 | 15526.4 | 15526.4
Business Evaluation (NPV, etc.) | 2021-05-07 08:02 | 2.38 | 2021-05-11 11:05 | 179 | Complete | 2576 | 2576 | 1 | 1 | 2576 | 3046.4 | 3046.4
PM Period 1 | 2021-03-31 09:00 | 18.06 | 2021-04-26 09:29 | 206 | Complete | 12300 | 12300 | 1 | 1 | 12300 | 17734.92 | 17734.92
Milestone 1 | 2021-05-11 11:05 | 0 | 2021-05-11 11:05 | 177 | Complete | 0 | 0 | 1 | 1 | 0 | 40 | 40
Design and Development Plan | 2021-05-11 11:05 | 3.88 | 2021-05-17 10:07 | 177 | Complete | 2352 | 2352 | 1 | 1 | 2352 | 3585.12 | 3585.12
Design Specs | 2021-05-17 10:07 | 13.75 | 2021-06-04 08:07 | 173 | Complete | 8624 | 8624 | 1 | 1 | 8624 | 12705 | 12705
Develop Prelim Marketing Plan | 2021-05-11 11:05 | 2.81 | 2021-05-14 09:34 | 177 | Complete | 3220 | 3220 | 1 | 1 | 3220 | 3596.8 | 3596.8
Develop Marketing Program | 2021-05-14 09:34 | 8.44 | 2021-05-26 14:05 | 174 | Complete | 9660 | 9660 | 1 | 1 | 9660 | 10803.2 | 10803.2
PM Period 2 | 2021-05-11 11:05 | 10.06 | 2021-05-25 11:34 | 177 | Complete | 6888 | 6888 | 1 | 1 | 6888 | 9878.92 | 9878.92
Milestone 2 | 2021-06-04 08:07 | 0 | 2021-06-04 08:07 | 159 | Complete | 0 | 0 | 1 | 1 | 0 | 360 | 360
Identify Testing Requirements | 2021-06-04 08:07 | 6.25 | 2021-06-14 10:07 | 159 | Complete | 3920 | 3920 | 1 | 1 | 3920 | 5775 | 5775
Risk Analysis | 2021-06-14 10:07 | 7.06 | 2021-06-23 10:36 | 153 | Complete | 3920 | 3920 | 1 | 1 | 3920 | 6523.44 | 6523.44
Train Sales Team | 2021-06-04 08:07 | 24.88 | 2021-07-08 16:10 | 159 | Complete | 11088 | 11088 | 1 | 1 | 11088 | 12440 | 12440
Advertising Campaign | 2021-06-04 08:07 | 31.38 | 2021-07-19 11:10 | 159 | Complete | 21952 | 21952 | 1 | 1 | 21952 | 24476.4 | 24476.4
PM Period 3 | 2021-06-04 08:07 | 10.13 | 2021-06-18 09:10 | 159 | Complete | 6888 | 6888 | 1 | 1 | 6888 | 9947.66 | 9947.66
Milestone 3 | 2021-07-19 11:10 | 0 | 2021-07-19 11:10 | 128 | Complete | 0 | 0 | 1 | 1 | 0 | 60 | 60
Design Labelling | 2021-07-14 08:07 | 3.25 | 2021-07-19 10:07 | 131 | Complete | 1960 | 1960 | 1 | 1 | 1960 | 3003 | 3003
Approve Design | 2021-07-19 10:07 | 2.63 | 2021-07-21 16:10 | 128 | Complete | 1568 | 1568 | 1 | 1 | 1568 | 2430.12 | 2430.12
Initial Engineering Specs | 2021-07-21 16:10 | 2.88 | 2021-07-26 15:12 | 126 | Complete | 2460 | 2460 | 1 | 1 | 2460 | 2828.16 | 2828.16
PM Period 4 | 2021-07-19 11:10 | 14.63 | 2021-08-09 08:12 | 128 | Complete | 10192 | 10192 | 1 | 1 | 10192 | 11411.4 | 11411.4
Milestone 4 | 2021-08-09 08:12 | 0 | 2021-08-09 08:12 | 113 | Complete | 0 | 0 | 1 | 1 | 0 | 663.75 | 663.75
Design Verification Activities | 2021-08-09 08:12 | 4.19 | 2021-08-13 09:43 | 113 | Complete | 3444 | 3444 | 1 | 1 | 3444 | 4114.58 | 4114.58
Verification Design Review | 2021-08-13 09:43 | 2.31 | 2021-08-17 13:12 | 109 | Complete | 1968 | 1968 | 1 | 1 | 1968 | 2268.42 | 2268.42
Release Pre-Production Specs | 2021-08-17 13:12 | 6 | 2021-08-25 13:12 | 107 | Complete | 4920 | 4920 | 1 | 1 | 4920 | 5892 | 5892
PM Period 5 | 2021-08-09 08:12 | 17 | 2021-09-01 08:12 | 113 | Complete | 11760 | 11760 | 1 | 1 | 11760 | 13260 | 13260
Milestone 5 | 2021-09-01 08:12 | 0 | 2021-09-01 08:12 | 96 | Complete | 0 | 0 | 1 | 1 | 0 | 4851 | 4851
Identify Vendors | 2021-09-01 08:12 | 4.5 | 2021-09-07 13:12 | 96 | Complete | 2800 | 2800 | 1 | 1 | 2800 | 3528 | 3528
Develop and Issue RFQ | 2021-09-07 13:12 | 3.88 | 2021-09-13 09:02 | 92 | Complete | 2400 | 2400 | 1 | 1 | 2400 | 3041.92 | 3041.92
Build Functional Model | 2021-09-01 08:12 | 11.25 | 2021-09-16 10:12 | 96 | Complete | 8856 | 8856 | 1 | 1 | 8856 | 11047.5 | 11047.5
Evaluate Design Specs | 2021-09-01 08:12 | 14.88 | 2021-09-21 16:14 | 96 | Complete | 6000 | 6000 | 1 | 1 | 6000 | 8928 | 8928
PM Period 6 | 2021-09-01 08:12 | 10.25 | 2021-09-15 10:12 | 96 | Complete | 7056 | 7056 | 1 | 1 | 7056 | 7995 | 7995
Milestone 6 | 2021-09-21 16:14 | 0 | 2021-09-21 16:14 | 82 | Complete | 0 | 0 | 1 | 1 | 0 | 4638 | 4638
Issue Sample | 2021-09-21 16:14 | 7.5 | 2021-10-01 11:14 | 82 | Complete | 3000 | 3000 | 1 | 1 | 3000 | 4500 | 4500
Perform Supplier Process Capability | 2021-10-01 11:14 | 17.13 | 2021-10-26 13:17 | 74 | Complete | 6608 | 6608 | 1 | 1 | 6608 | 9250 | 9250
Develop Testing Protocol for Prototype | 2021-09-21 16:14 | 10.25 | 2021-10-06 09:14 | 82 | Complete | 3520 | 3520 | 1 | 1 | 3520 | 4530.5 | 4530.5
PM Period 7 | 2021-09-21 16:14 | 12.5 | 2021-10-08 11:14 | 82 | Complete | 8624 | 8624 | 1 | 1 | 8624 | 9750 | 9750
Milestone 7 | 2021-09-21 16:14 | 0 | 2021-09-21 16:14 | 82 | Complete | 0 | 0 | 1 | 1 | 0 | 4449 | 4449
Approve Sample Parts | 2021-10-26 13:17 | 10.13 | 2021-11-09 14:19 | 57 | Complete | 4352 | 4352 | 1 | 1 | 4352 | 6078 | 6078
Design Validation Activities | 2021-11-12 10:17 | 3.06 | 2021-11-16 16:02 | 44 | Complete | 2200 | 2200 | 1 | 1 | 2200 | 3188.5 | 3188.5
Test Prototype | 2021-10-26 13:17 | 12.75 | 2021-11-12 10:17 | 57 | Complete | 6000 | 6000 | 1 | 1 | 6000 | 5635.52 | 5635.52
Process Engineering Plan | 2021-10-26 13:17 | 17.63 | 2021-11-19 09:19 | 57 | Complete | 6000 | 6000 | 1 | 1 | 6000 | 7811.1 | 7811.1
Show Functional Model at Trade Show | 2021-11-01 08:00 | 3.25 | 2021-11-04 10:00 | 53 | Complete | 2352 | 2352 | 1 | 1 | 2352 | 2535 | 2535
PM Period 8 | 2021-10-26 13:17 | 3.38 | 2021-10-29 16:19 | 57 | Complete | 2352 | 2352 | 1 | 1 | 2352 | 2636.4 | 2636.4
Milestone 8 | 2021-11-19 09:19 | 0 | 2021-11-19 09:19 | 39 | Complete | 0 | 0 | 1 | 1 | 0 | 40 | 40
Validation Design Review | 2021-11-19 09:19 | 4.75 | 2021-11-25 16:19 | 39 | Complete | 1968 | 1968 | 1 | 1 | 1968 | 2565 | 2565
Approve Model Design | 2021-11-25 16:19 | 5.13 | 2021-12-03 08:22 | 35 | Complete | 1968 | 1968 | 1 | 1 | 1968 | 2267.46 | 2267.46
Evaluate Test Results | 2021-11-19 09:19 | 7.38 | 2021-11-30 13:22 | 39 | Complete | 3600 | 3600 | 1 | 1 | 3600 | 4428 | 4428
PM Period 9 | 2021-11-19 09:19 | 4.63 | 2021-11-25 15:22 | 39 | Complete | 3136 | 3136 | 1 | 1 | 3136 | 3611.4 | 3611.4
Milestone 9 | 2021-12-03 08:22 | 0 | 2021-12-03 08:22 | 29 | Complete | 0 | 0 | 1 | 1 | 0 | 240 | 240
Qualify Supplier | 2021-12-03 08:22 | 12.5 | 2021-12-21 13:22 | 29 | Complete | 6000 | 6000 | 1 | 1 | 6000 | 7500 | 7500
Design Transfer Activities | 2021-12-03 08:22 | 8.25 | 2021-12-15 10:22 | 29 | Complete | 4200 | 4200 | 1 | 1 | 4200 | 4455 | 4455
Product Release Meetings | 2021-12-15 10:22 | 3.38 | 2021-12-20 14:24 | 21 | Complete | 3000 | 3000 | 1 | 1 | 3000 | 2636 | 2636
Develop Production Plan | 2021-12-03 08:22 | 8.25 | 2021-12-15 10:22 | 29 | Complete | 2400 | 2400 | 1 | 1 | 2400 | 3646.5 | 3646.5
PM Period 10 | 2021-12-03 08:22 | 5.63 | 2021-12-10 14:24 | 29 | Complete | 3920 | 3920 | 1 | 1 | 3920 | 4391.4 | 4391.4
Milestone 10 | 2021-12-21 13:22 | 0 | 2021-12-21 13:22 | 17 | Complete | 0 | 0 | 1 | 1 | 0 | 40 | 40
Assess RFQ Responses | 2021-12-21 13:22 | 6.06 | 2021-12-29 13:50 | 17 | Complete | 6000 | 6000 | 1 | 1 | 6000 | 6908.4 | 6908.4
Develop Production Control Plan | 2021-12-21 13:22 | 11.13 | 2022-01-05 14:24 | 17 | Complete | 3400 | 3400 | 1 | 1 | 3400 | 4919.46 | 4919.46
Approve Production Parts | 2022-01-05 14:24 | 3.31 | 2022-01-10 16:53 | 6 | Complete | 2000 | 2000 | 1 | 1 | 2000 | 3250.42 | 3250.42
Contracting for Deliveries | 2022-01-10 16:53 | 5.13 | 2022-01-18 08:55 | 3 | Busy | 3200 | 3200 | 1 | 0.39271 | 1256.6602 | 5037.66 | 1978.3208
PM Period 11 | 2021-12-21 13:22 | 14.75 | 2022-01-11 10:22 | 17 | Complete | 5720 | 5720 | 1 | 1 | 5720 | 11505 | 11505
Milestone 11 | 2022-01-18 08:55 | 0 | 2022-01-18 08:55 | -5 | Busy | 0 | 0 | 1 | 0 | 0 | 40 | 0
Submit Production Purchase Order | 2022-01-18 08:55 | 1.31 | 2022-01-19 11:24 | -5 | Busy | 800 | 800 | 1 | 0 | 0 | 1286.42 | 0
Production Pilot Test | 2022-01-19 11:24 | 3.19 | 2022-01-24 13:55 | -6 | Busy | 2000 | 2000 | 1 | 0 | 0 | 3132.58 | 0
Debugging Production System | 2022-01-24 13:55 | 2.44 | 2022-01-27 08:26 | -9 | Busy | 1600 | 1600 | 1 | 0 | 0 | 2396.08 | 0
Production Release | 2022-01-27 08:26 | 2 | 2022-01-31 08:26 | -12 | Busy | 1200 | 1200 | 1 | 0 | 0 | 1964 | 0
Product Launch | 2022-02-02 11:58 | 3.38 | 2022-02-07 16:00 | -16 | Busy | 1512 | 1512 | 1 | 0 | 0 | 2636.4 | 0
PM Period 12 | 2022-01-18 08:55 | 11.38 | 2022-02-02 11:58 | -5 | Busy | 4400 | 4400 | 1 | 0 | 0 | 8876.4 | 0
Milestone 12 | 2022-02-07 16:00 | 0 | 2022-02-07 16:00 | -19 | Busy | 0 | 0 | 1 | 0 | 0 | 0 | 0
Totals | [6 empty] | 296072 |  |  | 282616.6602 |  | 370026.4908
CPI | 0.7638
SPI | 0.9546
ETC | 17616.3129
EAC | 387642.8037
Formulas:
Network Days to Analysis Date = NETWORKDAYS([Real Start Date],D3)

## Period 12
Period 12 |  | Analysis Date at 17:00
2022-02-07 17:00
Task | Real Start Date | Real Duration | Real End Date | Network Days to Analysis Date | Complete/Busy | Full Budget | Planned Value | %Sched Completion | %Actual Completion | Earned Value | Actual Cost | Actual Cost at Analysis Date | Planned Start Date | Network Days to Analysis Date | Planned Duration
Evaluate Market | 2021-03-31 09:00 | 6.69 | 2021-04-08 15:31 | 224 | Complete | 7728 | 7728 | 1 | 1 | 7728 | 8563.2 | 8563.2
Develop Business Opportunity | 2021-04-08 15:31 | 8.06 | 2021-04-20 16:00 | 218 | Complete | 9016 | 9016 | 1 | 1 | 9016 | 10316.8 | 10316.8
Customer Preference Study | 2021-04-20 16:00 | 12.13 | 2021-05-07 08:02 | 210 | Complete | 13524 | 13524 | 1 | 1 | 13524 | 15526.4 | 15526.4
Business Evaluation (NPV, etc.) | 2021-05-07 08:02 | 2.38 | 2021-05-11 11:05 | 197 | Complete | 2576 | 2576 | 1 | 1 | 2576 | 3046.4 | 3046.4
PM Period 1 | 2021-03-31 09:00 | 18.06 | 2021-04-26 09:29 | 224 | Complete | 12300 | 12300 | 1 | 1 | 12300 | 17734.92 | 17734.92
Milestone 1 | 2021-05-11 11:05 | 0 | 2021-05-11 11:05 | 195 | Complete | 0 | 0 | 1 | 1 | 0 | 40 | 40
Design and Development Plan | 2021-05-11 11:05 | 3.88 | 2021-05-17 10:07 | 195 | Complete | 2352 | 2352 | 1 | 1 | 2352 | 3585.12 | 3585.12
Design Specs | 2021-05-17 10:07 | 13.75 | 2021-06-04 08:07 | 191 | Complete | 8624 | 8624 | 1 | 1 | 8624 | 12705 | 12705
Develop Prelim Marketing Plan | 2021-05-11 11:05 | 2.81 | 2021-05-14 09:34 | 195 | Complete | 3220 | 3220 | 1 | 1 | 3220 | 3596.8 | 3596.8
Develop Marketing Program | 2021-05-14 09:34 | 8.44 | 2021-05-26 14:05 | 192 | Complete | 9660 | 9660 | 1 | 1 | 9660 | 10803.2 | 10803.2
PM Period 2 | 2021-05-11 11:05 | 10.06 | 2021-05-25 11:34 | 195 | Complete | 6888 | 6888 | 1 | 1 | 6888 | 9878.92 | 9878.92
Milestone 2 | 2021-06-04 08:07 | 0 | 2021-06-04 08:07 | 177 | Complete | 0 | 0 | 1 | 1 | 0 | 360 | 360
Identify Testing Requirements | 2021-06-04 08:07 | 6.25 | 2021-06-14 10:07 | 177 | Complete | 3920 | 3920 | 1 | 1 | 3920 | 5775 | 5775
Risk Analysis | 2021-06-14 10:07 | 7.06 | 2021-06-23 10:36 | 171 | Complete | 3920 | 3920 | 1 | 1 | 3920 | 6523.44 | 6523.44
Train Sales Team | 2021-06-04 08:07 | 24.88 | 2021-07-08 16:10 | 177 | Complete | 11088 | 11088 | 1 | 1 | 11088 | 12440 | 12440
Advertising Campaign | 2021-06-04 08:07 | 31.38 | 2021-07-19 11:10 | 177 | Complete | 21952 | 21952 | 1 | 1 | 21952 | 24476.4 | 24476.4
PM Period 3 | 2021-06-04 08:07 | 10.13 | 2021-06-18 09:10 | 177 | Complete | 6888 | 6888 | 1 | 1 | 6888 | 9947.66 | 9947.66
Milestone 3 | 2021-07-19 11:10 | 0 | 2021-07-19 11:10 | 146 | Complete | 0 | 0 | 1 | 1 | 0 | 60 | 60
Design Labelling | 2021-07-14 08:07 | 3.25 | 2021-07-19 10:07 | 149 | Complete | 1960 | 1960 | 1 | 1 | 1960 | 3003 | 3003
Approve Design | 2021-07-19 10:07 | 2.63 | 2021-07-21 16:10 | 146 | Complete | 1568 | 1568 | 1 | 1 | 1568 | 2430.12 | 2430.12
Initial Engineering Specs | 2021-07-21 16:10 | 2.88 | 2021-07-26 15:12 | 144 | Complete | 2460 | 2460 | 1 | 1 | 2460 | 2828.16 | 2828.16
PM Period 4 | 2021-07-19 11:10 | 14.63 | 2021-08-09 08:12 | 146 | Complete | 10192 | 10192 | 1 | 1 | 10192 | 11411.4 | 11411.4
Milestone 4 | 2021-08-09 08:12 | 0 | 2021-08-09 08:12 | 131 | Complete | 0 | 0 | 1 | 1 | 0 | 663.75 | 663.75
Design Verification Activities | 2021-08-09 08:12 | 4.19 | 2021-08-13 09:43 | 131 | Complete | 3444 | 3444 | 1 | 1 | 3444 | 4114.58 | 4114.58
Verification Design Review | 2021-08-13 09:43 | 2.31 | 2021-08-17 13:12 | 127 | Complete | 1968 | 1968 | 1 | 1 | 1968 | 2268.42 | 2268.42
Release Pre-Production Specs | 2021-08-17 13:12 | 6 | 2021-08-25 13:12 | 125 | Complete | 4920 | 4920 | 1 | 1 | 4920 | 5892 | 5892
PM Period 5 | 2021-08-09 08:12 | 17 | 2021-09-01 08:12 | 131 | Complete | 11760 | 11760 | 1 | 1 | 11760 | 13260 | 13260
Milestone 5 | 2021-09-01 08:12 | 0 | 2021-09-01 08:12 | 114 | Complete | 0 | 0 | 1 | 1 | 0 | 4851 | 4851
Identify Vendors | 2021-09-01 08:12 | 4.5 | 2021-09-07 13:12 | 114 | Complete | 2800 | 2800 | 1 | 1 | 2800 | 3528 | 3528
Develop and Issue RFQ | 2021-09-07 13:12 | 3.88 | 2021-09-13 09:02 | 110 | Complete | 2400 | 2400 | 1 | 1 | 2400 | 3041.92 | 3041.92
Build Functional Model | 2021-09-01 08:12 | 11.25 | 2021-09-16 10:12 | 114 | Complete | 8856 | 8856 | 1 | 1 | 8856 | 11047.5 | 11047.5
Evaluate Design Specs | 2021-09-01 08:12 | 14.88 | 2021-09-21 16:14 | 114 | Complete | 6000 | 6000 | 1 | 1 | 6000 | 8928 | 8928
PM Period 6 | 2021-09-01 08:12 | 10.25 | 2021-09-15 10:12 | 114 | Complete | 7056 | 7056 | 1 | 1 | 7056 | 7995 | 7995
Milestone 6 | 2021-09-21 16:14 | 0 | 2021-09-21 16:14 | 100 | Complete | 0 | 0 | 1 | 1 | 0 | 4638 | 4638
Issue Sample | 2021-09-21 16:14 | 7.5 | 2021-10-01 11:14 | 100 | Complete | 3000 | 3000 | 1 | 1 | 3000 | 4500 | 4500
Perform Supplier Process Capability | 2021-10-01 11:14 | 17.13 | 2021-10-26 13:17 | 92 | Complete | 6608 | 6608 | 1 | 1 | 6608 | 9250 | 9250
Develop Testing Protocol for Prototype | 2021-09-21 16:14 | 10.25 | 2021-10-06 09:14 | 100 | Complete | 3520 | 3520 | 1 | 1 | 3520 | 4530.5 | 4530.5
PM Period 7 | 2021-09-21 16:14 | 12.5 | 2021-10-08 11:14 | 100 | Complete | 8624 | 8624 | 1 | 1 | 8624 | 9750 | 9750
Milestone 7 | 2021-09-21 16:14 | 0 | 2021-09-21 16:14 | 100 | Complete | 0 | 0 | 1 | 1 | 0 | 4449 | 4449
Approve Sample Parts | 2021-10-26 13:17 | 10.13 | 2021-11-09 14:19 | 75 | Complete | 4352 | 4352 | 1 | 1 | 4352 | 6078 | 6078
Design Validation Activities | 2021-11-12 10:17 | 3.06 | 2021-11-16 16:02 | 62 | Complete | 2200 | 2200 | 1 | 1 | 2200 | 3188.5 | 3188.5
Test Prototype | 2021-10-26 13:17 | 12.75 | 2021-11-12 10:17 | 75 | Complete | 6000 | 6000 | 1 | 1 | 6000 | 5635.52 | 5635.52
Process Engineering Plan | 2021-10-26 13:17 | 17.63 | 2021-11-19 09:19 | 75 | Complete | 6000 | 6000 | 1 | 1 | 6000 | 7811.1 | 7811.1
Show Functional Model at Trade Show | 2021-11-01 08:00 | 3.25 | 2021-11-04 10:00 | 71 | Complete | 2352 | 2352 | 1 | 1 | 2352 | 2535 | 2535
PM Period 8 | 2021-10-26 13:17 | 3.38 | 2021-10-29 16:19 | 75 | Complete | 2352 | 2352 | 1 | 1 | 2352 | 2636.4 | 2636.4
Milestone 8 | 2021-11-19 09:19 | 0 | 2021-11-19 09:19 | 57 | Complete | 0 | 0 | 1 | 1 | 0 | 40 | 40
Validation Design Review | 2021-11-19 09:19 | 4.75 | 2021-11-25 16:19 | 57 | Complete | 1968 | 1968 | 1 | 1 | 1968 | 2565 | 2565
Approve Model Design | 2021-11-25 16:19 | 5.13 | 2021-12-03 08:22 | 53 | Complete | 1968 | 1968 | 1 | 1 | 1968 | 2267.46 | 2267.46
Evaluate Test Results | 2021-11-19 09:19 | 7.38 | 2021-11-30 13:22 | 57 | Complete | 3600 | 3600 | 1 | 1 | 3600 | 4428 | 4428
PM Period 9 | 2021-11-19 09:19 | 4.63 | 2021-11-25 15:22 | 57 | Complete | 3136 | 3136 | 1 | 1 | 3136 | 3611.4 | 3611.4
Milestone 9 | 2021-12-03 08:22 | 0 | 2021-12-03 08:22 | 47 | Complete | 0 | 0 | 1 | 1 | 0 | 240 | 240
Qualify Supplier | 2021-12-03 08:22 | 12.5 | 2021-12-21 13:22 | 47 | Complete | 6000 | 6000 | 1 | 1 | 6000 | 7500 | 7500
Design Transfer Activities | 2021-12-03 08:22 | 8.25 | 2021-12-15 10:22 | 47 | Complete | 4200 | 4200 | 1 | 1 | 4200 | 4455 | 4455
Product Release Meetings | 2021-12-15 10:22 | 3.38 | 2021-12-20 14:24 | 39 | Complete | 3000 | 3000 | 1 | 1 | 3000 | 2636 | 2636
Develop Production Plan | 2021-12-03 08:22 | 8.25 | 2021-12-15 10:22 | 47 | Complete | 2400 | 2400 | 1 | 1 | 2400 | 3646.5 | 3646.5
PM Period 10 | 2021-12-03 08:22 | 5.63 | 2021-12-10 14:24 | 47 | Complete | 3920 | 3920 | 1 | 1 | 3920 | 4391.4 | 4391.4
Milestone 10 | 2021-12-21 13:22 | 0 | 2021-12-21 13:22 | 35 | Complete | 0 | 0 | 1 | 1 | 0 | 40 | 40
Assess RFQ Responses | 2021-12-21 13:22 | 6.06 | 2021-12-29 13:50 | 35 | Complete | 6000 | 6000 | 1 | 1 | 6000 | 6908.4 | 6908.4
Develop Production Control Plan | 2021-12-21 13:22 | 11.13 | 2022-01-05 14:24 | 35 | Complete | 3400 | 3400 | 1 | 1 | 3400 | 4919.46 | 4919.46
Approve Production Parts | 2022-01-05 14:24 | 3.31 | 2022-01-10 16:53 | 24 | Complete | 2000 | 2000 | 1 | 1 | 2000 | 3250.42 | 3250.42
Contracting for Deliveries | 2022-01-10 16:53 | 5.13 | 2022-01-18 08:55 | 21 | Complete | 3200 | 3200 | 1 | 1 | 3200 | 5037.66 | 5037.66
PM Period 11 | 2021-12-21 13:22 | 14.75 | 2022-01-11 10:22 | 35 | Complete | 5720 | 5720 | 1 | 1 | 5720 | 11505 | 11505
Milestone 11 | 2022-01-18 08:55 | 0 | 2022-01-18 08:55 | 15 | Complete | 0 | 0 | 1 | 1 | 0 | 40 | 40
Submit Production Purchase Order | 2022-01-18 08:55 | 1.31 | 2022-01-19 11:24 | 15 | Complete | 800 | 800 | 1 | 1 | 800 | 1286.42 | 1286.42
Production Pilot Test | 2022-01-19 11:24 | 3.19 | 2022-01-24 13:55 | 14 | Complete | 2000 | 2000 | 1 | 1 | 2000 | 3132.58 | 3132.58
Debugging Production System | 2022-01-24 13:55 | 2.44 | 2022-01-27 08:26 | 11 | Complete | 1600 | 1600 | 1 | 1 | 1600 | 2396.08 | 2396.08
Production Release | 2022-01-27 08:26 | 2 | 2022-01-31 08:26 | 8 | Complete | 1200 | 1200 | 1 | 1 | 1200 | 1964 | 1964
Product Launch | 2022-02-02 11:58 | 3.38 | 2022-02-07 16:00 | 4 | Complete | 1512 | 1512 | 1 | 1 | 1512 | 2636.4 | 2636.4
PM Period 12 | 2022-01-18 08:55 | 11.38 | 2022-02-02 11:58 | 15 | Complete | 4400 | 4400 | 1 | 1 | 4400 | 8876.4 | 8876.4
Milestone 12 | 2022-02-07 16:00 | 0 | 2022-02-07 16:00 | 1 | Complete | 0 | 0 | 1 | 1 | 0 | 0 | 0
Totals | [6 empty] | 296072 |  |  | 296072 |  | 393417.71
CPI | 0.7526
SPI | 1
ETC | 0
EAC | 393417.71
Formulas:
Network Days to Analysis Date = NETWORKDAYS([Real Start Date],D3)