## Period 1
Period 1 |  |  | Analysis Date at 17:00 | Start of Work Day |  |  | End of Work Day |  | Milestone costs assumed to take place at start of period
|  |  | 2021-05-05 | 8:00 |  |  | 17:00
Task | Real Start Date | Real Duration | Real Duration hh:mm:ss | Real End Date | Network Days to Analysis Date | Complete/Busy | Full Budget | Budget at Analysis Date | %Sched Completion | Planned Value | %Actual Completion | Earned Value | Actual Cost | Actual Cost at Analysis Date | Planned Start Date | Network Days to Analysis Date | Planned Duration
Evaluate Market | 2021-03-31 08:00 | 6.69 | 60:13 | 2021-04-08 14:13 | 26 | Complete | 7728 | 7728 | 1 | 7728 | 1 | 7728 | 8563.2 | 8563.2
Develop Business Opportunity | 2021-04-08 14:12 | 8.06 | 72:32 | 2021-04-20 14:44 | 20 | Complete | 9016 | 9016 | 1 | 9016 | 1 | 9016 | 10316.8 | 10316.8
Customer Preference Study | 2021-04-20 14:44 | 12.13 | 109:10 | 2021-05-06 15:54 | 12 | Busy | 13524 | 13524 | 1 | 13524 | 0.92 | 12442.08 | 15526.4 | 14284.288
Business Evaluation (NPV, etc.) | 2021-05-06 15:54 | 2.38 | 21:25 | 2021-05-11 10:19 | -2 | Busy | 2576 | 2576 | 1 | 2576 | 0 | 0 | 3046 | 0
PM Period 1 | 2021-03-31 08:00 | 18.06 | 162:32 | 2021-04-26 08:32 | 26 | Complete | 12300 | 12300 | 1 | 12300 | 1 | 12300 | 17771.04 | 17771.04
Milestone 1 | 2021-05-11 10:19 | 0 | 0 | 2021-05-11 10:19 | -5 | Busy | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0
Design and Development Plan | 2021-05-11 10:19 | 3.88 | 34:55 | 2021-05-17 09:14 | -5 | Busy | 2352 | 783.9216 | 0.3333 | 261.2811 | 0 | 0 | 3585.12 | 0 | 2021-05-05 | 1 | 3
Develop Prelim Marketing Plan | 2021-05-11 10:19 | 2.81 | 25:17 | 2021-05-14 08:36 | -5 | Busy | 3220 | 1288 | 0.4 | 515.2 | 0 | 0 | 3596.8 | 0 | 2021-05-05 | 1 | 2.5
PM Period 2 | 2021-05-11 10:19 | 10.06 | 90:32 | 2021-05-25 10:51 | -5 | Busy | 6888 | 984.2952 | 0.1429 | 140.6558 | 0 | 0 | 9889.04 | 0 | 2021-05-05 | 1 | 7
Totals | [7 empty] | 48200.2168 |  | 46061.1369 |  | 41486.08 |  | 50935.328
CPI | 0.8145
SPI | 0.9007
ETC | 8243.2619
EAC | 59178.5899
Formulas:
Start of Work Day = WORKDAY([Real Start Date],CEILING(([Analysis Date at 17:00]+MOD([Real Start Date],1)-F3)/(I3-F3),1)-1)+MOD([Real Start Date],1)+[Analysis Date at 17:00]-CEILING(MOD([Real Start Date],1)+[Analysis Date at 17:00]-F3,I3-F3)+I3-F3
Network Days to Analysis Date = NETWORKDAYS([Real Start Date],E3)
Network Days to Analysis Date = NETWORKDAYS([Planned Start Date],E3)
Note on B2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Tasks not related to this period might be shown here, this is because they were scheduled to be started by the analysis date. They are included to ensure the CPI and SPI are correct.
Note on E3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: All tasks that should have started before this date are shown on this sheet to esnure the CPI and SPI are correct. The analysis date is obtained from the end date of the critical path of the period in question.
Note on C5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: From Sim4
Note on D5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: From Sim4
Note on E5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: From Sim4, calculated from real duration
Note on F5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: From Sim4. Yellow Date is the end of the period. Used to determine analysis date.
Note on G5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Used to calculate if task is either partially complete, fully complete, or not even started by analysis date. Numbers that are negative and red mean task hasn't even started by Analysis Date.
Note on I5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Full budget from baseline plan
Note on J5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Budget allocated at analysis date. Calculated by multiplying the shceduled completion with the full budget.
Note on K5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Scheduled completion from baseline plan. For tasks that are in progress and not fully complete, more information on the right is used to calculate this percentage.
Note on L5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Calculated by multiplying scheduled completion and the budget at the analysis date.
Note on M5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Completion according to Sim4. Tasks that are at 0 hasn't started yet.
Note on N5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Calculated by multiplying the actual completion with the budget at analysis date.
Note on O5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: From Sim4
Note on P5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Actual completion times actual cost

## Period 2
Period 2 |  | Analysis Date at 17:00
2021-05-31
Task | Real Start Date | Real Duration | Real End Date | Network Days to Analysis Date | Complete/Busy | Full Budget | Budget at Analysis Date | %Sched Completion | Planned Value | %Actual Completion | Earned Value | Actual Cost | Actual Cost at Analysis Date | Planned Start Date | Network Days to Analysis Date | Planned Duration
Evaluate Market | 2021-03-31 09:00 | 6.69 | 2021-04-08 15:31 | 44 | Complete | 7728 | 7728 | 1 | 7728 | 1 | 7728 | 8563.2 | 8563.2
Develop Business Opportunity | 2021-04-08 15:31 | 8.06 | 2021-04-20 16:00 | 38 | Complete | 9016 | 9016 | 1 | 9016 | 1 | 9016 | 10316.8 | 10316.8
Customer Preference Study | 2021-04-20 16:00 | 12.13 | 2021-05-07 08:02 | 30 | Complete | 13524 | 13524 | 1 | 13524 | 1 | 13524 | 14240 | 14240
Business Evaluation (NPV, etc.) | 2021-05-07 08:02 | 2.38 | 2021-05-11 11:05 | 17 | Complete | 2576 | 2576 | 1 | 2576 | 1 | 2576 | 4973 | 4973
PM Period 1 | 2021-03-31 09:00 | 18.06 | 2021-04-26 09:29 | 44 | Complete | 12300 | 12300 | 1 | 12300 | 1 | 12300 | 17771.04 | 17771.04
Milestone 1 | 2021-05-11 11:05 | 0 | 2021-05-11 11:05 | 15 | Complete | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0
Design and Development Plan | 2021-05-11 11:05 | 3.88 | 2021-05-17 10:07 | 15 | Complete | 2352 | 2352 | 1 | 2352 | 1 | 2352 | 3585.12 | 3585.12
Design Specs | 2021-05-17 10:07 | 13.75 | 2021-06-04 08:07 | 11 | Busy | 8624 | 8624 | 1 | 8624 | 0.71 | 6123.04 | 12705 | 9020.55
Develop Prelim Marketing Plan | 2021-05-11 11:05 | 2.81 | 2021-05-14 09:34 | 15 | Complete | 3220 | 3220 | 1 | 3220 | 1 | 3220 | 3596.8 | 3596.8
Develop Marketing Program | 2021-05-14 09:34 | 8.44 | 2021-05-26 14:05 | 12 | Complete | 9660 | 9660 | 1 | 9660 | 1 | 9660 | 10803.2 | 10803.2
PM Period 2 | 2021-05-11 11:05 | 10.06 | 2021-05-25 11:34 | 15 | Complete | 6888 | 6888 | 1 | 6888 | 1 | 6888 | 9889.04 | 9889.04
Milestone 2 | 2021-06-04 08:07 | 0 | 2021-06-04 08:07 | -5 | Busy | 0 | 0 | 1 | 0 | 0 | 0 | 5000 | 0
Identify Testing Requirements | 2021-06-04 08:07 | 6.25 | 2021-06-14 10:07 | -5 | Busy | 3920 | 3920 | 1 | 3920 | 0 | 0 | 5775 | 0 | 2021-05-25 | 5 | 5
Risk Analysis | 2021-06-14 10:07 | 7.06 | 2021-06-23 10:36 | -11 | Busy | 3920 | 0 | 0 | 0 | 0 | 0 | 6523.44 | 0
Train Sales Team | 2021-06-04 08:07 | 24.88 | 2021-07-08 16:10 | -5 | Busy | 11088 | 2520.3024 | 0.2273 | 572.8647 | 0 | 0 | 12440 | 0 | 2021-05-25 | 5 | 22
Advertising Campaign | 2021-06-04 08:07 | 31.38 | 2021-07-19 11:10 | -5 | Busy | 21952 | 3920.6272 | 0.1786 | 700.224 | 0 | 0 | 24476.4 | 0 | 2021-05-25 | 5 | 28
PM Period 3 | 2021-06-04 08:07 | 10.13 | 2021-06-18 09:10 | -5 | Busy | 6888 | 4920.0984 | 0.7143 | 3514.4263 | 0 | 0 | 9967.92 | 0 | 2021-05-25 | 5 | 7
Milestone 3 | 2021-07-19 11:10 | 0 | 2021-07-19 11:10 | -36 | Busy | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0
Totals | [6 empty] | 91169.028 |  | 84595.515 |  | 73387.04 |  | 92758.75
CPI | 0.7912
SPI | 0.8675
ETC | 22474.7068
EAC | 115233.4568
Formulas:
Network Days to Analysis Date = NETWORKDAYS([Real Start Date],D3)
Network Days to Analysis Date = NETWORKDAYS([Planned Start Date],D3)

## Period 3
Period 3 |  | Analysis Date at 17:00
2021-07-13
Task | Real Start Date | Real Duration | Real End Date | Network Days to Analysis Date | Complete/Busy | Full Budget | Budget at Analysis Date | %Sched Completion | Planned Value | %Actual Completion | Earned Value | Actual Cost | Actual Cost at Analysis Date | Planned Start Date | Network Days to Analysis Date | Planned Duration
Evaluate Market | 2021-03-31 09:00 | 6.69 | 2021-04-08 15:31 | 75 | Complete | 7728 | 7728 | 1 | 7728 | 1 | 7728 | 8563.2 | 8563.2
Develop Business Opportunity | 2021-04-08 15:31 | 8.06 | 2021-04-20 16:00 | 69 | Complete | 9016 | 9016 | 1 | 9016 | 1 | 9016 | 10316.8 | 10316.8
Customer Preference Study | 2021-04-20 16:00 | 12.13 | 2021-05-07 08:02 | 61 | Complete | 13524 | 13524 | 1 | 13524 | 1 | 13524 | 14240 | 14240
Business Evaluation (NPV, etc.) | 2021-05-07 08:02 | 2.38 | 2021-05-11 11:05 | 48 | Complete | 2576 | 2576 | 1 | 2576 | 1 | 2576 | 4973 | 4973
PM Period 1 | 2021-03-31 09:00 | 18.06 | 2021-04-26 09:29 | 75 | Complete | 12300 | 12300 | 1 | 12300 | 1 | 12300 | 17771.04 | 17771.04
Milestone 1 | 2021-05-11 11:05 | 0 | 2021-05-11 11:05 | 46 | Complete | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0
Design and Development Plan | 2021-05-11 11:05 | 3.88 | 2021-05-17 10:07 | 46 | Complete | 2352 | 2352 | 1 | 2352 | 1 | 2352 | 3585.12 | 3585.12
Design Specs | 2021-05-17 10:07 | 13.75 | 2021-06-04 08:07 | 42 | Complete | 8624 | 8624 | 1 | 8624 | 1 | 8624 | 12705 | 12705
Develop Prelim Marketing Plan | 2021-05-11 11:05 | 2.81 | 2021-05-14 09:34 | 46 | Complete | 3220 | 3220 | 1 | 3220 | 1 | 3220 | 3596.8 | 3596.8
Develop Marketing Program | 2021-05-14 09:34 | 8.44 | 2021-05-26 14:05 | 43 | Complete | 9660 | 9660 | 1 | 9660 | 1 | 9660 | 10803.2 | 10803.2
PM Period 2 | 2021-05-11 11:05 | 10.06 | 2021-05-25 11:34 | 46 | Complete | 6888 | 6888 | 1 | 6888 | 1 | 6888 | 9889.04 | 9889.04
Milestone 2 | 2021-06-04 08:07 | 0 | 2021-06-04 08:07 | 28 | Complete | 0 | 0 | 1 | 0 | 1 | 0 | 5000 | 5000
Identify Testing Requirements | 2021-06-04 08:07 | 6.25 | 2021-06-14 10:07 | 28 | Complete | 3920 | 3920 | 1 | 3920 | 1 | 3920 | 5775 | 5775
Risk Analysis | 2021-06-14 10:07 | 7.06 | 2021-06-23 10:36 | 22 | Complete | 3920 | 3920 | 1 | 3920 | 1 | 3920 | 6523.44 | 6523.44
Train Sales Team | 2021-06-04 08:07 | 24.88 | 2021-07-08 16:10 | 28 | Complete | 11088 | 11088 | 1 | 11088 | 1 | 11088 | 12440 | 12440
Advertising Campaign | 2021-06-04 08:07 | 31.38 | 2021-07-19 11:10 | 28 | Busy | 21952 | 21952 | 1 | 21952 | 0.89 | 19537.28 | 24476.4 | 21783.996
PM Period 3 | 2021-06-04 08:07 | 10.13 | 2021-06-18 09:10 | 28 | Complete | 6888 | 6888 | 1 | 6888 | 1 | 6888 | 9967.92 | 9967.92
Milestone 3 | 2021-07-19 11:10 | 0 | 2021-07-19 11:10 | -5 | Busy | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0
Design Labelling | 2021-07-14 08:07 | 3.25 | 2021-07-19 10:07 | -2 | Busy | 1960 | 1960 | 1 | 1960 | 0 | 0 | 3003 | 0
Approve Design | 2021-07-19 10:07 | 2.63 | 2021-07-21 16:10 | -5 | Busy | 1568 | 1568 | 1 | 1568 | 0 | 0 | 2430.12 | 0
Initial Engineering Specs | 2021-07-21 16:10 | 2.88 | 2021-07-26 15:12 | -7 | Busy | 2460 | 2460 | 1 | 2460 | 0 | 0 | 2839.68 | 0
PM Period 4 | 2021-07-19 11:10 | 14.63 | 2021-08-09 08:12 | -5 | Busy | 10192 | 6272.1568 | 0.6154 | 3859.8853 | 0 | 0 | 11411.4 | 0 | 2021-07-02 | 8 | 13
Milestone 4 | 2021-08-09 08:12 | 0 | 2021-08-09 08:12 | -20 | Busy | 0 | 0 | 1 | 0 | 0 | 0 | -50000 | 0
Totals | [6 empty] | 135916.1568 |  | 133503.8853 |  | 121241.28 |  | 157933.556
CPI | 0.7677
SPI | 0.9081
ETC | 19115.3794
EAC | 177048.9354
Formulas:
Network Days to Analysis Date = NETWORKDAYS([Real Start Date],D3)
Network Days to Analysis Date = NETWORKDAYS([Planned Start Date],D3)

## Period 4
Period 4 |  | Analysis Date at 17:00
2021-08-03
Task | Real Start Date | Real Duration | Real End Date | Network Days to Analysis Date | Complete/Busy | Full Budget | Budget at Analysis Date | %Sched Completion | Planned Value | %Actual Completion | Earned Value | Actual Cost | Actual Cost at Analysis Date | Planned Start Date | Network Days to Analysis Date | Planned Duration
Evaluate Market | 2021-03-31 09:00 | 6.69 | 2021-04-08 15:31 | 90 | Complete | 7728 | 7728 | 1 | 7728 | 1 | 7728 | 8563.2 | 8563.2
Develop Business Opportunity | 2021-04-08 15:31 | 8.06 | 2021-04-20 16:00 | 84 | Complete | 9016 | 9016 | 1 | 9016 | 1 | 9016 | 10316.8 | 10316.8
Customer Preference Study | 2021-04-20 16:00 | 12.13 | 2021-05-07 08:02 | 76 | Complete | 13524 | 13524 | 1 | 13524 | 1 | 13524 | 14240 | 14240
Business Evaluation (NPV, etc.) | 2021-05-07 08:02 | 2.38 | 2021-05-11 11:05 | 63 | Complete | 2576 | 2576 | 1 | 2576 | 1 | 2576 | 4973 | 4973
PM Period 1 | 2021-03-31 09:00 | 18.06 | 2021-04-26 09:29 | 90 | Complete | 12300 | 12300 | 1 | 12300 | 1 | 12300 | 17771.04 | 17771.04
Milestone 1 | 2021-05-11 11:05 | 0 | 2021-05-11 11:05 | 61 | Complete | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0
Design and Development Plan | 2021-05-11 11:05 | 3.88 | 2021-05-17 10:07 | 61 | Complete | 2352 | 2352 | 1 | 2352 | 1 | 2352 | 3585.12 | 3585.12
Design Specs | 2021-05-17 10:07 | 13.75 | 2021-06-04 08:07 | 57 | Complete | 8624 | 8624 | 1 | 8624 | 1 | 8624 | 12705 | 12705
Develop Prelim Marketing Plan | 2021-05-11 11:05 | 2.81 | 2021-05-14 09:34 | 61 | Complete | 3220 | 3220 | 1 | 3220 | 1 | 3220 | 3596.8 | 3596.8
Develop Marketing Program | 2021-05-14 09:34 | 8.44 | 2021-05-26 14:05 | 58 | Complete | 9660 | 9660 | 1 | 9660 | 1 | 9660 | 10803.2 | 10803.2
PM Period 2 | 2021-05-11 11:05 | 10.06 | 2021-05-25 11:34 | 61 | Complete | 6888 | 6888 | 1 | 6888 | 1 | 6888 | 9889.04 | 9889.04
Milestone 2 | 2021-06-04 08:07 | 0 | 2021-06-04 08:07 | 43 | Complete | 0 | 0 | 1 | 0 | 1 | 0 | 5000 | 5000
Identify Testing Requirements | 2021-06-04 08:07 | 6.25 | 2021-06-14 10:07 | 43 | Complete | 3920 | 3920 | 1 | 3920 | 1 | 3920 | 5775 | 5775
Risk Analysis | 2021-06-14 10:07 | 7.06 | 2021-06-23 10:36 | 37 | Complete | 3920 | 3920 | 1 | 3920 | 1 | 3920 | 6523.44 | 6523.44
Train Sales Team | 2021-06-04 08:07 | 24.88 | 2021-07-08 16:10 | 43 | Complete | 11088 | 11088 | 1 | 11088 | 1 | 11088 | 12440 | 12440
Advertising Campaign | 2021-06-04 08:07 | 31.38 | 2021-07-19 11:10 | 43 | Complete | 21952 | 21952 | 1 | 21952 | 1 | 21952 | 24476.4 | 24476.4
PM Period 3 | 2021-06-04 08:07 | 10.13 | 2021-06-18 09:10 | 43 | Complete | 6888 | 6888 | 1 | 6888 | 1 | 6888 | 9967.92 | 9967.92
Milestone 3 | 2021-07-19 11:10 | 0 | 2021-07-19 11:10 | 12 | Complete | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0
Design Labelling | 2021-07-14 08:07 | 3.25 | 2021-07-19 10:07 | 15 | Complete | 1960 | 1960 | 1 | 1960 | 1 | 1960 | 3003 | 3003
Approve Design | 2021-07-19 10:07 | 2.63 | 2021-07-21 16:10 | 12 | Complete | 1568 | 1568 | 1 | 1568 | 1 | 1568 | 2430.12 | 2430.12
Initial Engineering Specs | 2021-07-21 16:10 | 2.88 | 2021-07-26 15:12 | 10 | Complete | 2460 | 2460 | 1 | 2460 | 1 | 2460 | 2839.68 | 2839.68
PM Period 4 | 2021-07-19 11:10 | 14.63 | 2021-08-09 08:12 | 12 | Busy | 10192 | 10192 | 1 | 10192 | 0.79 | 8051.68 | 11411.4 | 9015.006
Milestone 4 | 2021-08-09 08:12 | 0 | 2021-08-09 08:12 | -5 | Busy | 0 | 0 | 1 | 0 | 0 | 0 | -50000 | 0
Design Verification Activities | 2021-08-09 08:12 | 4.19 | 2021-08-13 09:43 | -5 | Busy | 3444 | 3444 | 1 | 3444 | 0 | 0 | 4131.34 | 0
Verification Design Review | 2021-08-13 09:43 | 2.31 | 2021-08-17 13:12 | -9 | Busy | 1968 | 1968 | 1 | 1968 | 0 | 0 | 2277.66 | 0
Release Pre-Production Specs | 2021-08-17 13:12 | 6 | 2021-08-25 13:12 | -11 | Busy | 4920 | 3280.164 | 0.6667 | 2186.8853 | 0 | 0 | 5916 | 0 | 2021-07-29 | 4 | 6
PM Period 5 | 2021-08-09 08:12 | 17 | 2021-09-01 08:12 | -5 | Busy | 11760 | 7840.392 | 0.6667 | 5227.1893 | 0 | 0 | 13260 | 0 | 2021-07-21 | 10 | 15
Milestone 5 | 2021-09-01 08:12 | 0 | 2021-09-01 08:12 | -22 | Busy | 0 | 0 | 0 | 0 | 0 | 0 | 15000 | 0
Totals | [6 empty] | 156368.556 |  | 152662.0747 |  | 137695.68 |  | 177913.766
CPI | 0.7739
SPI | 0.902
ETC | 24128.2801
EAC | 202042.0461
Formulas:
Network Days to Analysis Date = NETWORKDAYS([Real Start Date],D3)
Network Days to Analysis Date = NETWORKDAYS([Planned Start Date],D3)

## Period 5
Period 5 |  | Analysis Date at 17:00
2021-08-26
Task | Real Start Date | Real Duration | Real End Date | Network Days to Analysis Date | Complete/Busy | Full Budget | Budget at Analysis Date | %Sched Completion | Planned Value | %Actual Completion | Earned Value | Actual Cost | Actual Cost at Analysis Date | Planned Start Date | Network Days to Analysis Date | Planned Duration
Evaluate Market | 2021-03-31 09:00 | 6.69 | 2021-04-08 15:31 | 107 | Complete | 7728 | 7728 | 1 | 7728 | 1 | 7728 | 8563.2 | 8563.2
Develop Business Opportunity | 2021-04-08 15:31 | 8.06 | 2021-04-20 16:00 | 101 | Complete | 9016 | 9016 | 1 | 9016 | 1 | 9016 | 10316.8 | 10316.8
Customer Preference Study | 2021-04-20 16:00 | 12.13 | 2021-05-07 08:02 | 93 | Complete | 13524 | 13524 | 1 | 13524 | 1 | 13524 | 14240 | 14240
Business Evaluation (NPV, etc.) | 2021-05-07 08:02 | 2.38 | 2021-05-11 11:05 | 80 | Complete | 2576 | 2576 | 1 | 2576 | 1 | 2576 | 4973 | 4973
PM Period 1 | 2021-03-31 09:00 | 18.06 | 2021-04-26 09:29 | 107 | Complete | 12300 | 12300 | 1 | 12300 | 1 | 12300 | 17771.04 | 17771.04
Milestone 1 | 2021-05-11 11:05 | 0 | 2021-05-11 11:05 | 78 | Complete | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0
Design and Development Plan | 2021-05-11 11:05 | 3.88 | 2021-05-17 10:07 | 78 | Complete | 2352 | 2352 | 1 | 2352 | 1 | 2352 | 3585.12 | 3585.12
Design Specs | 2021-05-17 10:07 | 13.75 | 2021-06-04 08:07 | 74 | Complete | 8624 | 8624 | 1 | 8624 | 1 | 8624 | 12705 | 12705
Develop Prelim Marketing Plan | 2021-05-11 11:05 | 2.81 | 2021-05-14 09:34 | 78 | Complete | 3220 | 3220 | 1 | 3220 | 1 | 3220 | 3596.8 | 3596.8
Develop Marketing Program | 2021-05-14 09:34 | 8.44 | 2021-05-26 14:05 | 75 | Complete | 9660 | 9660 | 1 | 9660 | 1 | 9660 | 10803.2 | 10803.2
PM Period 2 | 2021-05-11 11:05 | 10.06 | 2021-05-25 11:34 | 78 | Complete | 6888 | 6888 | 1 | 6888 | 1 | 6888 | 9889.04 | 9889.04
Milestone 2 | 2021-06-04 08:07 | 0 | 2021-06-04 08:07 | 60 | Complete | 0 | 0 | 1 | 0 | 1 | 0 | 5000 | 5000
Identify Testing Requirements | 2021-06-04 08:07 | 6.25 | 2021-06-14 10:07 | 60 | Complete | 3920 | 3920 | 1 | 3920 | 1 | 3920 | 5775 | 5775
Risk Analysis | 2021-06-14 10:07 | 7.06 | 2021-06-23 10:36 | 54 | Complete | 3920 | 3920 | 1 | 3920 | 1 | 3920 | 6523.44 | 6523.44
Train Sales Team | 2021-06-04 08:07 | 24.88 | 2021-07-08 16:10 | 60 | Complete | 11088 | 11088 | 1 | 11088 | 1 | 11088 | 12440 | 12440
Advertising Campaign | 2021-06-04 08:07 | 31.38 | 2021-07-19 11:10 | 60 | Complete | 21952 | 21952 | 1 | 21952 | 1 | 21952 | 24476.4 | 24476.4
PM Period 3 | 2021-06-04 08:07 | 10.13 | 2021-06-18 09:10 | 60 | Complete | 6888 | 6888 | 1 | 6888 | 1 | 6888 | 9967.92 | 9967.92
Milestone 3 | 2021-07-19 11:10 | 0 | 2021-07-19 11:10 | 29 | Complete | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0
Design Labelling | 2021-07-14 08:07 | 3.25 | 2021-07-19 10:07 | 32 | Complete | 1960 | 1960 | 1 | 1960 | 1 | 1960 | 3003 | 3003
Approve Design | 2021-07-19 10:07 | 2.63 | 2021-07-21 16:10 | 29 | Complete | 1568 | 1568 | 1 | 1568 | 1 | 1568 | 2430.12 | 2430.12
Initial Engineering Specs | 2021-07-21 16:10 | 2.88 | 2021-07-26 15:12 | 27 | Complete | 2460 | 2460 | 1 | 2460 | 1 | 2460 | 2839.68 | 2839.68
PM Period 4 | 2021-07-19 11:10 | 14.63 | 2021-08-09 08:12 | 29 | Complete | 10192 | 10192 | 1 | 10192 | 1 | 10192 | 11411.4 | 11411.4
Milestone 4 | 2021-08-09 08:12 | 0 | 2021-08-09 08:12 | 14 | Complete | 0 | 0 | 1 | 0 | 1 | 0 | -50000 | -50000
Design Verification Activities | 2021-08-09 08:12 | 4.19 | 2021-08-13 09:43 | 14 | Complete | 3444 | 3444 | 1 | 3444 | 1 | 3444 | 4131.34 | 4131.34
Verification Design Review | 2021-08-13 09:43 | 2.31 | 2021-08-17 13:12 | 10 | Complete | 1968 | 1968 | 1 | 1968 | 1 | 1968 | 2277.66 | 2277.66
Release Pre-Production Specs | 2021-08-17 13:12 | 6 | 2021-08-25 13:12 | 8 | Complete | 4920 | 4920 | 1 | 4920 | 1 | 4920 | 5916 | 5916
PM Period 5 | 2021-08-09 08:12 | 17 | 2021-09-01 08:12 | 14 | Busy | 11760 | 11760 | 1 | 11760 | 0.82 | 9643.2 | 13260 | 10873.2
Milestone 5 | 2021-09-01 08:12 | 0 | 2021-09-01 08:12 | -5 | Busy | 0 | 0 | 0 | 0 | 0 | 0 | 15000 | 0
Identify Vendors | 2021-09-01 08:12 | 4.5 | 2021-09-07 13:12 | -5 | Busy | 2800 | 2800 | 1 | 2800 | 0 | 0 | 3528 | 0
Develop and Issue RFQ | 2021-09-07 13:12 | 3.88 | 2021-09-13 09:02 | -9 | Busy | 2400 | 1999.92 | 0.8333 | 1666.5333 | 0 | 0 | 3041.92 | 0 | 2021-08-20 | 5 | 6
Build Functional Model | 2021-09-01 08:12 | 11.25 | 2021-09-16 10:12 | -5 | Busy | 8856 | 8856 | 1 | 8856 | 0 | 0 | 11092.5 | 0
Evaluate Design Specs | 2021-09-01 08:12 | 14.88 | 2021-09-21 16:14 | -5 | Busy | 6000 | 6000 | 1 | 6000 | 0 | 0 | 8928 | 0
PM Period 6 | 2021-09-01 08:12 | 10.25 | 2021-09-15 10:12 | -5 | Busy | 7056 | 7056 | 1 | 7056 | 0 | 0 | 7995 | 0
Milestone 6 | 2021-09-15 10:12 | 0 | 2021-09-15 10:12 | -15 | Busy | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Totals | [6 empty] | 188639.92 |  | 188306.5333 |  | 159811.2 |  | 153508.36
CPI | 1.0411
SPI | 0.8487
ETC | 27690.6349
EAC | 181198.9949
Formulas:
Network Days to Analysis Date = NETWORKDAYS([Real Start Date],D3)
Network Days to Analysis Date = NETWORKDAYS([Planned Start Date],D3)

## Period 6
Period 6 |  | Analysis Date at 17:00
2021-09-15
Task | Real Start Date | Real Duration | Real End Date | Network Days to Analysis Date | Complete/Busy | Full Budget | Budget at Analysis Date | %Sched Completion | Planned Value | %Actual Completion | Earned Value | Actual Cost | Actual Cost at Analysis Date | Planned Start Date | Network Days to Analysis Date | Planned Duration
Evaluate Market | 2021-03-31 09:00 | 6.69 | 2021-04-08 15:31 | 121 | Complete | 7728 | 7728 | 1 | 7728 | 1 | 7728 | 8563.2 | 8563.2
Develop Business Opportunity | 2021-04-08 15:31 | 8.06 | 2021-04-20 16:00 | 115 | Complete | 9016 | 9016 | 1 | 9016 | 1 | 9016 | 10316.8 | 10316.8
Customer Preference Study | 2021-04-20 16:00 | 12.13 | 2021-05-07 08:02 | 107 | Complete | 13524 | 13524 | 1 | 13524 | 1 | 13524 | 14240 | 14240
Business Evaluation (NPV, etc.) | 2021-05-07 08:02 | 2.38 | 2021-05-11 11:05 | 94 | Complete | 2576 | 2576 | 1 | 2576 | 1 | 2576 | 4973 | 4973
PM Period 1 | 2021-03-31 09:00 | 18.06 | 2021-04-26 09:29 | 121 | Complete | 12300 | 12300 | 1 | 12300 | 1 | 12300 | 17771.04 | 17771.04
Milestone 1 | 2021-05-11 11:05 | 0 | 2021-05-11 11:05 | 92 | Complete | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0
Design and Development Plan | 2021-05-11 11:05 | 3.88 | 2021-05-17 10:07 | 92 | Complete | 2352 | 2352 | 1 | 2352 | 1 | 2352 | 3585.12 | 3585.12
Design Specs | 2021-05-17 10:07 | 13.75 | 2021-06-04 08:07 | 88 | Complete | 8624 | 8624 | 1 | 8624 | 1 | 8624 | 12705 | 12705
Develop Prelim Marketing Plan | 2021-05-11 11:05 | 2.81 | 2021-05-14 09:34 | 92 | Complete | 3220 | 3220 | 1 | 3220 | 1 | 3220 | 3596.8 | 3596.8
Develop Marketing Program | 2021-05-14 09:34 | 8.44 | 2021-05-26 14:05 | 89 | Complete | 9660 | 9660 | 1 | 9660 | 1 | 9660 | 10803.2 | 10803.2
PM Period 2 | 2021-05-11 11:05 | 10.06 | 2021-05-25 11:34 | 92 | Complete | 6888 | 6888 | 1 | 6888 | 1 | 6888 | 9889.04 | 9889.04
Milestone 2 | 2021-06-04 08:07 | 0 | 2021-06-04 08:07 | 74 | Complete | 0 | 0 | 1 | 0 | 1 | 0 | 5000 | 5000
Identify Testing Requirements | 2021-06-04 08:07 | 6.25 | 2021-06-14 10:07 | 74 | Complete | 3920 | 3920 | 1 | 3920 | 1 | 3920 | 5775 | 5775
Risk Analysis | 2021-06-14 10:07 | 7.06 | 2021-06-23 10:36 | 68 | Complete | 3920 | 3920 | 1 | 3920 | 1 | 3920 | 6523.44 | 6523.44
Train Sales Team | 2021-06-04 08:07 | 24.88 | 2021-07-08 16:10 | 74 | Complete | 11088 | 11088 | 1 | 11088 | 1 | 11088 | 12440 | 12440
Advertising Campaign | 2021-06-04 08:07 | 31.38 | 2021-07-19 11:10 | 74 | Complete | 21952 | 21952 | 1 | 21952 | 1 | 21952 | 24476.4 | 24476.4
PM Period 3 | 2021-06-04 08:07 | 10.13 | 2021-06-18 09:10 | 74 | Complete | 6888 | 6888 | 1 | 6888 | 1 | 6888 | 9967.92 | 9967.92
Milestone 3 | 2021-07-19 11:10 | 0 | 2021-07-19 11:10 | 43 | Complete | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0
Design Labelling | 2021-07-14 08:07 | 3.25 | 2021-07-19 10:07 | 46 | Complete | 1960 | 1960 | 1 | 1960 | 1 | 1960 | 3003 | 3003
Approve Design | 2021-07-19 10:07 | 2.63 | 2021-07-21 16:10 | 43 | Complete | 1568 | 1568 | 1 | 1568 | 1 | 1568 | 2430.12 | 2430.12
Initial Engineering Specs | 2021-07-21 16:10 | 2.88 | 2021-07-26 15:12 | 41 | Complete | 2460 | 2460 | 1 | 2460 | 1 | 2460 | 2839.68 | 2839.68
PM Period 4 | 2021-07-19 11:10 | 14.63 | 2021-08-09 08:12 | 43 | Complete | 10192 | 10192 | 1 | 10192 | 1 | 10192 | 11411.4 | 11411.4
Milestone 4 | 2021-08-09 08:12 | 0 | 2021-08-09 08:12 | 28 | Complete | 0 | 0 | 1 | 0 | 1 | 0 | -50000 | -50000
Design Verification Activities | 2021-08-09 08:12 | 4.19 | 2021-08-13 09:43 | 28 | Complete | 3444 | 3444 | 1 | 3444 | 1 | 3444 | 4131.34 | 4131.34
Verification Design Review | 2021-08-13 09:43 | 2.31 | 2021-08-17 13:12 | 24 | Complete | 1968 | 1968 | 1 | 1968 | 1 | 1968 | 2277.66 | 2277.66
Release Pre-Production Specs | 2021-08-17 13:12 | 6 | 2021-08-25 13:12 | 22 | Complete | 4920 | 4920 | 1 | 4920 | 1 | 4920 | 5916 | 5916
PM Period 5 | 2021-08-09 08:12 | 17 | 2021-09-01 08:12 | 28 | Complete | 11760 | 11760 | 1 | 11760 | 1 | 11760 | 13260 | 13260
Milestone 5 | 2021-09-01 08:12 | 0 | 2021-09-01 08:12 | 11 | Complete | 0 | 0 | 1 | 0 | 1 | 0 | 15000 | 15000
Identify Vendors | 2021-09-01 08:12 | 4.5 | 2021-09-07 13:12 | 11 | Complete | 2800 | 2800 | 1 | 2800 | 1 | 2800 | 3528 | 3528
Develop and Issue RFQ | 2021-09-07 13:12 | 3.88 | 2021-09-13 09:02 | 7 | Complete | 2400 | 2400 | 1 | 2400 | 1 | 2400 | 3041.92 | 3041.92
Build Functional Model | 2021-09-01 08:12 | 11.25 | 2021-09-16 10:12 | 11 | Busy | 8856 | 8856 | 1 | 8856 | 1 | 8856 | 11092.5 | 11092.5
Evaluate Design Specs | 2021-09-01 08:12 | 14.88 | 2021-09-21 16:14 | 11 | Busy | 6000 | 6000 | 1 | 6000 | 0.74 | 4440 | 8928 | 6606.72
PM Period 6 | 2021-09-01 08:12 | 10.25 | 2021-09-15 10:12 | 11 | Complete | 7056 | 7056 | 1 | 7056 | 1 | 7056 | 7995 | 7995
Milestone 6 | 2021-09-21 16:14 | 0 | 2021-09-21 16:14 | -5 | Busy | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0
Issue Sample | 2021-09-21 16:14 | 7.5 | 2021-10-01 11:14 | -5 | Busy | 3000 | 3000 | 1 | 3000 | 0 | 0 | 4500 | 0
Perform Supplier Process Capability | 2021-10-01 11:14 | 17.13 | 2021-10-26 13:17 | -13 | Busy | 6608 | 6608 | 1 | 6608 | 0 | 0 | 7395.68 | 0
Develop Testing Protocol for Prototype | 2021-09-21 16:14 | 10.25 | 2021-10-06 09:14 | -5 | Busy | 3520 | 3520 | 1 | 3520 | 0 | 0 | 4530.5 | 0
PM Period 7 | 2021-09-21 16:14 | 12.5 | 2021-10-08 11:14 | -5 | Busy | 8624 | 8624 | 1 | 8624 | 0 | 0 | 9750 | 0
Milestone 7 | 2021-09-21 16:14 | 0 | 2021-09-21 16:14 | -5 | Busy | 0 | 0 | 1 | 0 | 0 | 0 | 35000 | 0
Approve Sample Parts | 2021-10-26 13:17 | 10.13 | 2021-11-09 14:19 | -30 | Busy | 4352 | 544 | 0.125 | 68 | 0 | 0 | 6078 | 0 | 2021-09-15 | 1 | 8
Design Validation Activities | 2021-11-12 10:17 | 3.06 | 2021-11-16 16:02 | -43 | Busy | 2200 | 440 | 0.2 | 88 | 0 | 0 | 5635.52 | 0 | 2021-09-15 | 1 | 5
Test Prototype | 2021-10-26 13:17 | 12.75 | 2021-11-12 10:17 | -30 | Busy | 6000 | 600 | 0.1 | 60 | 0 | 0 | 5635.5 | 0 | 2021-09-15 | 1 | 10
Process Engineering Plan | 2021-10-26 13:17 | 17.63 | 2021-11-19 09:19 | -30 | Busy | 6000 | 400.2 | 0.0667 | 26.6933 | 0 | 0 | 9590.72 | 0 | 2021-09-15 | 1 | 15
Show Functional Model at Trade Show | 2021-11-01 08:00 | 3.25 | 2021-11-04 10:00 | -34 | Busy | 2352 | 0 | 0 | 0 | 0 | 0 | 2535 | 0
PM Period 8 | 2021-10-26 13:17 | 3.38 | 2021-10-29 16:19 | -30 | Busy | 2352 | 783.9216 | 0.3333 | 261.2811 | 0 | 0 | 2636.4 | 0 | 2021-09-15 | 1 | 3
Milestone 8 | 2021-11-19 09:19 | 0 | 2021-11-19 09:19 | -48 | Busy | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Totals | [6 empty] | 213560.1216 |  | 211295.9744 |  | 187480 |  | 203159.3
CPI | 0.9228
SPI | 0.8873
ETC | 28261.9436
EAC | 231421.2436
Formulas:
Network Days to Analysis Date = NETWORKDAYS([Real Start Date],D3)
Network Days to Analysis Date = NETWORKDAYS([Planned Start Date],D3)

## Period 7
Period 6 |  | Analysis Date at 17:00
2021-10-20
Task | Real Start Date | Real Duration | Real End Date | Network Days to Analysis Date | Complete/Busy | Full Budget | Budget at Analysis Date | %Sched Completion | Planned Value | %Actual Completion | Earned Value | Actual Cost | Actual Cost at Analysis Date | Planned Start Date | Network Days to Analysis Date | Planned Duration
Evaluate Market | 2021-03-31 09:00 | 6.69 | 2021-04-08 15:31 | 146 | Complete | 7728 | 7728 | 1 | 7728 | 1 | 7728 | 8563.2 | 8563.2
Develop Business Opportunity | 2021-04-08 15:31 | 8.06 | 2021-04-20 16:00 | 140 | Complete | 9016 | 9016 | 1 | 9016 | 1 | 9016 | 10316.8 | 10316.8
Customer Preference Study | 2021-04-20 16:00 | 12.13 | 2021-05-07 08:02 | 132 | Complete | 13524 | 13524 | 1 | 13524 | 1 | 13524 | 14240 | 14240
Business Evaluation (NPV, etc.) | 2021-05-07 08:02 | 2.38 | 2021-05-11 11:05 | 119 | Complete | 2576 | 2576 | 1 | 2576 | 1 | 2576 | 4973 | 4973
PM Period 1 | 2021-03-31 09:00 | 18.06 | 2021-04-26 09:29 | 146 | Complete | 12300 | 12300 | 1 | 12300 | 1 | 12300 | 17771.04 | 17771.04
Milestone 1 | 2021-05-11 11:05 | 0 | 2021-05-11 11:05 | 117 | Complete | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0
Design and Development Plan | 2021-05-11 11:05 | 3.88 | 2021-05-17 10:07 | 117 | Complete | 2352 | 2352 | 1 | 2352 | 1 | 2352 | 3585.12 | 3585.12
Design Specs | 2021-05-17 10:07 | 13.75 | 2021-06-04 08:07 | 113 | Complete | 8624 | 8624 | 1 | 8624 | 1 | 8624 | 12705 | 12705
Develop Prelim Marketing Plan | 2021-05-11 11:05 | 2.81 | 2021-05-14 09:34 | 117 | Complete | 3220 | 3220 | 1 | 3220 | 1 | 3220 | 3596.8 | 3596.8
Develop Marketing Program | 2021-05-14 09:34 | 8.44 | 2021-05-26 14:05 | 114 | Complete | 9660 | 9660 | 1 | 9660 | 1 | 9660 | 10803.2 | 10803.2
PM Period 2 | 2021-05-11 11:05 | 10.06 | 2021-05-25 11:34 | 117 | Complete | 6888 | 6888 | 1 | 6888 | 1 | 6888 | 9889.04 | 9889.04
Milestone 2 | 2021-06-04 08:07 | 0 | 2021-06-04 08:07 | 99 | Complete | 0 | 0 | 1 | 0 | 1 | 0 | 5000 | 5000
Identify Testing Requirements | 2021-06-04 08:07 | 6.25 | 2021-06-14 10:07 | 99 | Complete | 3920 | 3920 | 1 | 3920 | 1 | 3920 | 5775 | 5775
Risk Analysis | 2021-06-14 10:07 | 7.06 | 2021-06-23 10:36 | 93 | Complete | 3920 | 3920 | 1 | 3920 | 1 | 3920 | 6523.44 | 6523.44
Train Sales Team | 2021-06-04 08:07 | 24.88 | 2021-07-08 16:10 | 99 | Complete | 11088 | 11088 | 1 | 11088 | 1 | 11088 | 12440 | 12440
Advertising Campaign | 2021-06-04 08:07 | 31.38 | 2021-07-19 11:10 | 99 | Complete | 21952 | 21952 | 1 | 21952 | 1 | 21952 | 24476.4 | 24476.4
PM Period 3 | 2021-06-04 08:07 | 10.13 | 2021-06-18 09:10 | 99 | Complete | 6888 | 6888 | 1 | 6888 | 1 | 6888 | 9967.92 | 9967.92
Milestone 3 | 2021-07-19 11:10 | 0 | 2021-07-19 11:10 | 68 | Complete | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0
Design Labelling | 2021-07-14 08:07 | 3.25 | 2021-07-19 10:07 | 71 | Complete | 1960 | 1960 | 1 | 1960 | 1 | 1960 | 3003 | 3003
Approve Design | 2021-07-19 10:07 | 2.63 | 2021-07-21 16:10 | 68 | Complete | 1568 | 1568 | 1 | 1568 | 1 | 1568 | 2430.12 | 2430.12
Initial Engineering Specs | 2021-07-21 16:10 | 2.88 | 2021-07-26 15:12 | 66 | Complete | 2460 | 2460 | 1 | 2460 | 1 | 2460 | 2839.68 | 2839.68
PM Period 4 | 2021-07-19 11:10 | 14.63 | 2021-08-09 08:12 | 68 | Complete | 10192 | 10192 | 1 | 10192 | 1 | 10192 | 11411.4 | 11411.4
Milestone 4 | 2021-08-09 08:12 | 0 | 2021-08-09 08:12 | 53 | Complete | 0 | 0 | 1 | 0 | 1 | 0 | -50000 | -50000
Design Verification Activities | 2021-08-09 08:12 | 4.19 | 2021-08-13 09:43 | 53 | Complete | 3444 | 3444 | 1 | 3444 | 1 | 3444 | 4131.34 | 4131.34
Verification Design Review | 2021-08-13 09:43 | 2.31 | 2021-08-17 13:12 | 49 | Complete | 1968 | 1968 | 1 | 1968 | 1 | 1968 | 2277.66 | 2277.66
Release Pre-Production Specs | 2021-08-17 13:12 | 6 | 2021-08-25 13:12 | 47 | Complete | 4920 | 4920 | 1 | 4920 | 1 | 4920 | 5916 | 5916
PM Period 5 | 2021-08-09 08:12 | 17 | 2021-09-01 08:12 | 53 | Complete | 11760 | 11760 | 1 | 11760 | 1 | 11760 | 13260 | 13260
Milestone 5 | 2021-09-01 08:12 | 0 | 2021-09-01 08:12 | 36 | Complete | 0 | 0 | 1 | 0 | 1 | 0 | 15000 | 15000
Identify Vendors | 2021-09-01 08:12 | 4.5 | 2021-09-07 13:12 | 36 | Complete | 2800 | 2800 | 1 | 2800 | 1 | 2800 | 3528 | 3528
Develop and Issue RFQ | 2021-09-07 13:12 | 3.88 | 2021-09-13 09:02 | 32 | Complete | 2400 | 2400 | 1 | 2400 | 1 | 2400 | 3041.92 | 3041.92
Build Functional Model | 2021-09-01 08:12 | 11.25 | 2021-09-16 10:12 | 36 | Complete | 8856 | 8856 | 1 | 8856 | 1 | 8856 | 11092.5 | 11092.5
Evaluate Design Specs | 2021-09-01 08:12 | 14.88 | 2021-09-21 16:14 | 36 | Complete | 6000 | 6000 | 1 | 6000 | 1 | 6000 | 8928 | 8928
PM Period 6 | 2021-09-01 08:12 | 10.25 | 2021-09-15 10:12 | 36 | Complete | 7056 | 7056 | 1 | 7056 | 1 | 7056 | 7995 | 7995
Milestone 6 | 2021-09-21 16:14 | 0 | 2021-09-21 16:14 | 22 | Complete | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0
Issue Sample | 2021-09-21 16:14 | 7.5 | 2021-10-01 11:14 | 22 | Complete | 3000 | 3000 | 1 | 3000 | 1 | 3000 | 4500 | 4500
Perform Supplier Process Capability | 2021-10-01 11:14 | 17.13 | 2021-10-26 13:17 | 14 | Busy | 6608 | 6608 | 1 | 6608 | 0.79 | 5220.32 | 7395.68 | 5842.5872
Develop Testing Protocol for Prototype | 2021-09-21 16:14 | 10.25 | 2021-10-06 09:14 | 22 | Complete | 3520 | 3520 | 1 | 3520 | 1 | 3520 | 4530.5 | 4530.5
PM Period 7 | 2021-09-21 16:14 | 12.5 | 2021-10-08 11:14 | 22 | Complete | 8624 | 8624 | 1 | 8624 | 1 | 8624 | 9750 | 9750
Milestone 7 | 2021-09-21 16:14 | 0 | 2021-09-21 16:14 | 22 | Complete | 0 | 0 | 1 | 0 | 0 | 0 | 35000 | 0
Approve Sample Parts | 2021-10-26 13:17 | 10.13 | 2021-11-09 14:19 | -5 | Busy | 4352 | 4352 | 1 | 4352 | 0 | 0 | 6078 | 0
Design Validation Activities | 2021-11-12 10:17 | 3.06 | 2021-11-16 16:02 | -18 | Busy | 2200 | 2200 | 1 | 2200 | 0 | 0 | 3188.5 | 0
Test Prototype | 2021-10-26 13:17 | 12.75 | 2021-11-12 10:17 | -5 | Busy | 6000 | 6000 | 1 | 6000 | 0 | 0 | 5635.52 | 0
Process Engineering Plan | 2021-10-26 13:17 | 17.63 | 2021-11-19 09:19 | -5 | Busy | 6000 | 6000 | 1 | 6000 | 0 | 0 | 9590.72 | 0
Show Functional Model at Trade Show | 2021-11-01 08:00 | 3.25 | 2021-11-04 10:00 | -9 | Busy | 2352 | 2352 | 1 | 2352 | 0 | 0 | 2535 | 0
PM Period 8 | 2021-10-26 13:17 | 3.38 | 2021-10-29 16:19 | -5 | Busy | 2352 | 2352 | 1 | 2352 | 0 | 0 | 2636.4 | 0
Milestone 8 | 2021-11-19 09:19 | 0 | 2021-11-19 09:19 | -23 | Busy | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0
Validation Design Review | 2021-11-19 09:19 | 4.75 | 2021-11-25 16:19 | -23 | Busy | 1968 | 1968 | 1 | 1968 | 0 | 0 | 2854 | 0
Approve Model Design | 2021-11-25 16:19 | 5.13 | 2021-12-03 08:22 | -27 | Busy | 1968 | 1968 | 1 | 1968 | 0 | 0 | 2267.46 | 0
Evaluate Test Results | 2021-11-19 09:19 | 7.38 | 2021-11-30 13:22 | -23 | Busy | 3600 | 3600 | 1 | 3600 | 0 | 0 | 4428 | 0
PM Period 9 | 2021-11-19 09:19 | 4.63 | 2021-11-25 15:22 | -23 | Busy | 3136 | 3136 | 1 | 3136 | 0 | 0 | 3611.4 | 0
Milestone 9 | 2021-12-03 08:22 | 0 | 2021-12-03 08:22 | -33 | Busy | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0
Qualify Supplier | 2021-12-03 08:22 | 12.5 | 2021-12-21 13:22 | -33 | Busy | 6000 | 3000 | 0.5 | 1500 | 0 | 0 | 7500 | 0 | 2021-10-14 | 5 | 10
Design Transfer Activities | 2021-12-03 08:22 | 8.25 | 2021-12-15 10:22 | -33 | Busy | 4200 | 3000.06 | 0.7143 | 2142.9429 | 0 | 0 | 4668 | 0 | 2021-10-14 | 5 | 7
Product Release Meetings | 2021-12-15 10:22 | 3.38 | 2021-12-20 14:24 | -41 | Busy | 3000 | 0 | 0 | 0 | 0 | 0 | 2636 | 0
Develop Production Plan | 2021-12-03 08:22 | 8.25 | 2021-12-15 10:22 | -33 | Busy | 2400 | 1999.92 | 0.8333 | 1666.5333 | 0 | 0 | 3646.5 | 0 | 2021-10-14 | 5 | 6
PM Period 10 | 2021-12-03 08:22 | 5.63 | 2021-12-10 14:24 | -33 | Busy | 3920 | 3920 | 1 | 3920 | 0 | 0 | 4391.4 | 0 | 2021-10-14 | 5 | 5
Milestone 10 | 2021-12-21 13:22 | 0 | 2021-12-21 13:22 | -45 | Busy | 0 | 0 | 1 | 0 | 0 | 0 | 10000 | 0
Totals | [6 empty] | 234048 |  | 244720 |  | 209404.32 |  | 230103.6672
CPI | 0.91
SPI | 0.8557
ETC | 27080.967
EAC | 257184.6342
Formulas:
Network Days to Analysis Date = NETWORKDAYS([Real Start Date],D3)
Network Days to Analysis Date = NETWORKDAYS([Planned Start Date],D3)

## Period 8
Period 6 |  | Analysis Date at 17:00
2021-11-15
Task | Real Start Date | Real Duration | Real End Date | Network Days to Analysis Date | Complete/Busy | Full Budget | Budget at Analysis Date | %Sched Completion | Planned Value | %Actual Completion | Earned Value | Actual Cost | Actual Cost at Analysis Date | Planned Start Date | Network Days to Analysis Date | Planned Duration
Evaluate Market | 2021-03-31 09:00 | 6.69 | 2021-04-08 15:31 | 164 | Complete | 7728 | 7728 | 1 | 7728 | 1 | 7728 | 8563.2 | 8563.2
Develop Business Opportunity | 2021-04-08 15:31 | 8.06 | 2021-04-20 16:00 | 158 | Complete | 9016 | 9016 | 1 | 9016 | 1 | 9016 | 10316.8 | 10316.8
Customer Preference Study | 2021-04-20 16:00 | 12.13 | 2021-05-07 08:02 | 150 | Complete | 13524 | 13524 | 1 | 13524 | 1 | 13524 | 14240 | 14240
Business Evaluation (NPV, etc.) | 2021-05-07 08:02 | 2.38 | 2021-05-11 11:05 | 137 | Complete | 2576 | 2576 | 1 | 2576 | 1 | 2576 | 4973 | 4973
PM Period 1 | 2021-03-31 09:00 | 18.06 | 2021-04-26 09:29 | 164 | Complete | 12300 | 12300 | 1 | 12300 | 1 | 12300 | 17771.04 | 17771.04
Milestone 1 | 2021-05-11 11:05 | 0 | 2021-05-11 11:05 | 135 | Complete | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0
Design and Development Plan | 2021-05-11 11:05 | 3.88 | 2021-05-17 10:07 | 135 | Complete | 2352 | 2352 | 1 | 2352 | 1 | 2352 | 3585.12 | 3585.12
Design Specs | 2021-05-17 10:07 | 13.75 | 2021-06-04 08:07 | 131 | Complete | 8624 | 8624 | 1 | 8624 | 1 | 8624 | 12705 | 12705
Develop Prelim Marketing Plan | 2021-05-11 11:05 | 2.81 | 2021-05-14 09:34 | 135 | Complete | 3220 | 3220 | 1 | 3220 | 1 | 3220 | 3596.8 | 3596.8
Develop Marketing Program | 2021-05-14 09:34 | 8.44 | 2021-05-26 14:05 | 132 | Complete | 9660 | 9660 | 1 | 9660 | 1 | 9660 | 10803.2 | 10803.2
PM Period 2 | 2021-05-11 11:05 | 10.06 | 2021-05-25 11:34 | 135 | Complete | 6888 | 6888 | 1 | 6888 | 1 | 6888 | 9889.04 | 9889.04
Milestone 2 | 2021-06-04 08:07 | 0 | 2021-06-04 08:07 | 117 | Complete | 0 | 0 | 1 | 0 | 1 | 0 | 5000 | 5000
Identify Testing Requirements | 2021-06-04 08:07 | 6.25 | 2021-06-14 10:07 | 117 | Complete | 3920 | 3920 | 1 | 3920 | 1 | 3920 | 5775 | 5775
Risk Analysis | 2021-06-14 10:07 | 7.06 | 2021-06-23 10:36 | 111 | Complete | 3920 | 3920 | 1 | 3920 | 1 | 3920 | 6523.44 | 6523.44
Train Sales Team | 2021-06-04 08:07 | 24.88 | 2021-07-08 16:10 | 117 | Complete | 11088 | 11088 | 1 | 11088 | 1 | 11088 | 12440 | 12440
Advertising Campaign | 2021-06-04 08:07 | 31.38 | 2021-07-19 11:10 | 117 | Complete | 21952 | 21952 | 1 | 21952 | 1 | 21952 | 24476.4 | 24476.4
PM Period 3 | 2021-06-04 08:07 | 10.13 | 2021-06-18 09:10 | 117 | Complete | 6888 | 6888 | 1 | 6888 | 1 | 6888 | 9967.92 | 9967.92
Milestone 3 | 2021-07-19 11:10 | 0 | 2021-07-19 11:10 | 86 | Complete | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0
Design Labelling | 2021-07-14 08:07 | 3.25 | 2021-07-19 10:07 | 89 | Complete | 1960 | 1960 | 1 | 1960 | 1 | 1960 | 3003 | 3003
Approve Design | 2021-07-19 10:07 | 2.63 | 2021-07-21 16:10 | 86 | Complete | 1568 | 1568 | 1 | 1568 | 1 | 1568 | 2430.12 | 2430.12
Initial Engineering Specs | 2021-07-21 16:10 | 2.88 | 2021-07-26 15:12 | 84 | Complete | 2460 | 2460 | 1 | 2460 | 1 | 2460 | 2839.68 | 2839.68
PM Period 4 | 2021-07-19 11:10 | 14.63 | 2021-08-09 08:12 | 86 | Complete | 10192 | 10192 | 1 | 10192 | 1 | 10192 | 11411.4 | 11411.4
Milestone 4 | 2021-08-09 08:12 | 0 | 2021-08-09 08:12 | 71 | Complete | 0 | 0 | 1 | 0 | 1 | 0 | -50000 | -50000
Design Verification Activities | 2021-08-09 08:12 | 4.19 | 2021-08-13 09:43 | 71 | Complete | 3444 | 3444 | 1 | 3444 | 1 | 3444 | 4131.34 | 4131.34
Verification Design Review | 2021-08-13 09:43 | 2.31 | 2021-08-17 13:12 | 67 | Complete | 1968 | 1968 | 1 | 1968 | 1 | 1968 | 2277.66 | 2277.66
Release Pre-Production Specs | 2021-08-17 13:12 | 6 | 2021-08-25 13:12 | 65 | Complete | 4920 | 4920 | 1 | 4920 | 1 | 4920 | 5916 | 5916
PM Period 5 | 2021-08-09 08:12 | 17 | 2021-09-01 08:12 | 71 | Complete | 11760 | 11760 | 1 | 11760 | 1 | 11760 | 13260 | 13260
Milestone 5 | 2021-09-01 08:12 | 0 | 2021-09-01 08:12 | 54 | Complete | 0 | 0 | 1 | 0 | 1 | 0 | 15000 | 15000
Identify Vendors | 2021-09-01 08:12 | 4.5 | 2021-09-07 13:12 | 54 | Complete | 2800 | 2800 | 1 | 2800 | 1 | 2800 | 3528 | 3528
Develop and Issue RFQ | 2021-09-07 13:12 | 3.88 | 2021-09-13 09:02 | 50 | Complete | 2400 | 2400 | 1 | 2400 | 1 | 2400 | 3041.92 | 3041.92
Build Functional Model | 2021-09-01 08:12 | 11.25 | 2021-09-16 10:12 | 54 | Complete | 8856 | 8856 | 1 | 8856 | 1 | 8856 | 11092.5 | 11092.5
Evaluate Design Specs | 2021-09-01 08:12 | 14.88 | 2021-09-21 16:14 | 54 | Complete | 6000 | 6000 | 1 | 6000 | 1 | 6000 | 8928 | 8928
PM Period 6 | 2021-09-01 08:12 | 10.25 | 2021-09-15 10:12 | 54 | Complete | 7056 | 7056 | 1 | 7056 | 1 | 7056 | 7995 | 7995
Milestone 6 | 2021-09-21 16:14 | 0 | 2021-09-21 16:14 | 40 | Complete | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0
Issue Sample | 2021-09-21 16:14 | 7.5 | 2021-10-01 11:14 | 40 | Complete | 3000 | 3000 | 1 | 3000 | 1 | 3000 | 4500 | 4500
Perform Supplier Process Capability | 2021-10-01 11:14 | 17.13 | 2021-10-26 13:17 | 32 | Complete | 6608 | 6608 | 1 | 6608 | 0.79 | 5220.32 | 7395.68 | 5842.5872
Develop Testing Protocol for Prototype | 2021-09-21 16:14 | 10.25 | 2021-10-06 09:14 | 40 | Complete | 3520 | 3520 | 1 | 3520 | 1 | 3520 | 4530.5 | 4530.5
PM Period 7 | 2021-09-21 16:14 | 12.5 | 2021-10-08 11:14 | 40 | Complete | 8624 | 8624 | 1 | 8624 | 1 | 8624 | 9750 | 9750
Milestone 7 | 2021-09-21 16:14 | 0 | 2021-09-21 16:14 | 40 | Complete | 0 | 0 | 1 | 0 | 1 | 0 | 35000 | 35000
Approve Sample Parts | 2021-10-26 13:17 | 10.13 | 2021-11-09 14:19 | 15 | Complete | 4352 | 4352 | 1 | 4352 | 1 | 4352 | 6078 | 6078
Design Validation Activities | 2021-11-12 10:17 | 3.06 | 2021-11-16 16:02 | 2 | Busy | 2200 | 2200 | 1 | 2200 | 0.71 | 1562 | 3188.5 | 2263.835
Test Prototype | 2021-10-26 13:17 | 12.75 | 2021-11-12 10:17 | 15 | Complete | 6000 | 6000 | 1 | 6000 | 1 | 6000 | 5635.52 | 5635.52
Process Engineering Plan | 2021-10-26 13:17 | 17.63 | 2021-11-19 09:19 | 15 | Busy | 6000 | 6000 | 1 | 6000 | 0.82 | 4920 | 9590.72 | 7864.3904
Show Functional Model at Trade Show | 2021-11-01 08:00 | 3.25 | 2021-11-04 10:00 | 11 | Complete | 2352 | 2352 | 1 | 2352 | 1 | 2352 | 2535 | 2535
PM Period 8 | 2021-10-26 13:17 | 3.38 | 2021-10-29 16:19 | 15 | Complete | 2352 | 2352 | 1 | 2352 | 1 | 2352 | 2636.4 | 2636.4
Milestone 8 | 2021-11-19 09:19 | 0 | 2021-11-19 09:19 | -5 | Busy | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0
Validation Design Review | 2021-11-19 09:19 | 4.75 | 2021-11-25 16:19 | -5 | Busy | 1968 | 1968 | 1 | 1968 | 0 | 0 | 2854 | 0
Approve Model Design | 2021-11-25 16:19 | 5.13 | 2021-12-03 08:22 | -9 | Busy | 1968 | 1968 | 1 | 1968 | 0 | 0 | 2267.46 | 0
Evaluate Test Results | 2021-11-19 09:19 | 7.38 | 2021-11-30 13:22 | -5 | Busy | 3600 | 3600 | 1 | 3600 | 0 | 0 | 4428 | 0
PM Period 9 | 2021-11-19 09:19 | 4.63 | 2021-11-25 15:22 | -5 | Busy | 3136 | 3136 | 1 | 3136 | 0 | 0 | 3611.4 | 0
Milestone 9 | 2021-12-03 08:22 | 0 | 2021-12-03 08:22 | -15 | Busy | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0
Qualify Supplier | 2021-12-03 08:22 | 12.5 | 2021-12-21 13:22 | -15 | Busy | 6000 | 6000 | 1 | 6000 | 0 | 0 | 7500 | 0
Design Transfer Activities | 2021-12-03 08:22 | 8.25 | 2021-12-15 10:22 | -15 | Busy | 4200 | 4200 | 1 | 4200 | 0 | 0 | 4668 | 0
Product Release Meetings | 2021-12-15 10:22 | 3.38 | 2021-12-20 14:24 | -23 | Busy | 3000 | 3000 | 1 | 3000 | 0 | 0 | 2636 | 0
Develop Production Plan | 2021-12-03 08:22 | 8.25 | 2021-12-15 10:22 | -15 | Busy | 2400 | 2400 | 1 | 2400 | 0 | 0 | 3646.5 | 0
PM Period 10 | 2021-12-03 08:22 | 5.63 | 2021-12-10 14:24 | -15 | Busy | 3920 | 3920 | 1 | 3920 | 0 | 0 | 4391.4 | 0
Milestone 10 | 2021-12-21 13:22 | 0 | 2021-12-21 13:22 | -27 | Busy | 0 | 0 | 1 | 0 | 0 | 0 | 10000 | 0
Assess RFQ Responses |  |  |  | 31796 | Complete | 6000 | 1200 | 0.2 | 240 | 0 | 0 |  |  | 2021-11-12 | 2 | 10
Develop Production Control Plan |  |  |  | 31796 | Complete | 3400 | 800.02 | 0.2353 | 188.2447 | 0 | 0 |  |  | 2021-11-12 | 2 | 8.5
Approve Production Parts |  |  |  | 31796 | Complete | 2000 | 0 | 0 | 0 | 0 | 0
Contracting for Deliveries |  |  |  | 31796 | Complete | 3200 | 492.16 | 0.1538 | 75.6942 | 0 | 0 |  |  | 2021-11-12 | 2 | 13
PM Period 11 |  |  |  | 31796 | Complete | 57200 | 0 | 0 | 0 | 0 | 0
Totals | [6 empty] | 266732.18 |  | 264743.9389 |  | 230942.32 |  | 292116.8126
CPI | 0.7906
SPI | 0.8723
ETC | 45269.2386
EAC | 337386.0512
Formulas:
Network Days to Analysis Date = NETWORKDAYS([Real Start Date],D3)
Network Days to Analysis Date = NETWORKDAYS([Planned Start Date],D3)